Summary of Proposed 2012 Amendment

to King County’s Long-Term Combined Sewer Overflow (CSO) Control Plan

| CSO Control Project and Discharge Serial Number (DSN) | Control Measure(s) | Description | Design Criteria | Performance Criteria in a Typical Year | Critical Milestones, | Estimated Project Cost Million Dollars 2010 |
| --- | --- | --- | --- | --- | --- | --- |
| 2012 King County Executive’s Recommended Projects to Control the County’s Remaining 14 Uncontrolled CSOs |
| Duwamish Waterway |
| Hanford #1 (DSN 03) | Increased conveyance & storage tank | Increased conveyance to the Bayview Tunnel and storage tank near Rainier Avenue | Up to 0.34 million gallons (MG) of peak CSO storage with conveyance | Reduce untreated overflow events to 1 per year on a 20-year moving average | Complete Facilities Plan—2014 Completion of Bidding—2016 Construction Completion—2019 | $19.2 |
| Brandon St/ S Michigan (DSN 039, 041) | CSO treatment | High rate clarification treatment to control CSOs along the East Waterway | Up to 66 million gallons per day (MGD) treatment facility and new conveyance system | Treat peak CSO flows to state standard of 50% total suspended solids (TSS) removal and disinfection, meet state water quality standards | Complete Facilities Plan—2015 Completion of Bidding—2017 Construction Completion—2022 | $139.7 |
| W Michigan/ Terminal 115 (DSN 038, 042) | Storage pipe | Storage pipe along West Marginal Way & Green Stormwater Infrastructure (GSI) | Up to 0.32 MG storage pipe. Mitigate up to 24% of the impervious area with RainWise and green streets | Reduce untreated overflow events to 1 per year on a 20-year moving average | Complete Facilities Plan—2020 Completion of Bidding—2022 Construction Completion—2025 | $14.8 |
| Chelan Ave (DSN 036) | Storage tank | Storage tank near West Duwamish Waterway | Up to 3.85 MG storage tank on West Duwamish Waterway near Chelan Avenue | Reduce untreated overflow events to 1 per year on a 20-year moving average | Complete Facilities Plan—2018 Completion of Bidding—2020 Construction C0mpletion—2023 | $51.7 |
| Hanford #2/ Lander/ King St/ Kingdome (DSN 028, 029, 030, 032) | CSO treatment | High rate clarification treatment facility in South Seattle neighborhood | Up to 151 MGD treatment facility and modifications to existing conveyance system | Treat peak CSO flows to state standard of 50% TSS removal and disinfection; meet state water quality standards | Complete Facilities Plan—2024 Completion of Bidding—2026 Construction Completion—2030 | $270.8 |
| Ship Canal |
| 3rd Ave West (DSN 008) | 1.Joint City-County storage tank OR 2. Independent County storage tank | 1. Storage tank on north side of Ship Canal OR 2. Storage tank near Seattle Pacific University ($56.4 million) | 1. Up to 7.23 MG of peak CSO storage OR 2. Up to 4.18 MG of peak CSO storage | Reduce overflow event at 1 County and multiple Seattle sites to 1 per year on 20-year moving average | Complete Facilities Plan—2018 Completion of Bidding—2020 Construction Completion—2023 | $51 |
| University (DSN 015) | 1. Joint City-County storage tank OR 2. Independent County storage tank | 1. Storage tank near University of Washington campus & GSI OR 2. Storage tank near University of Washington campus & GSI ($50.4 million) | 1. Up to 7.87 MG of peak CSO storage OR 2. Up to 2.94 MG of peak CSO storage Mitigate up to 24% of impervious area with RainWise and green streets | Reduce overflow event at 1 County and multiple Seattle sites to 1 per year on a 20-year moving average | 1. Complete Facilities Plan—2023 2. Completion of Bidding—2025 3. Construction Completion—2028 | $45.2 |
| Montlake (DSN 014) | 1. Joint City-County storage tank OR 2. Independent County storage tank | 1. Storage tank on south side of Montlake Cut & GSI OR 2. Storage tank on south side of Montlake Cut & GSI ($102.8 million) | 1. Up to 7.87 MG of peak CSO storage. OR 2. Up to 6.6 MG of peak CSO storage. Mitigate up to 19% of impervious area with RainWise and green streets | Reduce overflow event at 1 County and multiple Seattle sites to 1 per year on 20-year moving average | 1. Complete Facilities Plan—2023 2. Completion of Bidding—2025 3. Construction Completion—2028 | $95.4 |
| 11th Ave NW (DSN 004) | Increased conveyance | Increased conveyance to Ballard Siphon & GSI | Combination of up to 3,200 feet of 84-inch diameter pipe conveyance. Mitigate up to 26% of the impervious area with RainWise and green streets | Reduce untreated overflow events to 1 per year on a 20-year moving average | Complete Facilities Plan—2026 Completion of Bidding—2028 Construction Completion—2030 | $23.7 |

# Endnotes

Each CSO outfall is assigned a Discharge Serial Number or “DSN.”

“Completion of the Bidding” means WTD has (1) appropriately allocated funds for a specific CSO control project (or portion thereto); (2) accepted and awarded the bid for construction of the specific CSO control project; and (3) issued a notice to proceed with construction that remains in effect for the specific CSO control project.

“Construction Completion” means completion of construction and installation of equipment or infrastructure such that equipment or infrastructure has been placed in operation, and is expected to both function and perform as designed, as well as completion of in-situ modified operations and maintenance manuals. This specifically includes all control systems and instrumentation necessary for normal operations and all residual handling systems. For those specified CSO control projects consisting of separate components, “Construction Completion” shall be achieved when the last component is completed.

The estimated cost of each recommended CSO control project uses conceptual design information. The project cost estimates are planning-level only, for use in developing long-range capital schedules and budgets. The accuracy of planning-level estimates is -50 to +100 percent. The accuracy will increase as the Wastewater Treatment Division gains more site-specific information during project design and then a project budget will be set.

The County will consider a joint project with the City of Seattle when it benefits the community or ratepayers. At this time, the County is proposing a joint and independent project until the City of Seattle completes its long-term control plan and project recommendations in 2014.