Department of Executive Services

Public Safety Answering Point Oversight Committee Work Plan

A regional oversight committee charged with recommending a strategic plan for the implementation, governance and operation of the Next Generation 911 system in King County, to include proposed governance structures, operating rules and infrastructure for countywide Enhanced 911 operations.

June 30, 2015

Prepared for:

King County Council

Prepared by:

Department of Executive Services

Table of Contents

Introduction	1

Scope of Work	2

Objectives of the King County Regional Public Safety Answering Point (PSAP) Oversight Committee	2

Responsibilities of Committee Members, Facilitator, Project Coordination Team and Project Manager	5

Tasks, deliverables, milestones and budget	10

Project Coordination Team; members and responsibilities	13

Committee Membership	14

# Introduction

Ordinance 17941, which adopted the 2015/2016 King County Biennial Budget included proviso (P1) that states:

Of this appropriation, $500,000 shall not be expended or encumbered until the executive transmits an ordinance establishing the King County regional public safety answering point oversight committee and the ordinance is adopted by the council. The ordinance shall reference the subject matter, the proviso's ordinance, ordinance section and proviso number in both the title and body of the motion [sic].

The ordinance shall include, but not be limited to:

A. A description of the purpose, processes and role of the committee relative to recommending a strategic plan for the implementation, governance and operation of the Next Generation 911 system in King County, to include proposed governance structures, operating rules and infrastructure for countywide Enhanced 911 operations; and

B. Committee membership including the chair of the council, the vice chair of regional coordination of the council or the vice chair's successor, the chair of the law, justice, health and human services committee, or the committees successor, the executive or his designee, a city of Seattle elected official appointed by the mayor, three elected officials from other jurisdictions to be appointed by the council, a representative of the Sound Cities Association, a representative of a public safety agency, which is police, fire or emergency medical services, to be appointed by the council and a nonvoting technical and facilitation consultant selected by the executive.

The department of executive services and the office of performance, strategy and budget shall provide any necessary support to develop the ordinance required by this proviso.

The executive must file the ordinance required by this proviso by July 1, 2015, in the form of a paper original and an electronic copy with the clerk of the council, who shall retain the original and provide an electronic copy to all councilmembers, the council chief of staff, the policy staff director and the lead staff for the committee of the whole, or its successor.

This work plan addresses the requirements of Proviso 1 from Section 24 of Ordinance 17941.

# Scope of Work

This section outlines the scope of work, including the objectives, oversight committee membership, responsibilities of the facilitator/mediator, and key assumptions supporting the scope and budget.

## Objectives of the King County Regional Public Safety Answering Point (PSAP) Oversight Committee

The primary objective of the committee is to recommend to the King County Executive and Council a strategic plan for the implementation, governance and operation of the Next Generation 911 (NG911) system in King County.  This work will specifically include proposed governance structures, operating rules and infrastructure for countywide Enhanced 911 (E911) operations.  In addition to the full committee meetings, several sub committees may be formed to complete the work on this project.

The committee will undertake the following tasks:

- Receive background information on E-911; PSAPs; the local, state and national status of NG-911;  an overview of the work from the previous phases of the PSAP planning process; and the financial review and technical audit conducted by the King County Auditor’s Office.

Committee work: The committee will receive the following orientation:

- The 2015/2016 budget proviso;

- The role of PSAPs in public safety;

- The national vision for NG911;

- State implementation of NG911;

- The current state of NG911 in the County;

  - The major technical and operational components of NG911;

  - Changes and issues arising from the implementation of NG911;

- Current organizational structures of King County  and statewide E911 provision;

- Governance structure options;

- The body of work developed from previous efforts in the past four years to contribute to a common base of understanding of the current E911 structure, funding and operations within King County;

- An overview of the work of the recommendation committee established for the planning process in 2014; and

- The most recent work by the King County Auditor’s Office, which included a financial review and a technical audit of E911.

- Recommend components of a sustainable 10-year strategic plan for the E911 system and NG911 implementation in King County:

King County E911 Program funding and operations have been heavily effected by changing technology (e.g. the now-pervasive use of cellular phones and SMS messaging), and the different ways the public interacts with 911. To address these changes, the E911 Program Office and PSAPs have worked together to implement NG911 technology over the last decade. The Automatic Location Identification (ALI) Database, PSAP Mapping System, backroom E 911 equipment at the PSAPs, and the ALI displays at the PSAP call answering positions have been upgraded for NG911. The transition to a statewide NG911 network was completed in 2011. The chart below shows NG911 projects that have been completed or are in-progress.

Efforts will continue to ensure that King County’s system is capable of receiving 911 calls and data once NG911 service is commercially available. It is anticipated that the additional data and data distribution resulting from NG911 upgrades will increase system costs and staffing needs at PSAPs.  For example, text and data have different staffing requirements than voice calls, and this situation creates challenges for all PSAPs to handle these new demands. As a result, NG911 will be more expensive than E911 due to increased costs of new technology, additional services to the public and ongoing system operations.

The realities of NG911 costs, combined with the less-reliable 911 funding from wireless and VoIP technology, necessitate a collective recommendation for a service-driven, sustainable 10-year strategic plan.

King County E911 is in agreement with the King County Auditor’s recommendation to temporarily suspend implementation of new NG911 technology until a detailed NG911 implementation plan is completed.  King County E911 also agrees with the report recommendation to continue to implement those efforts that are nearly complete, interim text to 911 compliance with state mandatory security requirements, and SMART 911) and will work closely with PSAPs to implement these components..

Committee work: The plan will include recommendations on the following components:

  - Vision and Mission Statement for King County E911;

  - Guiding principles for the King County  E911 system;

  - Goals of the King County E911 system;

  - Governance for the regional organizational structure;

  - Organizational structure and rules for the regional system; and

  - Implementation steps: The committee will recommend steps needed to implement the strategic plan and a reasonable timeline and financially sustainable plan to achieve those steps. At a minimum, those steps will address the following issues:

    - NG911 infrastructure needs and investments;

    - Staffing and training needs and investments;

    - Transitional issues;

    - Recommended sustainable financial plan, built from a baseline budget; and

    - Scope, schedule and budget for implementation steps.

- Produce Recommended Strategic Plan

Committee work: Based on the recommendations per task #2 above, the committee will produce and submit to the Executive and Council a recommended strategic plan for the implementation, governance and operation of the E911 system in King County, including implementation of NG911.

## Responsibilities of Committee Members, Facilitator, Project Coordination Team and Project Manager

Committee: (Established by ordinance with membership approved by the King County Council);  The Committee is responsible for recommending a strategic plan for the implementation, governance and operation of the Next Generation 911 (NG911) system in King County and proposed governance structures, operating rules and infrastructure for countywide Enhanced 911 (E911) operations.

Facilitator: (A non-voting committee member selected by the Executive); The Facilitator will have the overall responsibility for working with Committee members, laying the process foundation, building the framework for consensus and guiding the Committee towards producing a recommended strategic plan as directed by the proviso. The Project Manager will be responsible for managing the contract with the Facilitator.

Project Team and Project Manager: The Project Manager is primarily responsible for directing the work of the Facilitator, ensuring the Facilitator has support for a successful process and for leading the Project Team.  The Project Manager will report to the Department of Executive Services. The Project Team is an internal King County staff team from the Executive and Council branches, formed to provide input and support to the Project Manager and Facilitator.

| Task | Committee | Facilitator | Project Team & Manager |
| --- | --- | --- | --- |
| Lay the Process Foundation |  |  |  |
|  | Participate in initial interviews with Facilitator and: Express opinions, perspectives, and interests. Identify possible solutions that might be proposed during the meetings. | Conduct initial interviews with Committee members and: Understand their opinions, perspectives, and interests. Learn of possible solutions that they may propose during the meetings. Ensure members are comfortable with and supportive of the process. | Assist with developing interview script to be used by facilitator |
|  | Establish by-laws | Work with Project Manager to develop a detailed work plan, budget and schedule. | Project Manager - Work with facilitator to develop a detailed work plan, budget and schedule. |
|  |  | Review draft materials |  |
|  |  | Work with Project Coordination Team to define topics that will be a part of the committee process and those that will be addressed in the Strategic Plan. |  |
|  |  | Draft and finalize the letter that invites the committee members. |
|  |  | Provide a memo that summarizes general themes of the interviews |  |
|  |  | Work with Project Coordination Team to brief, review, provide input on, and organize a background notebook of information for committee members. | Provide materials for background notebook that will help guide the discussion in this process; Review this notebook with facilitator, and recommend additions and changes; |
|  |  | Work with Project Coordination Team to create an overall schedule to achieve the objectives of the committee and establish specific agendas for committee meetings. | Project Manager: Establish agendas for Committee meetings; Prepare agendas for meetings with Project Coordination Team, in consultation with the facilitator. |
|  |  | Coordinate with Project Coordination Team to review and comment on meeting materials and presentations. | Assist facilitator with creating meeting materials and presentations |

| Task | Committee | Facilitator | Project Team & Manager |
| --- | --- | --- | --- |
| Build the Framework of Consensus |  |  |  |
|  | Attend seven Committee meetings between September and February. Meetings are anticipated to be three hours each. | Prepare for, convene, facilitate and follow up on committee meetings. |  |
|  | Attend additional meetings as needed. |  |  |
|  | Communicate as needed with Facilitator between meetings. | Propose committee ground rules and procedures, and finalize those with members. |  |
|  |  | Build positive working relationships with committee members Communicate as needed with committee members between meetings to build relationships, maintain their engagement and move the group toward objectives. |  |
|  |  | Schedule special committee meetings and subcommittee meetings, if any. |  |
|  |  | Provide all materials and logistic support for meetings. Provide logistic support for all committee meetings – i.e. secure and schedule meeting locations, provide name tags and name tents, provide flip charts and easels, provide sign-in sheets, copying and distribution of materials related to the committee work – i.e. background notebooks, briefing materials and all hard copy materials. |  |
|  |  | Provide refreshments, as appropriate, and any necessary audio/visual aids. |  |
|  |  | Draft meeting notes that include next steps and action items, including deadlines and assignments, from each meeting. | Establish parameters of meeting notes. |
|  |  |  | If meeting summaries are prepared for the Project Coordination Team meetings, they will be prepared by County staff. |
|  |  | Project Coordination Team will be responsive to requests for information and analysis from committee members and the public. Facilitator will work with the Committee and County staff to insure that volume and type of requests are reasonable. |
|  |  |  | Attend and support Project Coordination Team meetings with Facilitator. |
|  |  | Prepare meeting summaries of the key discussions, decisions and agreements, and distribute to members for comment and correction in a timely manner sufficient for members’ review. Edit meeting summary, if needed, then re-distribute the finalized summary of the meeting with the draft agenda for the next session. |  |
|  |  | Propose and help committee evaluate potential recommendations. |  |
|  |  | Attend Project Coordination Team meetings with King County staff. | Attend and support Project Coordination Team meetings with Facilitator. |
|  |  | Coordinate with King County staff as necessary. |  |

| Task | Committee | Facilitator | Project Team & Manager |
| --- | --- | --- | --- |
| Draft and finalize the Recommendations |  |  |  |
|  | Develop and strive to reach consensus on a recommended 10-year Strategic Plan. |  |  |
|  | Review and approve final report. | Prepare a summary report that documents the process, information provided to the Committee, Committee discussion summaries and the consensus recommended 10 year Strategic Plan, implementation steps and timeline. Circulate the draft report to all participants and stakeholders, and solicit comments. Include dissenting comments, if any | Support preparation of a summary report that documents the process, information provided to the committee, committee discussion summaries and the consensus recommendations. |
|  |  | In conjunction with Project Coordination Team, produce the final consensus report to be presented to the Committee for approval |
|  |  | Work with Project Coordination Team to prepare presentation materials and messaging pieces. |
|  | Coordinate with the committee and Project Coordinator on how the recommendations should be presented to the King County Executive, King County Council and others as appropriate. |

# Tasks, deliverables, milestones and budget

The table below outlines the tasks involved in supporting the Committee, and tentative deliverables milestones.

| Tasks | Deliverables | Responsibility | Milestones |
| --- | --- | --- | --- |
| Lay the Process Foundation |  |  |
| Prepare & Reach Agreement on Scope of Work and Schedule | Final scope of work, budget and schedule | Facilitator | July 30, 2015 |
|  | Final invitation letter to committee members | Facilitator | July 30, 2015 |
| Initial communication with Committee Members | Initial interviews w/committee members | Facilitator | August 2015 |
|  | Memo that summarizes members interests | Facilitator | August 28, 2015 |
|  | Statement of key findings and mutual interests | Facilitator | August 28, 2015 |
| Set up Committee meetings and framework | Schedule meetings for Committee, and Project Coordination Team | Facilitator | August 3, 2015 |
|  | Provide all materials, logistic support for meetings | Facilitator | Ongoing |
| Prepare initial materials for committee | Create background notebook | Project Manager | August 17, 2015 |
|  | Review and shape background notebook | Facilitator | August 28, 2015 |
| Prepare Materials for Committee Meetings | Work with Project Coordination Team to prepare and establish committee meeting agendas | Facilitator | 1-2 times per month |
|  | Prepare meeting materials, presentations | Facilitator | 1-2 times per month |
|  | Review and comment on meeting agendas, materials and presentations | Facilitator | 1-2 times per month |

| Tasks | Deliverables | Responsibility | Milestones |
| --- | --- | --- | --- |
| Build the Framework of Consensus |  |  |
| Facilitate Committee Meetings | Prepare for, facilitate and follow-up on committee meetings | Facilitator | 1-2 times per month |
|  | Prepare ground rules | Facilitator | August 28, 2015 |
|  | Prepare and distribute meeting summaries | Facilitator | 1-2 times per month |
|  | Handle meeting logistics, materials preparation | Facilitator | Ongoing |
| Ongoing communication with committee members | Build relationships with committee members | Facilitator | Ongoing |
|  | Communicate with members between meetings | Facilitator | 1-2 times per month |
|  | Respond to requests for information | Project Coordination Team | Ongoing |
| Facilitate Sub-committee meetings (if needed) | Facilitate and support sub-committees as needed | Project Manager | As needed |
| Communication w/ Staff | Project Coordination Team logistics | Facilitator | 1-2 times per month |
|  | Attend Project Coordination Team | Facilitator, Project Manager, Project Coordination Team | 2-4 times per month |
|  | Coordinate with County Staff as needed | Facilitator | Ongoing |
| Finalize the Recommendations |  |  |
| Prepare Final Recommended Strategic Plan | Draft outline of draft recommended strategic plan | Facilitator | November 20, 2015 |
|  | Draft, support preparation of recommended strategic plan | Facilitator/Project Coordination Team | December 15, 2015 |
|  | Prepare final recommended strategic plan | Facilitator/Project Coordination Team | February 1, 2016 |
| Participate in Briefings and updates of Executive, Council and Other Stakeholders | Prepare presentation materials summarizing committee work | Facilitator | February 29, 2016 |
|  | Presentations to stakeholders as needed | Facilitator | As needed |
|  | Total Estimated Facilitation Budget : $125,000 |

Proposed Schedule

This proposed schedule is subject to change based on planning with facilitator once a contract is executed.

# Project Coordination Team; members and responsibilities

Project Coordination Team: This team’s role is to assist the facilitator with planning and preparation of materials and agendas for upcoming meetings and debriefs of past meetings.  Plan to meet the Friday after each committee meeting and one or two weeks prior.

| Name | Title | Responsibility | Group/Agency/Councilmember |
| --- | --- | --- | --- |
| TBD | Facilitator | (see previous tables) |  |
| TBD | Project Manager | Facilitator & Project Support | Dept. of Executive Services |
| Lise Kaye | Senior Legislative Analyst | County Legislative Policy Liaison | Central Council Staff |
| Marlys Davis | E-911 Manager | E-911 Program Subject Matter Expertise | E-911 Staff |
| Jody Woodcock | Deputy Director | Emergency Management Policy Expertise | Emergency Management |
| Tom Koney | Deputy Director | Department-Level Policy Expertise | Dept. of Executive Services |
| Helene Ellickson | Budget Manager | County-level Financial Policy Guidance | Performance, Strategy and Budget |
| Diane Carlson | Director Regional Initiatives | Executive Office Strategic Direction | Executive’s Office |

# Committee Membership

Committee membership was specified in the P1 proviso.  Two additional members are being recommended by the Executive.  One position to allow for both a fire and police representative to serve on the Committee and a second position providing for an elected law enforcement official.

Members will be selected to provide a balanced representation of providers and customers of small and large PSAPs including consideration of geographic representation.  Representatives will be identified through consultation with stakeholders and will be recruited by the Executive’s office. The final membership will be transmitted separately and confirmed by the King County Council through the passage of a companion motion.

| Position/Representation | Name | Designated by |
| --- | --- | --- |
| Council Chair |  | Proviso |
| Vice Chair Regional Coordination |  | Proviso |
| Chair Law Safety Justice Committee |  | Proviso |
| Executive or designee |  | Executive per Proviso |
| Seattle Elected Official |  | Appointed by Seattle Mayor per Proviso |
| Elected Official other jurisdiction |  | Appointed by King County Council per Proviso |
| Elected Official other jurisdiction |  | Appointed by King County Council per Proviso |
| Elected Official other jurisdiction |  | Appointed by King County Council per Proviso |
| SCA Representative |  | Appointed by SCA per Proviso |
| Police or Fire Representative |  | Appointed by King County Council per Proviso |
| Executive Recommended additional positions |  |  |
| Elected Official Law Enforcement |  | Appointed by King County Council |
| Fire Representative |  | Appointed by King County Council |
| Non-voting Member |  |  |
| Facilitation Consultant | TBD | Selected by Executive |