## STAFF REPORT

| Agenda Item: | 8 | Name: | Beth Mountsier |
| --- | --- | --- | --- |
| Proposed No.: | 2016-B0091 | Date: | May 4, 2016 |

SUBJECT

A briefing and update on the Georgetown (formerly Brandon and Michigan) Combined Sewer Overflow (CSO) Control project to be constructed and operated in compliance with the Long Term CSO Control Program as approved by the Council and the Executive in fulfillment of the obligations of a consent decree with the United States Environmental Protection Agency (EPA)  and the Washington State Department of Ecology (Ecology) to control CSOs in the King County wastewater treatment conveyance system by 2030.

SUMMARY

The Georgetown Wet Weather Treatment Station (WWTS) will address the Brandon and Michigan CSO basins that collect sewage and stormwater and convey the combined influent to the West Point Treatment Plant.  Each basin currently has a combined sewer overflow pipe that discharges more frequently than allowed by EPA and Ecology, exceeding the average of one discharge per year into the Duwamish River.

King County proposed in its updated 2012 CSO Control Plan – to meet the EPA and State of Washington’s CSO control standards by building and operating a wet-weather treatment plant to handle the flows within both basins and treating the wastewater/influent during overflow conditions.  Discharge of the treated wastewater to the Duwamish River is planned to occur at a new discharge location and the water discharged would meet certain standards as approved by EPA and Ecology.  The current overflow pipes from each basin for Brandon and Michigan would also remain and would be required to not overflow more than once per year.

The purpose of this briefing is to have the Wastewater Treatment Division (WTD) report on progress towards the consent decree milestones and ultimate completion of the Georgetown WWTS project, as required by the consent decree.

The project recently reached 30% design completion.  WTD staff are anticipated to report on the project design and the base-lined cost-estimates for the project.   The current design is within the projected cost range presented to the Council in fall 2014, when the project was subject to additional scrutiny following a performance audit issued by the Auditor’s Office.

BACKGROUND

Consent Decree and Long-term CSO Control Plan

EPA and Ecology alleged that the County violated Sections 301 and 402 of the Clean Water Act (“CWA”) and the conditions and limitations of the County’s National Pollutant Discharge Elimination system (“NPDES”) permit issued to the County by Ecology.  These are violations related to the quality of the effluent released from CSO control facilities that act as satellite treatment plants to West Point Treatment Plant.    In response, King County, without admitting any liability related to the alleged violations, negotiated a consent decree with EPA and Ecology that the Regional Water Quality Committee recommended and the Council approved via adoption of Proposed Ordinance 2012-0459 (Ordinance 17413) in the first quarter of 2013.

The consent decree obligates King County and its Wastewater Treatment Division (“WTD”) to implement the long-term CSO control plan that the Council approved in September 2012 for future projects per the proposed design criteria/specifications and schedule in the plan, including final completion of all projects in 2030.  In addition, the consent decree provides direction for 1) implementation of CSO control projects were currently in design 2) improvements in operations of existing CSO treatment plants to meet effluent standards, 3) various reporting requirements regarding progress towards these goals, post-construction monitoring, etc., 4) dispute resolution procedures and 5) penalties.

The Long Term CSO Control Plan guides one of the most significant capital improvement projects in terms of significant   investments that re required by 2030.  The CSO Control plan via a program review, was last updated in 2012; updates are anticipated approximately every five years (in conjunction with the renewal of the NPDES permits for West Point Treatment Plant.  The Regional Wastewater Services Plan (RWSP) policy and state administrative code requirements address frequency and substance requirements for the plan amendments and program review.  The RWSP also speaks to Regional Water Quality Committee (RWQC) and Council review opportunities.  The RWQC was briefed on these reviews and program updates at its April meeting (Briefing 2016-B0073).

Georgetown WWTS project

In October 2014 RWQC was briefed on all of the CSO projects that were addressed in the consent decree with special attention and additional information regarding the Georgetown project provided by the King County Auditor’s Office and the WTD Director (at the time), Pam Elardo.

At that October meeting there was a briefing and discussion of a September 2014 report from the King County Council’s Auditors Office (“Performance Audit of the Georgetown Combined Sewer Overflow Project, Sept 9, 2014”) regarding the planned wet weather treatment plant now called the Georgetown WWTS – which will be handling the two CSO basins and outfalls at Brandon and Michigan.

The County Council had been concerned about the cost growth of the CSO program, as planning-level estimates provided to the County Council in the 2012 CSO Control Plan were double previous planning-level estimates.  The purpose of the audit (that was added to the Auditor’s work program for 2014) was to focus on one of the first projects to be executed under the consent decree - the Georgetown CSO project and review how the Wastewater Treatment Division manages projects in the early development phase when significant cost growth has occurred on CSO projects in the past.

The Auditor’s Office had concluded that:

The Wastewater Treatment Division (WTD) has some best practices in place for managing large capital projects. However, WTD selected its preferred alternative for controlling sewer overflows in the Georgetown area based on insufficient analysis of alternatives. Project costs are expected to increase substantially, and WTD lacks mechanisms to control project cost growth in early project development phases. We recommend that WTD consider alternatives to the projects identified in the Combined Sewer Overflow Control Plan, develop performance measures, and provide additional oversight to control project cost growth and minimize potentially substantial program cost and rate increases.

The Wastewater Treatment Division concurred with the findings and recommendations of the Auditor’s Office, in part because in advance of the Audit Report being released at the September 9, 2014 report to the Council’s Government Accountability and Oversight (GAO) Committee – the Director of the Department of Natural Resources and Parks, Christie True had already suspended the Georgetown Project in July 2014 and ordered an independent review of the project by consultants not previously associated with the project.

WTD had selected Carollo Engineers, Inc. to conduct the evaluation and report back to the DNRP Director.  Carollo submitted its final report to King County on October 10, 2014 during the middle of 2015-16 budget deliberation by the King County Council.  Because of the concerns with regard to possible construction costs of the project in excess of the cost estimate ranges presented to the Council at the time that the CSO Control Plan was approved by the Council in 2012 – the Georgetown project was of particular interest as component of the 2015-16 capital budget for WTD.

Council staff with assistance from a team of staff from the Auditor’s Office reviewed the Carollo report during budget deliberations and made recommendations to the Council via verbal and written briefings to Physical Environment Panel and the Council’s Budget Leadership Team (BLT).

Based on these briefings and interviews with WTD’s consultants/engineers (CH2MHill) on the Georgetown Project, council staff and BLT recommended to the full Council the inclusion of a budget proviso (quoted below) to direct WTD’s engineers and consultants to include additional analysis of several aspects of the Georgetown project as recommended by Carollo Engineers.  And, additionally retaining an independent ‘expert review panel’ for at least the next two years to review the work of WTD with regard to these additional analyses for Georgetown in particular, but also to advise with regard to other pending CSO projects and the conveyance system to potentially improve or revise project designs to optimize the investments in CSO Control projects.

The budget proviso (in part) reads (beginning on line 20153 of Ordinance 17941):

P3 PROVIDED FURTHER THAT:

Of this appropriation, $250,000 shall not be expended or encumbered until the executive transmits a detailed work plan for utilizing an expert review panel to provide review and recommendations regarding optimization, cost control measures, risk management and risk mitigation for combined sewer overflow ("CSO") control projects and the wastewater conveyance and treatment system and a motion approving the plan and the motion is passed by the council. The motion shall reference the subject matter, the proviso's ordinance, ordinance section and proviso number in both the title and body of the motion.

A. The expert review panel shall:

- Review and make technical recommendations to the executive and council

- regarding the Georgetown wet weather treatment plant project;

- Make its recommendations based on existing and new technical analyses that shall include:

- the October 10, 2014, Carollo Engineering, Inc., report and recommendations regarding the design and construction of the Georgetown wet weather treatment plant;

- potential redefinition of CSO basin boundaries to ensure optimization and correct sizing of treatment plants and storage throughout the combined system of wastewater and stormwater collection;

- the feasibility of isolating or separating the sanitary sewer system from the existing combined system where appropriate;

- additional consideration of upstream improvements to divert storm water 2075 flows from the CSO system; and

- Review King County's other pending CSO control projects to identify options for optimization, cost control, risk management and risk mitigation, noting which projects would be the highest priority for alternatives analysis;

- Consist of five to seven experts in the field of combined sewer overflow

management and project design, construction and implementation; and

- Meet at least quarterly.

The Council (and RWQC) approved the selection of a CSO Expert Review Panel and their work plan in spring 2015.    Their first report to the RWQC and Council occurred in fall 2015 and affirmed the selection of a wet weather treatment plant to control overflows for Brandon and Michigan and also provided some recommendations as the project continued through the design process.

Issue Identification and History on Investigation(s) and Analysis in 2014

As noted above, the County Council has been concerned about the cost growth of the combined sewer overflow (CSO) control program, as planning-level estimates provided to the County Council in the 2012 CSO Control Plan were double previous planning-level estimates reported in the RWSP Annual Reports.   Up until 2012, the remaining 14 uncontrolled CSOs were expected to cost approximately $300 million.  Instead, the 2012 proposed update to the CSO program and projects pegged the total costs at $700+ million (with a planning range that was $350 million to 1.4 billion).

Based on this concern, the Council directed a Performance Audit for the initial stages of design and property acquisition for the Georgetown Wet-Weather Treatment Plant (WWTP) Project.   Work was started in February 2014 with Auditor’s Office staff meeting with WTD staff and collecting materials through the first two quarters of the year.  In July 2014 Auditor’s Office staff presented draft conclusions to WTD and Department of Natural Resources leadership.

In advance of the Auditor’s Office Performance Audit of the first stage of the Georgetown Project, released on September 9 – Christie True, Director, Department of Natural Resources and Parks, suspended the Georgetown CSO Project at the end of July 2014 and ordered an independent WTD consultant review of the project by local engineers not previously associated with the project.

Carollo advised that the proposed Georgetown WWTP was the least costly engineering solution and would best meet the scheduled deadlines for EPA’s consent decree.  In making this judgment, Corolla used the materials provided to them by WTD supplemented by interviews with WTD and CH2M Hill staff.  The Carollo analysis only considered the past work by King County and other consultants and did not consider any other engineering solutions which might have been analyzed in the early project planning phase.

Based on WTD’s consultant report (Carollo and sub-consultants) it the DNRP Director has directed the Wastewater Treatment Division capital project team to proceed with the design and construction of a wet weather treatment plant, as approved by the Council in 2012 and incorporated into a consent decree with EPA/DOJ in 2013.

Based on the schedule and the anticipated interests of regulators (EPA and Ecology) that it consideration of alternatives (should they have appeared promising) to a WWTS to control the combined sewer overflows (CSOs) in the Brandon and Michigan CSO basins, would have been nearly impossible, given the schedule.  However; the Council provided direction in the 2015-16 biennial budget to meet additional objectives with this project (i.e. cost savings, risk mitigation and benefits to ‘downstream’ projects) and provided additional Council oversight by making plans to retain an ‘expert review panel’.

Staff Team Analysis as part of 2015-16 budget deliberations:

Assumptions:

- It was not possible to amend the December 31, 2015 timeline for submittal of a completed “facilities plan” for the Georgetown project to the US EPA and Department of Ecology.

- The Metropolitan King County Council should not pursue a course of project study and implementation which would significantly cause delays which might trigger EPA and DOE penalties for schedule noncompliance.

- There was insufficient time to develop a “facilities plan” for any alternative(s) to the proposed Georgetown project in time to meet the current December 31, 2015 consent decree deadline; nor was an alternative recommended based upon the Carollo review of the project options/alternatives.

- There was insufficient time to negotiate an extension of the December 31, 2015 consent decree deadline for the Georgetown project for any alternative project strategy.

Conclusions:

- There was not time to change course on the proposed Georgetown wet weather treatment plant project as proposed by WTD, but there was time to optimize the design based on Carollo Engineers, Inc. recommendations.

- Consent decree deadlines include a December 31, 2015 submittal of a “facilities plan” to EPA and Ecology; a Completion of Bidding milestone of December 31, 2017; and a requirement for Construction Completion by December 31, 2022. The consent decree also mandates a March, 2016 submittal requirement for a joint City of Seattle / King County WTD coordinated compliance plan.

- The Carollo report did not provide enough technical evidence to alter course and pursue other project alternatives; and in fact appeared to substantiate initial WTD assertions that the project as proposed, was/is the best alternative going forward.

- If pursued in a timely manner, the option of investigating project alternatives for the remaining CSO projects through a “parallel path” of independent engineering analysis should be considered for the most complex and highest risk remaining projects.

BACKGROUND REGARDING CSO PROJECTS AND THE CONSENT DECREE

The overall goal of the consent decree and EPA’s compliance action is to ensure that combined sewer overflows at King County’s outfalls occur on average only once per year based on a rolling 20-year average and that the effluent discharged from CSO control treatment plants meet certain standards.

The consent decree contains some provisions for ‘flexibility’ with regard to the implementation of King County’s long term combined sewer overflow control plan.  King County may propose changes to the design specifications for projects, the priority and sequencing of projects and may propose a supplemental ‘integrated plan’ that includes additional activities or refines the proposed CSO control projects to address other water pollution issues and thereby results in better water quality in the receiving waters where CSOs currently discharge.

The consent decree also includes payment of a civil penalty totaling $400,000 with half paid to EPA and half paid to Ecology. By agreeing to the consent decree and paying the penalty, all potential liabilities related to past violations of existing NPDES permits are discharged and King County is also held harmless from third party lawsuits, related to past or potential future violations.  However, there are stipulated penalties (with payments to EPA and Ecology) should King County fail to comply with the consent decree with regard to completing the specified projects (including meeting various milestones), improving the operations of existing facilities, achieving effluent standards, and meeting reporting requirements.

Combined Sewer Overflows

Combined sewer overflows are discharges of untreated or partially treated sewage and stormwater released directly into marine waters, lakes and rivers during heavy rainfall, when the sewers have reached their capacity.   Although the sewage in CSOs is greatly diluted by stormwater, both CSOs and stormwater may be harmful to public health and aquatic life because they carry chemicals and disease-causing pathogens.

From the late 1800s through the 1940s, engineers designed combined sewers (sewers that carry sewage and stormwater runoff in a single pipe) to convey sewage, horse manure, street and rooftop runoff, and garbage from city streets to the nearest receiving body of water.   Around the 1950s, most sewer systems were built as separated systems (sewage in one pipe; stormwater in another pipe). In the late 1950s, treating wastewater became the standard. Interceptor pipes were built to transport all wastewater (from either combined or separated systems) to treatment plants.

Combined sewers exist in many parts of older cities, including Seattle. During heavy or long storms, the volume of the stormwater runoff may become too much for the combined sewers to handle. To protect treatment plants and avoid sewer backups into homes, businesses and streets, combined sewers sometimes overflow into Puget Sound, the Duwamish Waterway, Elliott Bay, the Lake Washington Ship Canal and Lake Washington.

Both King County and the City of Seattle manage CSOs within Seattle. King County's Wastewater Treatment Division manages 38 locations and Seattle Public Utilities manages more than 90.  King County also has four CSO treatment plants, one in north Seattle (Carkeek Park CSO Treatment Plant) and one in West Seattle (Alki CSO Treatment Plant), and the new Mercer/Elliott West and Henderson/MLK facilities (see map below).

Clean Water Act and CSO Control Planning and Implementation in King County

The federal Clean Water Act was adopted in 1972.  Its objective is to restore and maintain the integrity of the nation’s waters with two primary goals of eliminating discharges of pollutants into the nation’s waters and achieving/maintaining swimmable and fishable waters. The Clean Water Act requires all wastewater treatment facilities and industries that discharge effluent into surface waters to have a National Pollutant Discharge Elimination System (NPDES) permit.  The Washington State Department of Ecology (Ecology) issues the permit as a vehicle for setting limits on the quality and quantity of effluent discharged from point sources such as treatment plants, CSOs, and industrial facilities.  King County holds NPDES permits for the West Point, South, and Vashon Treatment Plant.

By 1979 King County (under the auspices of “Metro”, prior to the merger) was planning for CSO control projects. Metro’s CSO control program was first formalized with the development of the 1979 Combined Sewer Overflow Control program, which identified nine projects to control sewer overflows into fresh water areas of Lake Washington, Lake Union and the Ship Canal.

In 1984, Ecology introduced legislation requiring agencies with CSOs to develop plans for the “greatest reasonable reduction [of CSOs] at the earliest possible date.”  In 1987 the greatest reasonable reduction was defined as “control of each CSO such that an average of one untreated discharge may occur per year.”    In the following year, Metro published the “Final 1988 Combined Sewer Overflow Control Plan” which addressed control alternatives for the remaining CSOs discharging to the Ship Canal, Duwamish River and Elliott Bay.  The County subsequently prepared an update/amendment of the 1988 Plan in 1995 that included an assessment of the effectiveness of CSO reduction efforts to date, a re-evaluation of priority for CSO control projects and a list of three projects the County intended to implement in the following five years.

In 1999 King County adopted the Regional Wastewater Services Plan (“RWSP) to update its policies and describe wastewater projects to be built to protect human health and the environment, provide sufficient wastewater treatment capacity and conveyance for anticipated population growth and meet regulatory requirements.  It established policies for completing CSO control by 2030 and identified 21 projects, that when completed, were to bring all County CSOs into compliance.

In 2000, King County produced an update to the 1988 Plan entitled the Year 2000 CSO Control Plan Update.  It summarized King County’s progress on its CSO projects and was approved by Ecology as amendment to the CSO reduction plan.

A CSO program review in 2005-2006 reaffirmed the RWSP priorities of protecting public health, the environment and endangered species that are the foundation of the CSO control program.  The review also reinforced the environmental and operational benefits of transferring as many CSO flows as possible to regional treatment plants for best available treatment prior to discharge.

The 2008 CSO Control Plan Update described the county’s wastewater system and the control status of its CSOs, indicated how the county was meeting the EPA’s Nine Minimum Controls, and summarized the scientific studies that had shaped the control program over time. The update also described completed, in progress, and planned CSO control projects, available CSO control strategies, and how these strategies applied to county projects.

Most recently, King County adopted the 2012 CSO Control Plan Update and an amendment to its long term combined sewer overflow control plan (Ordinance 17413) to be submitted to Ecology with the next NPDES permit renewal for West Point.  It was developed to provide the blueprint and updated schedule for construction of projects to address the remaining CSO outfalls that do not meet state standards. It was also understood that the approved 2012 CSO plan would become part of the consent decree with EPA and Ecology.

To date, out of the thirty-eight CSO sites in the regional wastewater system, sixteen of the sites are controlled to the Department of Ecology’s standard of no more than one overflow per year.  Of the remaining CSO locations, three are being refined and adjusted to meet the control standard, five CSO control projects are currently in design.  Fourteen sites remain uncontrolled and are addressed through nine projects (2 treatment plants and 7 storage facilities) in the 2012 Update and incorporated into the consent decree as Appendix B.   An illustration of the remaining projects is below.

Significant progress has been made to meet federal and state CSO control standards.  Thus far approximately $389 million has been spent to reduce untreated wastewater and CSO volumes from over 2 billion gallons per year in 1980 to 800 million gallons per year.  Completion of the five projects currently in design is estimated to cost $100 million.  The nine remaining projects have a very preliminary cost estimate of $711 million.

Environmental Protection Agency Policy Compliance and Enforcement

Based on a 2004 report to Congress noting the lack of progress in many communities, the U.S. Environmental Protection Agency (‘EPA’) stepped up its efforts in nearly all major metropolitan areas to ensure that long-term control plans were being implemented.  EPA has been systematically auditing and then enforcing compliance across the country via consent decrees which mandate CSO control actions.

Though King County has successfully controlled about half of its 38 CSOs since the 1980s and was only slightly off its schedule to complete control of all CSOs by 2030, EPA began a compliance review of the County’s wet weather management programs in 2008.  The County met with EPA and its contractors several times and by December 2010 the County presented an analysis of the Ecology performance or control standard to EPA’s presumptive standards for system control.  WTD had also submitted an overview of the process and milestones of its CSO Program Review (that had started in 2009 and was scheduled to conclude with Council action in 2012).   In mid-2011, EPA and the U.S. Department of Justice and the County began discussing potential elements of a consent decree as a start to negotiations.  Conversations and technical meetings with EPA, its contractor and the Department of Justice (DOJ) continued to occur through 2012 with the understanding that the County’s proposed (now adopted) 2012 Long-term CSO Control Plan Amendment met EPA’s requirements and would be referenced as a part of a consent decree.

Consent Decree

A consent decree is a written agreement between all parties to a potential law suit or complaint that describes the actions that must be taken to resolve the alleged violations of law.  In this case the parties are EPA and DOJ and the Washington State Department of Ecology (Ecology) and King County.  A consent decree avoids the cost of litigation.  Rather than disputing the alleged violations, the King County Executive and WTD chose to negotiate a settlement agreeing to implement a schedule for improvement of operations at existing CSO Treatment plants, construction of CSO control projects that were in design (the “Beach projects”) and design and construction of an additional nine projects to address 14 uncontrolled combined sewer overflow outfalls.

The decree had to be acceptable to the federal and state agencies involved.  Once the terms are agreed to, the proposed decree was filed in federal court where a federal court judge reviewed the terms, allowed for interested parties to comment during a comment period, and issued the decree as final.  Changes to the consent decree must be approved by the court.

Consent Decree Description

The proposed consent decree is a legal document with twenty-six sections.  Each was the subject of negotiation, though the Department of Justice and EPA had many components/sections they consider to be “boiler plate”.   The following is a summary of some of the key sections of the consent decree.

Applicability The consent decree applies to and is binding upon King County, including its officers, directors, agents and employees.  It also applies to contractors and all persons, firms and corporations acting under the direction and control of the County.

Objective The primary objective is to have King County obtain Construction Completion of all CSO control project no later than December 31, 2030.   But overall objective is to not only have the projects constructed but also operating to meet the Washington State standard of no more than one overflow per year on average (over a 20-year period) for each outfall or meeting effluent standards at the CSO treatment plants.  The rest of the consent decree details the schedule for completing projects, monitoring projects post-construction to ensure they meet that standards dictated by EPA and Ecology.

Compliance Programs These sections essentially describe how King County will implement the consent decree to complete construction, monitor and report on all of the CSO outfalls that still need to meet Washington State defined CSO control standards.

Sections 10-11 prescribe the schedule for completion of projects currently being constructed (Ballard Siphon and related CSO control project) or in design that are to begin construction by December 2013 (the “Beach Projects”)

Section 12 stipulates the post construction monitoring and reporting required for the projects above.  If projects have not achieved control within one year, a supplemental compliance plan is required.

Sections 13-14 requires a plan within 30 days of the effective date of the consent decree for modifications of facilities or operations at Dexter, Denny Way and Harbor Ave regulators) to meet control parameters.  And, the CSO Annual Report (for EPA and Ecology) must show compliance to control parameters by December 2015 for those projects; otherwise a supplemental compliance plan is due August 2016.

Seattle and King County Combined Sewer Overflow Locations

King County's Approved Long-term CSO Control Plan Amendment

Section 15 directs construction of the nine projects (to control the remaining 14 uncontrolled CSOs) per the design and performance criteria and the schedule for significant milestones as described in Appendix B.   This is the implementation of the updated long-term control plan.

Section 16 – 18 requires post-construction monitoring for those projects including submittal of Annual Reports and additional Supplemental Compliance Plans if the effluent standards are not being met or discharges at the storage facilities exceed one per year.

Sections 21 – 27 describe some opportunities for proposals King County may make to deviate from the proposed projects and schedules.

- Section 21 allows King County to request deviations from the design criteria for individual projects if it can demonstrate the requested revision reflects good engineering practice and will still meet the performance criteria.    EPA and Ecology have discretion to approve such a change.  If a modification is rejected, King County is entitled to dispute resolution and appeal of the decision to the EPA Region 10 Compliance and Enforcement Director.  If a modification is judged to be a revision of 20% of more, the consent decree must be modified and approved by the court.

- Section 22 allows the County to propose Green Stormwater Infrastructure (GSI) control measures to substitute in part or reduce the “Gray” Infrastructure projects for the four designated projects.

- Section 23 allows the County to propose/request a modification of the critical milestones in Appendix B for the sole purpose of “revising the priority and sequencing of its CSO Control Measures if the County demonstrates the requested modification 1) reflects good engineering practice, 2) is required to coordinate or align with the City of Seattle’s stormwater or CSO infrastructure projects  3) is necessary to attain cost effective and technically sound CSO Control Measures and 4) will not change, modify or extend in any way the County’s final Construction Completion of December 31, 2030.”

- Section 24 - 26 recognizes the parties interest in supporting comprehensive and integrated planning approach to obligations under the Clean Water Act, and allows the County to submit a work plan or “Integrated Plan” that proposed water quality improvement projects to be implemented by the county or jointly by the County and other entities to result in significant benefits to surface water quality beyond those that would be achieved by implementation of the approved CSO Control Measures only.  If an Integrated Plan is rejected, there is a dispute resolution process.

- Section 27 allows the County to request a modification of CSO Control Measure and/or an extension of milestone up to a maximum of five years if the County experiences significant adverse changes to its financial circumstances.

Sewer System Operation Program Plan Within 90 days of the effective date of the consent decree – the County must submit a Sewer System Operation Program Plan which details how the system will be operated to maximize or essentially optimize the utilization of all of the facilities constructed to control CSOs and also provide for real-time coordination with Seattle and its CSO control system.

Joint Operations and System Optimization Plan Between City of Seattle and the County This section requires the development and submittal by March 2016 of a Joint Operations and System Optimization Plan for Seattle and King County.

Civil Penalties  Within 30 days of the effective date of the consent decree, King County must pay $400,000.

Stipulated Penalties   There are various penalty amounts for failure to comply with effluent standards at CSO Treatment Plants, failure to meet milestone dates for projects, failure to meet reporting requirements, etc.

ATTACHMENTS:   none

INVITED:

- Gunars Sreibers,  Acting Director, Wastewater Treatment Division, Department of Natural Resources and Parks (DNRP)

- Stan Hummel, P.E.  Capital Projects Supervisor, Wastewater Treatment Division, DNRP

Ordinance 17413, Attachment A

The cost estimates in the 2012 CSO control plan were Class V estimates (with a range of -50% to +100%) and reflected design development of 0-2%  and based upon the minimal project scoping done for the 1999 Regional Wastewater Services Plan.

The West Point NPDES permit includes the Alki and Carkeek CSO treatment plants, the CSO outfalls, and the recently constructed Mercer/Elliott West and Henderson/Norfolk CSO storage and treatment facilities.  Department of Ecology’s CSO regulations (WAC 173-245) and King County’s RWSP policies require WTD to submit a CSO plan update to Ecology that coincides with each NPDES permit renewal for the West Point Treatment Plant.  Updates are intended to describe WTD’s progress on its CSO program to date, identify its program for the next 5 years, and provide a vehicle for making changes in the overall long-term CSO control program.

King County’s predecessor agency was the Municipality of Metropolitan Seattle, also known as “Metro”, which was consolidated/merged with the County in 1994.

The standard of an average of one untreated discharge per year is now based on a 20-year moving or rolling average.

The consent decree has some provisions for flexibility with regard to design criteria/specifications, schedule and re-sequencing of projects and a supplemental integrated plan that might lead to refinements of CSO control projects.  Some of the decision-making for these changes is proposed to be at the discretion of EPA and Ecology, beyond a certain threshold the court would need to approve the changes.

This graphic is from the 2012 Approved CSO Control Plan Update.  The cost estimates in the graphic and in the control plan were Class V estimates (with a range of -50% to +100%) and reflected design development of 0-2% - based upon the minimal project scoping done for the 1999 Regional Wastewater Services Plan.