## STAFF REPORT

| Agenda Item: | 8 | Name: | Hiedi Popochock |
| --- | --- | --- | --- |
| Proposed No.: | 2016-B0145 | Date: | July 13, 2016 |

SUBJECT

A briefing on the status of Puget Sound Emergency Radio Network (PSERN) implementation.

SUMMARY:

The PSERN project will replace and upgrade the county's current emergency radio network.  King County is responsible for leading and implementing the PSERN project through completion, which is expected in late 2020.

The PSERN project is a complex project with multiple tasks over the course of the implementation period including radio site design, acquisition and construction, as well as the acquisition of radios, consoles, and data systems.

Today’s briefing provides an update on the status of the implementation of PSERN.

BACKGROUND:

On April 28, 2015, King County voters approved a nine-year, $273 million property tax levy to fund PSERN, the replacement of the King County emergency radio communications system.

PSERN will replace and upgrade King County's nearly 20-year old emergency radio communications system, which is used to dispatch responders to incidents and allow responders to communicate with each other at those incidents.  Countywide, the current system consists of 26 transmitter sites and multiple interconnecting microwave and fiber systems, and it supports over 100 agencies and approximately 17,000 radio users, each with a portable radio handset and/or installed mobile radio in a vehicle.  The current system is owned in equal shares by King County, the City of Seattle, Valley Communications Center (ValleyCom), and the Eastside Public Safety Communications Agency (EPSCA).

Once completed, PSERN will replace the current countywide emergency radio network.  PSERN will improve and upgrade the countywide emergency radio network by providing increased system reliability, increasing coverage capacity from 94 percent coverage to 97 percent coverage, providing better security on the network, and nearly doubling the number of radio transmitter sites.

PSERN Implementation

Implementation Interlocal Agreement.  Under the terms of the PSERN Implementation Interlocal Agreement ("Implementation ILA"), King County will be responsible for leading and implementing the PSERN project on behalf of the four owners of the current emergency radio network through completion of the project.  Oversight during that implementation period, which is expected to take approximately five years, will be conducted by a Joint Board, composed of one non-voting chair (the Executive or the Executive's designee) and four voting representatives, one representing each of the current system's owners.  The four voting members of the Joint Board may appoint two additional non-voting participants: a chief of a police agency and a chief of a fire agency.

The PSERN project management team includes a project director and information technology and construction managers, a communications manager, a government relations official, technical support technicians and inspectors.  King County Information Technology's Business & Finance Section and the Office of Performance, Strategy and Budget will provide financial support.  Under the terms of the $112 million, 20-year contract between Motorola and the County, Motorola will provide design, development, implementation, testing and ongoing support, maintenance and upgrade services for the PSERN project.  In addition to the primary contract with Motorola, the Executive has hired a consultant to develop the site design and intends to retain a firm to provide construction management oversight.

Operations Memorandum of Agreement.  Under the terms of the Memorandum of Agreement Regarding Future Operation of The Puget Sound Emergency Radio Network ("Operations MOA"), ownership and operation and maintenance of PSERN after completion would be vested in a new, nonprofit organization governed by a Board of Directors.

Oversight of PSERN Implementation

Council Committee Oversight.   Motion 14437, enacted in October 2015, requires the Executive to brief the Law, Justice and Emergency Management Committee (or its successor) on a quarterly basis on the status of the PSERN project in relation to the project’s identified milestones.

PSERN project staff presented their second quarter update to the Law and Justice Committee on May 10, 2016.

Table 1 below shows the 13 major project milestones identified in the report transmitted by the Executive in September 2015 (2015-RPT0134) that remain to be completed during the PSERN implementation process, along with the original expected date of completion and the revised expected date of completion.

Table 1: Future PSERN Implementation Milestones including the Original Expected Completion Dates and the Revised Expected Completion Dates

| Project Milestone | Original Completion Date | Revised Completion Date (as of 5/10/16) |
| --- | --- | --- |
| Group 1 Site Leasing and Final Site Design | March 2016 | May 2017* |
| Construction Permitting | August 2016 | April 2017* |
| Site Construction Mid-point | September 2016 | Milestone eliminated |
| Group 2 Site Leasing | August 2017 | Milestone eliminated |
| Factory Acceptance Testing | September 2017 | No change |
| Site Construction Complete (all sites) | October 2017 | May 2019 (incl. U.S. Forest Service Sites) |
| Backhaul System Implementation | November 2017 | November 2017* |
| Land Mobile Radio System Implementation | September 2018 | September 2018* |
| System Optimization and Testing | May 2019 | No change |
| PSERN Non-profit Operator Formation | September 2019 | No change |
| Transition Users to PSERN System | March 2020 | No change |
| Full System Acceptance | September 2020 | No change |
| Project Closeout | September 2021 | No change |

*Expected completion date for non U.S. Forest Service land sites only

Revised Expected Completion Dates

As noted in Table 1, the expected date of completion for three milestones have changed since September 2015.

Site Leasing and Final Site Design. According to PSERN project staff the “site leasing and final site design” milestone is expected to be completed in May 2017 for the non U.S. Forest Service land sites instead of the original expected date of March 2016 for all radio sites. PSERN project staff indicated that the reason for the extension relates to the length of time necessary to develop ten radio sites located on U.S. Forest Service land.

Also, PSERN project staff eliminated “Group 1” in the milestone title. PSERN staff state that the project’s expected approach to transmitting leases to the Council for approval has evolved since September 2015.  At that time, PSERN project staff intended to transmit all the leases necessary for the PSERN project to the Council in two bundles or groups (i.e., Group 1 site leasing and Group 2 site leasing).  PSERN staff now intend to transmit leases to Council as they are completed.  According to PSERN staff, the project will require 55 agreements, the majority of which will require Council approval since the term of the lease agreements will exceed five years.

Construction Permitting.  PSERN project staff stated that the expected completion date for the “construction permitting” milestone has changed from August 2016 for all sites to April 2017 for the non U.S. Forest Service sites only. PSERN project staff indicate that this is due to slow progress in completing lease agreements, conditional use permits and zoning issues with local municipalities.

Site Construction Complete. The expected date of completion for all radio sites has been extended from October 2017 to May 2019.  PSERN project staff expect to complete development of all radio sites in the area known as the Primary Coverage Bounded Area or Metropolitan Seattle area sites by June 2017.  This area includes all radio sites west of the 1250’ Cascade ridge line (including the Issaquah Alps).  Radio sites located on U.S. Forest Service land are expected to be developed by May 2019.

Backhaul System Implementation.  One of the first subsystems the system vendor will install is the backhaul subsystem. The backhaul subsystem routes communications among sites, as opposed to transmitting communications between radios and sites. PSERN project staff indicate that the expected completion date to implement the backhaul system is November 2017 for the non U.S. Forest Service land sites only. Originally, the expected completion date for this milestone was for all radio sites including the ten U.S. Forest Service land sites.

Land Mobile Radio System Implementation.  The implementation of the land mobile radio system, which enables the communication between a tower and a radio or console will be completed in September 2018 for the non U.S. Forest Service land sites only as opposed to all radio sites including the U.S. Forest Service land sites.

Eliminated Project Milestones

In addition to the changes discussed above, PSERN project staff are no longer following two milestones that were initially identified in the September 2015 report.

Site Construction Mid-Point. PSERN project staff have stated that the “site construction mid-point” milestone no longer makes sense given the extended work required for the ten U.S. Forest Service sites and therefore, they will no longer utilize this milestone.

Group 2 Site Leasing.  As mentioned previously in this staff report, since the site leasing agreements will be transmitted to Council as they are completed versus being transmitted in groups as originally planned in late 2015, PSERN project staff will no longer utilize this milestone.

King County Auditor Capital Projects Oversight.  On November 10, 2015, the Capital Projects Oversight Program of the King County’s Auditor’s Office released a report on PSERN. The report focused on project schedule and cost risks.  The Auditor’s Office presented the report to the Government Accountability and Oversight Committee on November 10, 2015.

The report included five recommendations for the PSERN project:

Recommendation 1.  The PSERN project team should revise the project schedule and communicate it to stakeholders before the end of 2015 to include reasonable time to accomplish the remaining tasks necessary to finish tower site construction. The schedule should be based on progress to date and identify the impact on the remainder of the project schedule.

Recommendation 2.  The PSERN project team should improve reporting to clearly demonstrate to stakeholders the progress on leasing and constructing radio tower sites. Reporting should show how current cost and schedule forecasts compare to the assumptions used in the preliminary project estimate.

Recommendation 3.  The PSERN project team should establish and document a project baseline prior to signing any construction contract. The baseline should use the certainties from the Motorola contract, best available information for tower site costs and schedule, and refined estimates of other costs.

Recommendation 4.  The Finance and Business Operations Division (FBOD) should provide ongoing technical assistance to the PSERN project team to help manage the cost risks of any construction work order contracts for this project.

Recommendation 5.  Before seeking bids on a work order construction contract for the radio tower sites, the PSERN project team and FBOD should evaluate the relative benefits, costs, and risks specific to each site of inclusion in a work order contract or a traditional design-bid-build contract. This evaluation should be documented and result in a recommended approach for each individual site for consideration and approval by the project sponsor.

The PSERN project staff indicated that the PSERN project generally agreed with these recommendations.

The Capital Projects Oversight Program staff indicate that they expect to release the next report on the PSERN project in September or October 2016.

ATTACHMENTS:

- PowerPoint Presentation “Puget Sound Emergency Radio Network (PSERN), Regional Policy Committee, July 13, 2016”

INVITED:

- David Mendel, PSERN Project Director, King County Information Technology

Ordinance 18075.

The existing system is owned in equal shares by King County, the City of Seattle, Valley Communications Center (ValleyCom), and the Eastside Public Safety Communications Agency (EPSCA).

As of May 2, 2016, the members of the Joint Board are as follows:  Fred Jarrett, non-voting Chair; Bill Kehoe, King County voting member; Patti DeFazio, Seattle voting member; Kurt Triplett, EPSCA voting member; Lora Ueland, ValleyCom voting member; Chris Elwell, non-voting fire agency member; and John Vinson, non-voting police agency member.

Ordinance 18074.

In 2016, the Law, Justice and Emergency Management Committee was changed to the Law and Justice Committee.

K.C.C. 4A.100.070D.4

2015-B0210: A briefing on the Capital Projects Oversight Report regarding PSERN.