## Sheet1
SCAI Meeting | Topic | Program | Details | Time | Who
September 27 (Balducci) | · EHD RFP update | EHD |  | 10 | · DAJD
| · Best practices/other jurisdictions | Both | Reporting out and building on work in proviso report | 20 | · PSB/DAJD
| · FMD planning timeline | WER | Options include: -> Lease and remodel a site -> buy and build -> buy and remodel -> Remodel County-owned | 30 | · FMD
| · Defining Planning Periods | WER | What is meant by "short term," "interim," and "long term"? | 15 | · Committee
| · FMD Planning Funding | WER | Project to charge for preliminary planning | 10 | · PSB/FMD
| · Long-term vision | Both | Need Council, CJ, Exec agreement -> Approve proviso motion with vision | 20 | · Committee
105
October 25th (Dunn) | · EHD RFP Update | EHD | May not be necessary | 10 | · DAJD
| · Fee Schedule Review | Both | Define principles to guide update and/or review proposal from DAJD | 20 | · DAJD/PSB
| · Interim Vision | WER | Include pieces of long-term vision that make sense and also address: -> Program size/expansion -> Characteristics of population -> Services provided -> More contracting? | 30 | · Committee?
| · Interim Alternatives Overview | WER | Including, but not limited to: -> status quo on 10th floor -> Re-open 11th floor -> West Wing of KCCF -> Yesler | 20 | · DAJD/FMD
| · Legal environment | Both | Any State law or local regulatory changes the County wants to pursue? | 10 | · PSB/Courts
90
November 29th (Balducci) | · Assess demand for contracting | Both | Exec's office doing outreach | 20 | · Exec’s Office
| · Interim Alternatives implementation timelines | WER | Including, but not limited to: -> status quo on 10th floor -> Re-open 11th floor -> West Wing of KCCF -> Yesler | 30 | · DAJD/FMD
| · Interim Alternatives costs | WER | Operating and Capital | 30 | · PSB/FMD
| · Fee Schedule Review | Both | Potential scenarios to update fee schedule | 15 | · PSB
95
December | · No meeting
January (Dunn) | · Interim Alternative selection | WER | Informed by: -> Updated cost estimates -> Updated Implementation timeline -> Siting considerations & community/jurisdiction feedback -> Robust pros and cons for alternatives | 90 | · All?
January | Potential report out to COW or LJ
February (Balducci) | · Final interim implementation funding proposal | WER | Should be a final review and affirmation of January meeting | 20 | · Committee
| · Long-term planning timeline and project plan | WER | Plan for how we get to long-term vision -> identify important topics, such as -> community outreach -> consultant/architect… | 40 | · FMD/PSB/ DAJD
| · Long-term planning budget preliminary proposal | WER | Funding for first stage of planning to get to full budget proposal later | 30 | · FMD/PSB
|  |  |  | 90 | · FMD/PSB
March (Dunn) | · Reserve in case needed