| Agenda Item: | -- | Name: | Rick Bautista |
| --- | --- | --- | --- |
| Proposed No.: | FCZD2009-0--6 | Date: | March 16, 2009 |

STAFF REPORT

SUBJECT:	A MOTION amending the contract between the King County Flood Control Zone District and Lund Consulting for administrative services..

Background

Lund Consulting, Inc. and Cocker Fennessy have a current contract with the King County Flood District for the period May 5, 2008 – May 31, 2009.  The current contract budget is for $175,725, which was expended as of January 31, 2009.  Table 1 outlines the work performed up to early March 2009:

Table 1

| Task | Budget for 12 months | Actual for 9 months | Difference | Average Hours/month |
| --- | --- | --- | --- | --- |
| Develop Board Accountability System | 60 hours | 75 | 15 | 8 |
| Review and Update Interlocal Agreement | 40 hours | 79 | 39 | 9 |
| Develop Milestones for Board action | 20 hours | 31 | 11 | 3 |
| Staff 16 meetings | 208 hours | 263 | 55 | 29 |
| Monitor advisory and basin committees | 104 hours | 12 | (92) | 1 |
| Monitor WLRD Performance | 104 hours | 108 | 4 | 12 |
| Assist with financial and legal service | 40 hours | 139 | 99 | 15 |
| Develop communications plan and protocols | 43 hours | 37 | (6) | 4 |
| Migrate, update and maintain web site | 52 hours | 54 | 2 | 6 |
| Develop Fact Sheet, FAQ, Presentation, e-newsletter | 50 hours | 69 | 19 | 8 |
| Implement communications plan, media and government relations, issue management coordination | 260 hours | 114 | (146) | 13 |
| Total Hours | 981 | 981 | 0 | 108 |

In order for these contractors to continue to perform services through the remainder of 2009, amendments are needed to both the contract time period and budgeted funds.  NOTE:  While the contract budget is expended, the approved District management budget for 2008 had a surplus and the 2009 budget has not yet been encumbered by the contract.

SUMMARY OF PROPOSED REVISIONS TO CONTRACT:

The  proposed revisions relate to the contract period and the total funding for the contract.  The proposed revisions:

- Extend the contract time period through March 31, 2010 with provision to terminate by either party to allow for sufficient time to rebid contract.

- Amend contract funding to an amount not to exceed $231,000 for the period from February 1 – December 31, 2009.   This amount is reflected on Table 2 (2009 District-approved budget for contract services) below for the Executive Director and Communications line items.  The proposed contract amounts are based on an anticipated monthly rate of approximately $13,000 for Lund Consulting, Inc and $7,500 Cocker Fennessy.

The table shows the breakdown of consultant services and indicates that no additional action on the District budget is required to fund the revised contract through 2009.  That said, the budget for the last three months of the proposed contract period (1st quarter of 2010) would be based on an approved District budget for 2010.

Table 2

2009 District -Approved Budget For Contract Services

| District Oversight & Management | Approved Budget | Proposed Contracts |
| --- | --- | --- |
| Executive Director (Lund) | 155,000 | 147,200 |
| Communications (Cocker Fennessy) | 90,000 | 83,000 |
| Legal Services | 85,000 | 85,000 |
| Accounting | 65,000 | 50,000 |
| Clerk & Council Staff | 30,000 | 30,000 |
| Supplies, copies, web | 15,000 | 15,000 |
| Other Services: audit, experts, reserve | 10,000 | 39,800 |
| Total | $450,000 | $450,000 |

Although tasks will be billed in accordance with the billing rate shown on Table 3, for purposes of cost estimating an average hourly rate of $175 was assumed.

Table 3

| Task | Contract Rates | Standard Rates |
| --- | --- | --- |
| Partner/Project Manager/Principal | $195 | $245 - $250 |
| Senior Manager | $185 | $190 |
| Senior Associates | $150 | $188 |
| Associates | $125 | $135 |
| Administrative support | $60 | $63 - $75 |

ATTACHMENTS

- Proposed Motion FCZD2009-0--