## Softcost
Construction Costs
003 | Clay Tile Wall Suppot
Seismic Upgrade
Mechanical System
Fire Sprinkler System
Fire Alarm
Data/Communications Core Service
Remodel/Renovation to Support Reprogramming
Electrical Work outside of the items
Subtotal
Escalation
Base Cost
Asbestos/Lead Paint Abatement
Total Construction Cost Including Abatement
41058688
| Court Security/Electrical Project Allowance |  | 1447010
|  |  | 43000000 | 50718904 | MACC
| Additional Contingency |  | 2000000 | 204000 | Preconstruction Services
|  |  |  | 50922904 | Subtotal GC/CM
|  |  |  | 394627 | Braces
|  |  |  | 220000 | Service Elevators
|  |  |  | 177000 | Heat Exchanger
|  |  |  | 791627 | Subtotal County
| Subtotal Construction |  | 45000000 | 51714531
Soft Costs
001 | Design Fees |  | 5150337 | 5908686
002 | Acquisition
| CM Fees |  | 1173194 | 1443200
| Additional Administration |  | 250000
| Subtotal CM Fees |  | 1423194 | 1443200
005 | Construction Contingency | 15% | 6300000 | 5502000 | 10.64%
004 | Office Furnishings and Equipment
| Washington State Sales Tax | 8.8% | 4250400 | 4550878.728
| Building Permit | 1% | 476767 | 434488
| Bid & Project Costs |  | 1500 | -
| Printing |  | 226500 | 226500
| Owner Testing |  | 200000 | 400000
| Concrete Beam Testing |  | 72840 | 72840
| Subtotal Testing |  | 272840 | 472840
| Project Insurance |  | 421898 | 328743
006 | 1% Art | 1% | 570612 | 677916
| County Planning Program |  | 872000 | 872000
007 | County Force Design |  | 150000
009 | County Force Administration |  | 1759576
| Additional Administration |  | 250000
| Subtotal County Administration |  | 2159576 | 2464761
| Total Cost |  | 67125624 | 74596543.728

## Budget
| A | B | C | D | E | F | G
|  | Pre-Earthquake | Post Earthquake | Bid Period |  | Current
# | Description/Category | Baseline | Additional | Unfunded | Revised | Budget
|  | Project Budget | Contingency #1 | Move Budget #2 | Baseline Budget | 07/18/02 | Difference
1 | Design | 5150337 |  |  | 5150337 | 6130895 | 980558
2 | Construction Taxes & Contingency | 53666203 | 1360000 |  | 55026203 | 62558721 | 7532518 | 6294295 | 56264426
3 | Construction Management | 1173194 | 170000 |  | 1343194 | 1443200 | 100006
4 | Special Testing & Inspection | 272840 |  |  | 272840 | 472840 | 200000
5 | 1% for Art | 572218 |  |  | 572218 | 680799 | 108581
6 | Temp Relocation/Yesler Courts | 3388266 |  | 3507000 | 6895266 | 7442724 | 547458
7 | County Administration | 1822320 | 170000 |  | 1992320 | 2153977 | 161657
8 | Insurance Permit Printing FPP | 2248524 |  |  | 2248524 | 2361728 | 113204
9 |  | 68293902 | 1700000 | 3507000 | 73500902 | 83244884 | 9743982
10 | Subtotal Budget |  | 69993902
11 |  |  |  |  | Plus Pre-1998 | 40542
12 | Appropriation History |  |  |  | Total Current Budget | 83285426
13 | Jul 1997 | 3500000
14 | Ordinance 13859 May 2000 | 160000
15 | Ordinance 13945 Sep 2000 | 5383823
16 | Ordinance 4018 Adopted 2001 Budget | 455711
17 | Ordinance 4018 Adopted 2001 Budget | 164045
18 | Ordinance 14088 Apr 2001 | 59308884
19 | Ordinance 14088 Apr 2001 | 1227000
20 | Total Appropriation to date |  | 70199463 |  |  | 70199463
21 |  |  |  |  | Supplemental Appropriation Request | 13085963
22 | Notes
23 | #1 Additional Contingency
24 | Proposed Additional Contingency | 2500000
25 | Less Council Reduction | 800000
26 | Net Additional Contingency | 1700000
27 | #2 Unfunded Move Budget | 3507000
|  | 68% | -205561 |  |  | 1352400
84597284