## ATTACHMENT 1

King County District Court: Community Court Planning

Project Action Plan

This Action Plan is designed to outline the possible milestones and other key activities you might consider as you plan your community court project, as well as provide a timeframe for completing them. These milestones and activities are based on the Center for Court Innovation’s experience with helping to launch and enhance other community justice programs.

| Community Court Planning Milestones | Key Dates (Mo/Day/Yr) |
| --- | --- |
| Identify lead planner | Anticipated completion date: July 2017 Actual completion date: TBD |
| Convene steering committee * e.g. ☐ Identify members-Visits done by end of July, decision about where pilots August 2017 ☐ Convene initial meeting-September 2017 ☐ Calendar and convene regular meetings ☐ Other: _______________________ | Anticipated date of first convening: TBD Actual date of first convening: TBD Other anticipated meeting dates: TBD |
| Conduct a needs assessment * e.g. ☐ Conduct data analysis May/June ☐ Complete community survey ☐ Complete focus groups ☐ Complete stakeholder interviews ☐ Produce a needs assessment report, with description of concept ☐ Other: _______________________ | Anticipated completion of needs assessment: November 2017 Actual completion of needs assessment: TBD |
| Create a concept paper e.g. ☐ Describe the needs assessment process ☐ Define project principles ☐ Provide a detailed overview of program elements, including range of services provided ☐ Other: _______________________ | Anticipated completion of concept paper: November/December 2017 Actual completion of concept paper: TBD |
| Create a project implementation plan e.g. ☐ Develop mission statement and objectives ☐ Determine location(s) to be used ☐ Define operations (e.g., day/time) ☐ Define staffing and roles ☐ Develop eligibility criteria, screening and assessment process, and case flow ☐ Create policy for linking participants to services ☐ Develop community service protocol ☐ Define case management and monitoring procedures ☐ Develop a communication strategy ☐ Develop plan for ongoing community engagement ☐ Create policy & procedures manual ☐ Draft project implementation plan ☐ Identify performance measures ☐ Other: _______________________ | Anticipated completion of implementation plan: November/December 2017 Actual completion of implementation plan: TBD |
| Community Court Planning Milestones (provided on going funding) | Key Dates (Mo/Day/Yr) |
| Launch community court or enhancement project ☐ Set “soft” launch ☐ Set “hard” launch | Anticipated soft launch date: TBD Actual soft launch date: TBD Anticipated hard launch date: TBD Actual hard launch date: TBD |
| Implement a risk/needs assessment tool, if desired e.g. ☐ Review existing risk/needs tools ☐ Select tool and determine implementation strategy ☐ Train relevant staff on its use ☐ Use tool in court’s screening and assessment process ☐ Other: _______________________ | Anticipated training date: Actual training date: Anticipated implementation date: Actual training implementation date: |
| Collect and report data (ongoing) ☐ Identify data collection personnel ☐ Determine performance metrics to be collected ☐ Develop and implement data tracker ☐ Collect data on a quarterly basis | Anticipated date of completion of data tracker: Actual date of completion of data tracker: |

*Data collection and Spokane visits, once completed, will inform us where to place pilot communities (2). Once communities have been determined, steering committees and stakeholder meetings will be determined.