## Slide 1
KingCounty.gov/Harborview
Harborview bond program updates
Budget Status
May 2026
Harborview campus,
overlooking new hospital
tower location

## Slide 2
Budget Status
Original voter‑approved bond: $1.74B for the New Tower, renovation/backfill, behavioral health facilities, a new Pioneer Square Clinic, and related infrastructure.
In 2023, OWG reduced scope by removing behavioral health facilities and the Pioneer Square Clinic.
Highest‑tier OWG scope remains fundable within the original $1.74B, but there are projects needed that were NOT in the OWG scope that are necessary to actually operate a building of this magnitude.
Current estimate to build and occupy the OWG scoped building: $1.9B–$2.1.
Budget discrepancy linked to pricing differences between Mortenson (design‑build contractor) and Cumming (County’s third‑party cost expert).
Additional hospital needs identified since the original bond total $250M–$325M.
Revised OWG Top Tier Scope

## Slide 3
Background on Ordinance Workgroup (OWG) 2023
Formed to evaluate original 2020 Bond projects and provide guidance on necessary updates to mitigate budget deficits.
Membership: 27-person project team and 10 voting members1
Outcomes:
  Program scope was divided by priority
  Highest priorities were bed capacity and acute care areas, but also included County needs
  Other key items deprioritized
1: Project team included members from King County, Harborview, UW Medicine, and consultants. Voting members included representatives from King County Executive Office, King County Council, Harborview Board of Trustees, UW Medicine.

## Slide 4: Progressive Design Build – Where are we in the process?
  Progressive Design Build (PDB) is a project delivery method where the Owner bring on a design-build (DB) team early in the project.
  Owner and DB work together on the design, and progress that design into a full project.
  Five stages of design on major construction projects.
  Pricing is conducted during and at the conclusion of each stage.
Current Phase
Schematic Design (SD) pricing difference must resolve as follows:
Within 20% of target value price by 6/29/26
Within 10% of target value price by 9/15/26

## Slide 5: Schedule

## Slide 6: Pressing Hospital Needs - Parking
  Parking was not identified as major issue at Bond inception; original HLG report didn’t account for increased traffic from new tower.
  Pandemic-driven shift to outpatient‑centric operations significantly increased parking demand.
  HCID and Harborview are pursuing a predesign for a large parking structure at 9th & Alder to support a future medical office building, and Council-funded design work in the 2026–2027 budget.
  Estimated cost for additional parking: approximately $160M, firm pricing expected August 2026.
  HMC is concerned about patient access if replacement parking is not available before View Park I demolition (scheduled early 2028).
#1

## Slide 7: Pressing Hospital Needs – Central Utility Node
  City energy code changes now require New Tower to be fully electric
  All‑electric design would require two 800kW electric boilers with high peak‑demand operating costs and potential electricity‑supply constraints
  This outcome was not anticipated and is not ideal for a resilient disaster‑recovery safety‑net hospital.
  Solution:
  City code permits natural‑gas boilers for peak loads if part of campus is converted to an energy-district.
  Energy‑district approach requires higher upfront capital (about $90M more, largely for converting West Hospital and West Clinic) but avoids major Seattle City Light grid‑upgrade costs.
  Expected to save several million dollars per month in winter operations and avoid impacts of Seattle City Light’s new large‑load policy.
  More resilient design, improving reliability during seismic events.
#2

## Slide 8: Pressing Hospital Needs – Loop road and site access
  Current schematic design omits a loop road; Jefferson St. and Alder St. would terminate at the hospital’s west edge.
  This reduces program costs but may be operationally infeasible.
  HCID, Seattle Fire, and HMC must evaluate safety and patient‑access impacts of the no‑loop‑road design.
  If concerns cannot be resolved, a Loop Road may be required.
  Loop Road option adds about $75M in cost and introduces schedule risks tied to WSDOT site‑control and long‑term lease issues.
  HCID expects to validate the preferred approach by end of September.
#3

## Slide 9
Planning Direction from County Executive
Total New Tower Needs Estimates: $2.25B - $2.43B
Components of Estimate Include:
Current Bond Program Estimates for OWG Scope: $1.936B - $2.1
Pressing Need Projects for New Tower:
  $160 million - parking garage (approx. $115M additional funding needed)
  $90 million - Central Utility Node
  $75 million Loop Road