## All Projects Summary
Nisqually Earthquake Project Summary
2002-05-19
Project | FEMA Project | Description | Orig Estimate | LTD Budget | 2001 Actuals | 2002 Actuals & Encumbrances | 2002 Balance | Projected Cost of Repairs to Complete | Projected Balance | Status | FEMA Approved Cost to Date | 75% FEMA Reimbursement | 12.5% State Reimbursement | Estimated Insurance Reimbursement | Estimated Net to Finance | Total Estimated cost
Courthouse Earthquake Repairs
395134 |  | Master Project | 0 | 217723 | 7892 | -16848 | 226679 | 0 | 226679 | Master Project |  | 0 | 0 | 0 | -8956 | -8956
134T01 | CFM-010 | Elevator Repairs | 1498620 | 1899273 | 1844779.08 | 31355 | 23138.92 | 0 | 23138.92 | Complete |  | 0 | 0 | 1251836 | 624298.08 | 1876134.08
134T02 | CFM-011 | Stairwell Repairs | 2553456 | 2386408 | 131956 | 110995 | 2143457 | 2144780 | -1323 | Design Complete |  | 0 | 0 | 1493001 | 894730 | 2387731
134T03 | CFM-012 & CFM-016 | Misc. Crack & Wall Repairs** | 1282295 | 530000 | 105953.53 | 238919 | 185127.47 | 100000 | 85127.47 | 70% Complete |  | 0 | 0 | 1024390 | -579517.47 | 444872.53
134T04 | CFM-006 | Debris Cleanup | 0 | 20856 | 20856 | 0 | 0 | 0 | 0 | Complete |  | 0 | 0 | 20856 | 0 | 20856
134T05 | CFM-001 | Emergency Protection | 0 | 92925 | 92925 | 0 | 0 | 0 | 0 | Complete |  | 0 | 0 | 363151 | -270226 | 92925
134T06 |  | Ombudsman Office Repair | 0 | 56870 | 56870 | 0 | 0 | 0 | 0 | Complete |  | 0 | 0 | 48693 | 8177 | 56870
134T07 |  | Domestic Violence Office Repair | 0 | 38730 | 38730 | 0 | 0 | 0 | 0 | Complete |  | 0 | 0 | 38640 | 90 | 38730
134T08 |  | W292 Repair | 0 | 49 | 48.95 | 49 | -48.95 | 0 | -48.95 | Complete |  | 0 | 0 | 49 | 48.95 | 97.95
134T09 |  | Budget Office Repair | 0 | 14223 | 14223 | 0 | 0 | 0 | 0 | Complete |  | 0 | 0 | 14064 | 159 | 14223
134T10 |  | ExteriorTerra Cotta Repairs | 0 | 50814 | 30482 | 22286 | -1954 | 336635 | -338589 | Report Complete |  | 0 | 0 | 460611 | -71208 | 389403
134T11 |  | Above ceiling Review | 0 | 20000 | 4068.19 | 0 | 15931.81 | 0 | 15931.81 | On-going |  | 0 | 0 | 0 | 4068.19 | 4068.19
134T12 |  | W355 Wall replacement | 0 | 6500 | 4266 | 0 | 2234 | 0 | 2234 | Complete |  | 0 | 0 | 4266 | 0 | 4266
|  | Subtotal for Courthouse | 5334371 | 5334371 | 2353049.75 | 386756 | 2594565.25 | 2581415 | 13150.25 |  | 2086200 | 1564650 | 260775 | 4719557 | 735204.75 | 5321220.75
|  | Portion of Insurance Deductible | [11 empty] | 1958966
|  | Expected Insurance Settlement for 395134 | [11 empty] | 2760591
601663.75
395137 | CFM-013 | CH Corridor/Public Assembly Wall Repairs** | 3006230 | 2616722 | 515265 | 65473 | 2035984 | 1800000 | 235984 | Design Complete | 353800 | 265350 | 44225 | 1153763 | 1271200 | 2380738
137T01 |  | Stairwell #4 |  | 600000 | 0 | 54135 | 545865 | 545000 | 865
|  | Portion of Insurance Deductible | [11 empty] | 353800
|  | Expected Insurance Settlement for 395137 | [11 empty] | 799963
|  | Subtotals For Courthouse | 8340601 | 8551093 | 2868314.75 | 506364 | 5176414.25 | 4926415 | 249999.25 |  |  | 1830000 | 305000 | 3560554
395136 | CFM-001 thru CFM--009 | Outlying Building Repairs | 1261214 | 1261214 | 486289 | 227889 | 547036 | 150000 | 397036 | 80% Complete | 723741 | 542805.75 | 90467.625 | 0 | 230904.625 | 864178
395135 | CFM-014, CFM-015 | Johnson Building Repairs | 702095 | 702095 | 38073 | 136460 | 527562 | 527000 | 562 | In Design | 250000 | 187500 | 31250 | 452095 | 30688 | 701533
|  | Total Earthquake Repairs | 10303910 | 10514402 | 3392676.75 | 870713 | 6251012.25 | 5603415 | 647597.25 |  | 3413741 | 2560305.75 | 426717.625 | 4012649 | 2867132.375 | 9267669.75 | 2134456.375
|  |  | Budgeted Amount | Current Estimate
|  | Estimated County Liability | 3514729.625 | 2867132.375
|  | Additional Maintenance Cost incurred in Facilities Mgmt internal service fund for earthquake cleanup and repair not included above. |  |  |  | 258687 | -258687 | 0 | -258687 | Complete |  | 0 | 0 | 127234 | 131453
**$337,000 transferred from 134T03 to 395137 as part of year end project reconciliation
|  |  |  | Total |  | Courthouse Repairs | CH Stairwells and Lobbies | Outlying | Johnson Bldg | Miscellaneous Other
|  |  | Current Budget | 10514402 |  | 5334371 | 3216722 | 1261214 | 702095 | 0
|  |  | Less Projected balance | 647597.25 |  | 13150.25 | 235984 | 397036 | 562 | -258687
|  |  | Total Current Estimate | 9866804.75 |  | 5321220.75 | 2980738 | 864178 | 701533 | 258687
|  |  | FEMA | 2560305.75 |  | 1564650 | 265350 | 542805.75 | 187500
|  |  | State | 426717.625 |  | 260775 | 44225 | 90467.625 | 31250
|  |  | Insurance | 4012649 |  | 4719557 | 1153763 | 0 | 702095 | 127234
|  |  | Less Ins Deductible |  |  | -1958966 | -353800 |  | -250000
|  |  | Net to Finance | 2867132.375 |  | 735204.75 | 1871200 | 230904.625 | 30688 | 131453