Harborview Bond Program Monthly Status Report

September 2023

# Contents

Contents	2

Executive Summary	3

Background	5

Department Overview	5

Historical Context	5

Current Context	8

Report Methodology	9

IV. Report Requirements	10

1.	Description of the Current Program Scope	10

2.	Updates on the Project Schedule Including Status of and Planned Dates for Major Milestones	14

3.	Status and Progress for Each Component Capital Improvement Projects	14

4.	Budgetary Update	15

5.	Update on Tasks Completed on Major Milestones Since the Preceding Report and a Three-Month Projected Outlook on Upcoming Tasks to Accomplish Milestones	17

6.	A Description of Stakeholder Engagement and Public Communications Over the Preceding Month Including Appearances on Agendas at Regional Meetings and Mailings	18

7.	A Description of Risks Including Newly Identified Risks and Realized Risks	19

V. Conclusion	21

VI. Appendices	22

# Executive Summary

On November 3rd, 2020, more than 70 percent of King County voters approved Proposition 1 authorizing King County to sell $1.74 billion in bonds to fund facility and infrastructure improvements at Harborview Medical Center. Since its passage, the Facilities Management Division has worked diligently to establish the necessary organization and management structures needed to implement this complex capital program; one of the largest in King County’s history.

Harborview Medical Center is a 540-licensed-bed hospital owned by King County, governed by the Harborview Board of Trustees, and managed under contract by the University of Washington. Harborview Medical Center has a unique mission statement that identifies and prioritizes services to the most vulnerable residents of King County. It is the only Level I Adult and Pediatric Trauma Center in Washington. It provides centers of emphasis and specialized comprehensive emergency services to a broad range of patients and throughout the region. The medical center is also the disaster preparedness and disaster control location for the City of Seattle and King County.

For nearly 100 years, Harborview provided medical services from its location atop Seattle’s First Hill. It is distinctive in its consistent provision of care to King County residents regardless of their race, religion, ethnic origins, or ability to pay. As stewards of the campus facilities, King County regularly provides facility improvements and expansions through voter-approved financing, generally occurring every 15-20 years. The original center tower was constructed with bonds in 1930 and through the ensuing years, the voters continued to entrust King County with funding approvals on behalf of Harborview.

King County Council Motion 15183, passed in 2018, called for the establishment of a planning group to identify hospital and community needs and make recommendations regarding a capital program. The resulting Harborview Leadership Group (HLG) was comprised of representatives from Harborview administration, the Board of Trustees, the University of Washington, labor partners, the First Hill Improvement Association, the mission population, the King County Council, and the Executive Office. The HLG provided a report making recommendations for health and safety improvements at Harborview Medical Center. The recommendations included building a new in-patient tower to increase critical care capacity and meet modern infection control standards as well as making seismic improvements to older structures on the campus to increase surge capacity, expand flexibility for hospital operations, and save lives in the event of a major earthquake.

Since the approval of the $1.74 million bond funding, the Facilities Management Division (FMD) has focused on establishing the structures and processes required to effectively implement the historic, multi-year Harborview Bond Program. Other Bond Program start-up activities included:

- Hiring key County staff;

- Selecting project management firms;

- Developing financial accounting reporting protocols;

- Expanding partnerships and collaborations with Harborview staff; and

- Establishing monthly meetings with King County Auditor’s Office staff.

As part of the Bond planning, Coronavirus Disease 2019 (COVID-19) pandemic, and associated impacts on supply chains and workforce, King County requested that the Bond Program’s project management consulting firm, Vanir, review and update the 2019 cost assumptions used to establish the Bond. Presentation of the initial findings led King County Council of the Whole members to pass Ordinance 19583 (Appendix A) which called for the creation of a work group to identify a recommended Program Plan within the escalated pricing for health and safety improvements at Harborview Medical Center.

The recommended Program Plan submitted to the Council on August 1, 2023, has three key components: 1) construction of a new multi-story medical tower; 2) renovation of essential services currently located in older hospital spaces; and 3) expansion of County spaces located in older hospital facilities. The recommended Program Plan was determined after considering the operational needs of Harborview and the shared priorities of King County, the Board of Trustees, and UW Medicine. At this time, the Council has not yet acted on the proposed Program Plan but has scheduled a review of the plan in September 2023.

The Bond Program continues with key elements of a program scope that aligns with the Bond Program’s mission. Tasks associated include:

- Progressing toward the submission of a City of Seattle Major Institution Master Plan (MIMP) major amendment;

- Developing a campuswide utility and infrastructure plan;

- Collaborating with King County and UW Medicine departments to understand new and modified spaces needed;

- Establishing the request for proposal (RFP)/Procurement processes and bid work activities needed to accomplish the Bond Program goals;

- Managing the capital improvement project budget and expenditures;

- Coordinating and conducting stakeholder engagement, meetings, and mailings;

- Identifying key milestones, risks, and realized risks for the recommended Program Plan.

# Background

Department Overview

The Department of Executive Services (DES) provides internal services to King County agencies and departments, and public-facing services directly to King County residents. The divisions and offices that make up DES include the Business Resource Center, Finance and Business Operations Division, Office of Emergency Management, Facilities Management Division, Fleet Services Division, Inquest Program, King County International Airport-Boeing Field, Office of Risk Management Services, and Records and Licensing Services Division. The Facilities Management Division (FMD) oversees and maintains King County's real estate assets and provides safe and secure environments for County service delivery.

### Historical Context

Harborview Medical Center (HMC) is a 540-licensed-bed hospital owned by King County and operated by UW Medicine through a Hospital Services Agreement between King County and the University of Washington (UW)., The hospital is overseen by a 13-member Board of Trustees appointed by King County.

HMC is a comprehensive regional health care facility dedicated to providing specialized care for a broad spectrum of patients, the control of illness, and the promotion and restoration of health. Harborview is one of the nation’s leading academic medical centers and is the only adult and pediatric Level 1 Trauma Center serving a five-state region (Alaska, Idaho, Montana, Wyoming, and Washington).

The medical center is home to a wide range of critical medical and behavioral health services, including state-of-the-art emergency medical services, general medicine and specialty clinics and centers of excellence in burn, neurosciences, ophthalmology, infectious disease, and rehabilitation therapy. Harborview’s mission ensures that the following patients and programs are given priority care:

- Persons who are non-English speaking poor

- Persons who are uninsured or underinsured

- Persons who experience domestic violence

- Persons who experience sexual assault

- Persons incarcerated in King County’s jails

- Persons with mental illness, particularly those treated involuntarily

- Persons with substance abuse

- Persons with sexually transmitted diseases

- Persons who require specialized emergency care

- Persons who require trauma care

- Persons who require burn care

Services Offered at HMC - The Harborview campus facilities house a variety of services provided by UW Medicine and King County as highlighted below:

- Behavioral Health: A variety of in and out-patient behavioral health services, including psychiatric emergency services, outpatient clinics, and medication-assisted treatment are provided at the HMC campus. In addition, King County’s Superior Court operates the Involuntary Treatment Act (ITA) Court at Harborview.

- Trauma Response: As the only Level I Adult and Pediatric Trauma Center in Washington, HMC provides specialized comprehensive emergency services to patients throughout the region and serves as the disaster preparedness and disaster control hospital for the City of Seattle and King County. It is also the only Level 1 Trauma Center serving a five-state region (Alaska, Idaho, Montana, Wyoming, and Washington).

- International Medicine: HMC is unique in its offering of an International Medicine Clinic, providing primary care and mental health care services to adult refugees and immigrants. Staff speak several languages in addition to English, including Spanish, Amharic, Cantonese, Chao Jo, Mandarin, Hmong, Khmer, Laotian, Mien, Oromo, Somali, Tigrinya, and Vietnamese; interpreter services are also available.

- Emergency Management / Disaster Relief: The medical center is the regional emergency management command center during a natural disaster or major crisis event. The hospital is required to have flexible inpatient beds, operating capacity, and rapid response systems as needed for crisis response.

- Infection and Infectious Disease Control: HMC is at the forefront of containing and combating infectious diseases. Harborview is required to have clinical facilities and isolation room capacity to respond to emergency infectious disease outbreaks.

- King County Clinics and Services: A number of King County’s core public health services are located at Harborview, including the Tuberculosis (TB) Clinic, Sexual Health Clinic, the County’s Public Health Lab, and the King County Medical Examiner’s Office (MEO). The King County Regional Homeless Authority operates a 24/7 homeless shelter at Harborview Hall in partnership with the Salvation Army.

Harborview Facility Improvements - Over time, Harborview’s medical facilities have evolved to meet the demands of a growing and diverse population, as well as advancements in the fields of patient care, research, medicine, and technology. King County has provided for such facility improvements and expansions through voter-approved financing, generally occurring every 15-20 years. Prior to the 2020 election, the last bond measure approved by voters was in 1999.

King County Council Motion 15183 called for the establishment of a planning group to identify hospital and community needs and make recommendations regarding the capital program to the Harborview Board of Trustees, the King County Executive, and the King County Council. The resulting Harborview Leadership Group (HLG), comprised of representatives from HMC management, the Board of Trustees, the University of Washington, labor partners, the First Hill Improvement Association, the mission population served by HMC, the King County Council, and the King County Executive Office, conducted a 13-month assessment between December 2018 and January 2020 of Harborview’s facility needs.

Supported by staff from HMC, UW Medicine, the King County Council, and the King County Executive Office, the HLG reviewed data and information provided by industry experts. The group hosted numerous community forums to gather public input. After conducting the assessment process, the HLG determined:

  - A majority of the medical center’s facilities are aging and out of date in terms of modern medical best practice standards for infection control and privacy.

- Due to facility configuration, Harborview Medical Center often operates at more than 100 percent capacity, and critical surge capacity and emergency department capacity are limited.

- The majority of the medical center’s patient beds are located in double patient rooms or multi-patient wards. On average, 50 patient beds per day cannot be used due to modern infection control requirements for shared rooms.

- A new inpatient facility would increase single-bed capacity and enable HMC to meet modern infection control and privacy standards. It would provide surge capacity for the hospital to effectively respond to a disaster or mass casualty event.

Table 1 summarizes the key elements of the HLG recommendations for capital improvements at Harborview to address the medical center’s facility needs.

Table 1 – Harborview Facility Improvement Recommendations

| Harborview Facility Improvement Recommendations: Harborview Leadership Group 2020 |  |
| --- | --- |
| Component Name | Component Description |
| New Tower | Increase bed capacity; expand/modify ED; meet privacy and infection control standards; disaster preparedness; plant infrastructure |
| New Behavioral Health Building | Existing behavioral health services/programs and Behavioral Health Institute services/programs |
| Existing Hospital Space Renovations | Expand ITA court; move/expand gamma knife; lab; Public Health TB, sexually transmitted disease (STD), MEO; nutrition, etc. |
| Harborview Hall | Seismic upgrades; improve and modify space; create space for up to 150 respite beds; (maintain enhanced homeless shelter in most appropriate location) |
| Center Tower | Seismic upgrades; improve and modify space for offices |
| Pioneer Square Clinic | Seismic and code improvements; improve and modify space for medical clinic/office space |
| East Clinic | Demolish East Clinic building |

Ultimately the HLG provided recommendations to the Harborview Board of Trustees, King County Executive, and King County Council on the size and scope of a potential bond measure.

The King County Council, via Ordinance 19117, voted to place Proposition 1 on the November 2020 General Election ballot for consideration by King County voters. The measure sought voter approval of $1.74 billion in general obligation bond funding over 20 years for health and safety improvements at Harborview Medical Center, including: increasing critical health care capacity; updating and expanding infection control capability; and expanding capacity for behavioral health services.  On November 3, 2020, over 76 percent of King County residents once again confirmed their commitment to public health and Harborview Medical Center through the approval of Proposition 1.

County Bond Program Launch - The first two years of the Bond Program work (2021-2022) saw FMD establishing the structures and processes necessary to effectively implement the historic, multi-year Harborview Bond Program. Bond Program start-up activities included:

- Hiring key County staff;

- Selecting project management firms;

- Developing financial accounting reporting protocols;

- Expanding partnerships and collaborations with Harborview staff; and

- Establishing monthly meetings with the King County Auditor’s Office staff.

For additional information, please see the biannual Harborview Bond Program reports transmitted to the King County Council for June 2021, December 2021, June 2022, and December 2022. Please note that these reports are replaced by this monthly report.

### Current Context

Cost Escalation - In late 2022, King County requested that its HMC Bond Program project management consulting firm, Vanir, review and update the 2019 cost assumptions used to establish the HMC Bond Program. King County requested this review both as part of its planning for the next phases of the Bond work but also due to the global COVID-19 pandemic and associated impacts to the supply chain and workforce.

Reflective of rising costs across the country post-pandemic, the Vanir team’s review and resulting Cost Study report confirmed that the HMC Bond Program faces financial pressures from the impacts of inflation, labor, and supply chain challenges. The initial Vanir team Cost Study, dated January 24, 2023, identified an estimated $900 million gap between anticipated revenues and updated cost of the Harborview Bond Program.

In February 2023, each King County Councilmember, along with leadership from UW Medicine and the HMC Board of Trustees, received individual briefings on the expanded costs. Digital copies of the Cost Study were also provided. On March 6, 2023, the King County Council’s Committee of the Whole received an initial briefing from King County FMD staff and the Vanir team (Bond Program consultants). On March 7, 2023, as a result of analysis from the Auditor’s Office, the consultants updated the Cost Study. The funding gap was updated from $900 million to $888 million (Appendix C).

On March 29, 2023, the King County Council passed Ordinance 19583 (Appendix A) calling for a workgroup to develop and submit to the King County Council, a Program Plan recommending health and safety improvements at the Harborview Medical Center that can be built within the amount of the bond revenues estimated to be available. An Ordinance Workgroup (OWG) was established shortly after passage of the Ordinance, comprised of leaders from UW Medicine, Harborview’s Board of Trustees, the King County Council, Facilities Management Division, and King County Executive’s Office.

The OWG’s recommended Program Plan submitted to the Council on August 1, 2023, has three key components: 1) construction of a new 10-story tower (base tower) with seven finished and three shelled floors; 2) construction of essential services currently located in older hospital spaces requiring renovation; and 3) expansion of County spaces located in older hospital facilities. Data provided by the Vanir team estimates that the components can be built within the $1.7 billion bond revenue amount. The recommended Program Plan was determined by the OWG after considering the operational needs of Harborview and the shared priorities of King County, the Board of Trustees, and UW Medicine.

As of the writing of this report, the Council has not yet acted on the proposed Program Plan. Therefore, this report is based on the Program Plan recommended by the OWG.

Report Methodology

This report was drafted by FMD staff.  In preparation for this inaugural report, Executive Office staff engaged with Council central staff to clarify terms and confirm the presentation of information in this report.

# IV. Report Requirements

This section is organized to align with the requirements of Ordinance 19583 (Appendix A).

## Description of the Current Program Scope

This report defines the program scope proposed in the OWG recommended Program Plan that was provided to the King County Council on August 1, 2023. This recommended Program Plan includes the health and safety improvements at the Harborview Medical Center built within the amount of the bond revenues ($1.74 billion) estimated to be available and as authorized by Ordinance 19117. As of the writing of this report, the Council has not yet acted on the proposed Program Plan. Therefore, this report is based on the Program Plan recommended by the OWG.

Recommended Program Plan Description - As outlined above, the OWG’s recommended Program Plan has three components: 1) construction of a new 10-story tower (base tower) with seven finished and three shelled floors; 2) construction of essential services currently located in older hospital spaces requiring renovation; and 3) expansion of County spaces located in older hospital facilities. Integrated within these components are necessary supporting infrastructure such as a new roadway and energy infrastructure.  The scope of the Program Plan components are detailed below in Tables 2 and 3.

Table 2 - Program Plan Component 1: New In-Patient Tower

| New Tower Component | Description of Planned Component | Estimated Square Footage of Completed Component |
| --- | --- | --- |
| Seven finished inpatient bed floors | - Estimated minimum 224 beds - 32 beds per floor x 7 floors = 224 new beds - Usable upon completion | 34,000 sq ft / floor |
| Three shelled inpatient bed floors | - Completed but unfinished floors - Floors, windows, walls, some infrastructure (e.g., plumbing and heating, ventilation, air conditioning [HVAC]) - Will be completed as additional funds become available | 34,000 sq ft /floor |
| 12 operating rooms (ORs) | - Additional ORs - Including perioperative support (e.g., post anesthesia care unit, prep/holding and OR support spaces) | 65,000 sq ft |
| Expanded single floor emergency department (ED) | - Expanded ED with additional single patient treatment rooms and allowing for modern models of emergency care | 87,000 sq ft (includes PES & CSU) |
| Expanded Behavioral Health Services | - Psychiatric Emergency Services (PES): renovated & expanded by up to six new single patient rooms |  |
|  | - New Crisis Stabilization Unit (CSU): 23-hour observation unit with approximately 18 recliner chairs and single patient quiet rooms |  |
| Observation Unit | - For patients requiring less than a 24 hour stay for medical care | 20,000 sq ft |
| Right-sized essential services | - Pharmacy, lab, clinical engineering, environmental services, kitchen | 150,000 sq ft |
| Parking | - Minimum 350 replacement parking spots for View Park Garage spots that will be lost to make room for new tower | 160,000 sq ft |
| Helicopter pads | - Minimum two pads; potentially a third if feasible | 35,000 sq ft |

Table 3 - Program Plan Component 2: County Space Expansion

| County Space Expansion Component | Description of Planned Component | Estimated Square Footage of Completed Component* |
| --- | --- | --- |
| Involuntary Treatment Act (ITA) Court | - Additional space for courtrooms, admin, attorney workspace, client areas, and public entry | 20,000 sq ft |
| Medical Examiner’s Office (MEO) | - Additional cooler space, offices, and education rooms | 36,300 sq ft |
| Tuberculosis (TB) Clinic | - Additional space for outreach, staff offices, and a conference room/break room | 11,000 sq ft |
| Sexual Health Clinic | - Additional clinic and office space | 22,000 sq ft |
| Public Health Lab | - TBD | TBD |

At the time of the writing of this report, analysis of the Public Health Lab space needs is underway. Subsequent reports will update this item as information is available.

This report identifies no changes to the number, size, or components of the OWG’s proposed Program Plan.

Key Elements of the Program Scope: This subsection describes key elements associated with the scope of the Program Plan. Tasks associated with these items are discussed in subsequent subsections.

City of Seattle Major Institution Master Plan (MIMP)

- The City’s MIMP establishes the zoning rules and requirements for major institutions, such as universities, colleges, and hospitals. Changes to HMC’s adopted MIMP will be made through a prescribed, multi-step process involving the City Department of Neighborhoods (DON), Department of Construction and Inspections (SDCI), the City Hearing Examiner, and the City Council in a process that could take up to two years and potentially longer.

- The County will seek approval from the City of Seattle for a major amendment to Harborview’s MIMP. The Seattle City Council has authority to revise Hearing Examiner decisions and/or attach conditions to HMC’s MIMP amendment, either of which could potentially involve open space, parking, transportation management, building height or other items, which in turn could result in increased costs and impacts to timeline.

- Since February 2023, Seattle’s DON has led meetings with a standing Implementation Advisory Committee (IAC) to discuss HMC’s facility and campus plans as part of the MIMP amendment process. Once the IAC provides its feedback to DON, the County will initiate the MIMP amendment application process.

Infrastructure Master Plan

- FMD is developing a campuswide utility and infrastructure master plan for Harborview’s campus. The infrastructure master plan will identify the condition and capacities of the existing campus utility infrastructure to develop strategies to meet the growth in demand anticipated from the bond program components. It will also include identifying engineering solutions to enable future growth, including re-routing utilities and systems; providing energy usage improvements; and developing redundancy for mission critical systems.

- The final infrastructure master plan document will be the strategic guide to infrastructure redevelopment for the campus. It will reflect the goals of HMC and the County, including resiliency; economic, environmental, and social sustainability; reducing reliance on fossil fuels; and target leadership in energy and environmental design (LEED) Platinum certification for the new inpatient tower and LEED Gold certification for the renovation of the remainder of the campus. Notably, identified alternatives and upgrades that fall outside of the scope of the proposed Bond projects may be designed and developed in future phases.

The Infrastructure Master Plan contract was awarded to OAC Consulting and, as of August 2023, the team had begun evaluating and rating of existing buildings and systems. The team projects completion by 1Q 2024.

Space Programming

- The space assessment informs the needs of key programs across Harborview campuses through 2040, including King County departments located in the hospital. Space programming includes planning for new or modified spaces for Harborview-located programs, developing and maintaining space planning guidelines, assessing available space to address changing needs, finding solutions for immediate and long-term space issues, and managing space requests and reallocations for County-owned and leased properties.

The process includes learning about department needs, and using tools to provide space, equipment, and furniture needed for the department to function efficiently. Departments consider items such as service-level projections, industry standards, operating needs, storage, adjacencies, and other spacing needs in their projected outlook.

- King County, HMC, Harborview-located departments, and various consultants are involved in space programming. This work will influence concurrent projects such as the Infrastructure Master Plan and information will be used to inform the procurement documents, such as the new tower request for proposal (RFP).

- King County and Harborview continue to lead blocking and stacking workshops to gather additional space programming information about department needs, identify location requirements, and outline general floor layouts across the Harborview campus. A consultant will be onboarded in September to further advance the space planning work.

## Updates on the Project Schedule Including Status of and Planned Dates for Major Milestones

A schedule of major milestones was included in the August 1, 2023 Harborview Program Plan Report transmitted to the Council. The timeline and milestones remain current as of the writing of this report and are shown below in Table 4. Please note one update to the milestone table below from the report transmitted in August is the addition of numbering the milestones for clearer referencing.

To expedite program development, several key tasks are occurring concurrently and driving towards procurement for design and construction of the new tower. It should be noted however, that some milestones are dependent on the sequential completion of key tasks. Meeting these major milestones include managing several tasks and sub-tasks. The subsections below outline the work being conducted by FMD around major schedule milestones and provides a three-month progress outlook.

Table 4 - Recommended OWG Program Plan Milestones

| Milestone | Estimated Completion Timeframe |
| --- | --- |
| - HMC MIMP major amendment application to City of Seattle | 3Q 2023* |
| - City MIMP process (DON, SDCI, Hearing Examiner, City Council) | 2Q 2024* |
| - Issue new tower request for proposal (RFP) | 3Q 2024* |
| - Notice to proceed | 1Q 2025* |
| - Design and City permitting | 2Q 2025-4Q 2025* |
| - Begin construction | 1Q 2026* |
| - Occupy new tower | 4Q 2028* |

## Status and Progress for Each Component Capital Improvement Projects

Component 1 – New Tower

The following narrative summarizes key elements underway for the new tower (Table 5).

Table 5 - Project Component Activities

| Item | Activities Update | Objective |
| --- | --- | --- |
| MIMP Amendment | The County is awaiting the Implementation Advisory Committee’s (IAC) recommendation letter on a major amendment to the HMC MIMP; expected in September. | Achieve City of Seattle approval of a major amendment to the MIMP. The MIMP will outline a number of actions, some of which have environmental impacts. The Environmental Impact Statement (EIS) will show the impacts of those actions and the alternatives considered by King County in the development of the MIMP major amendment application. |
| Infrastructure Master Plan | Onboarding of the infrastructure contractor OAC is underway, including campus site analysis and engineer review of existing systems. | A campuswide analysis of internal and external systems (e.g., electricity, gas, and steam), informing energy options to meet the hospital’s growing needs. |
| Space Programming | HMC is contracting with a consultant to develop a campus-wide programming master plan. Once programming information is available from HMC, the County's consultant will complete space programming for the Council-directed spaces. The selection of the consultant performing the campus-wide programming master plan is expected 4th quarter of 2023. | Assess programmatic space needs, including projected future needs to inform costs, schedule and design criteria required for the procurement process. |
| Procurement Process and development of the Request for Proposals (RFP) for the new tower | FMD staff, working with HMC and consultants, are identifying project criteria and other requirements, initiating project delivery method selection, and procurement requirements for issuing the new tower RFP. FMD is also continuing coordination of property acquisition tasks and will lead the development of sustainability objectives that will inform prospective bidders. | The objective of the new tower RFP process is to seek the prime construction contractor and subconsultants to support or manage individual projects and subprojects of the Bond Program. |

## Budgetary Update

Ordinance 19583 calls for “updates on the budget including expenditures to date and remaining budget for each component capital improvement project, budget and expenditures.” Table 6 below provides the required information along with projections for upcoming months.

Due to the timing of when the County’s monthly financial data is final and the timeline for the completion of this report for transmittal to the Council, the financial data in this report is for two months prior. To provide more relevant financial information to the Council, this report also includes projected expenditure data for the upcoming two months. In addition, subsequent reports will provide a rolling two-month projection and include variance information between projected and actual months. For example, this September report provides July actuals along with projected August and September data. The October report will include August actuals, and variance for the August projected, along with September projected and October projected data.

The 2020 voter-approved bonds are expected to provide $1.74 billion in revenue. As shown in Table 6, $67M of expenditure authority has been granted to date. July expenditures total $8.6 million. Approximately 70 percent of expenditures to date are attributed to labor costs for County and Harborview staff.

Notably, as the project moves closer to bidding of the design request for proposal in 2024, the financial reporting will transition to a more detailed budget.

Table 6 - July 2023 Expenditures and Projected Financial Data for Harborview Medical Center Capital Bond Program 2020 Prop 1 (Fund 3750)

| Fund 3750 Harborview Medical Center Capital Program 2020 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| July 2023 Data |  |  |  |  |  |
| Harborview Project Plan Component | Adopted 2023-2024 Budget Total | July 2023 Actual Expenditures | August 2023 Projected | September 2023 Projected | October 2023 Projected |
| New Tower | 21,569,984 | 76,021 | 472,729 | 524,661 | 366,631 |
| Existing Space Renovations | 35,169,985 | 810,316 | 469,908 | 952,717 | 446,817 |
| Other Costs | 10,600,000 | 0 | 0 | 0 | 0 |
|  | 67,339,969 | 886,337 | 942,637 | 1,477,377 | 813,447 |
| Total Bond Authority |  | 1,740,000,000 |  |  |  |
| Remaining Bond Authority |  | 1,672,660,031 |  |  |  |

In addition to this financial reporting, a joint County/HMC group meets monthly to monitor bond program financial activity. Members of this group include:

- UW Medicine Chief Finance Director;

- UW Medicine Controller;

- King County Business and Finance Officer;

- King County Harborview Bond Program Administrator;

- King County Executive Budget Analyst; and

- UW Medicine Accountants.

Finally, a data dashboard is provided to the Auditor’s office and the Capital Projects Oversight Committee (CPOC) each month which includes financial data.

## Update on Tasks Completed on Major Milestones Since the Preceding Report and a Three-Month Projected Outlook on Upcoming Tasks to Accomplish Milestones

Milestone 1: HMC MIMP major amendment application to City of Seattle

Tasks Completed through July

- Continued onboarding activities with infrastructure contractor OAC, including a Harborview campus site analysis with engineers to review existing systems. This work will lead to an analysis of energy options to meet the hospital’s growing needs;

- Revised infrastructure schedule to focus on overall systems in lieu of individual buildings;

- Continued blocking & stacking exercises, including communication with Public Health – Seattle-& King County for space programming needs of Harborview and King County spaces; and

- Participated on the Harborview campus master plan request for qualifications interviews and selection process with UW Medicine staff.

Projected August Tasks include

- Convene King County lead agency EIS review committee;

- Evaluation and rating of existing buildings and system by FMD and contractor OAC. The team estimates completion by 1Q 2024;

- Selection and onboarding of Harborview campus master plan consultant by HMC;

- Attend IAC meeting(s) to answer any questions about the planned MIMP amendment proposal and view a draft of the IAC recommendation letter. Since February 2023, Seattle’s DON has led meetings with a standing IAC to discuss HMC’s facility needs as part of the MIMP process. Once the IAC provides its feedback to DON, the County will initiate the MIMP amendment application process. The recommendation letter from the IAC to the City regarding a major amendment to Harborview’s MIMP shapes the development of future work and ensures the well-being of the community, and captures the collective voice and concerns of the residents, highlighting their perspectives and advocating for their interests; and

- Follow up on SDCI/King County meetings to verify status of IAC process and timing of IAC letter to SDCI that impacts timing of Bond milestones.

Projected September Tasks

- Receive initial draft of annotated MIMP and EIS amendments, and King County will lead agency review of the amendments to identify improvements and ensure regulatory guideline alignment;

- Receive copy of final IAC recommendation letter to the City of Seattle which will include requests that will impact the MIMP process;

- Verify SDCI receipt of IAC letter and obtain SDCI confirmation/concurrence with IAC letter that proposed actions align as a major amendment, so follow-up MIMP process steps can occur; and

- Draft and review notice of intent (NOI). The NOI notifies relevant authorities and stakeholders about King County’s intention to implement the recommended Program Plan on the Harborview campus.

Projected October Tasks

- File NOI with approving agency SDCI for major amendment;

- Follow-up review of draft of MIMP and EIS major amendment by King County lead agency; and

- Establish target date for submittal of draft amendments to MIMP and EIS and identify impact on Program timeline.

Milestone 2: City MIMP process (DON, SDCI, Hearing Examiner, City Council)

Following the completion of Milestone 1, the Bond Program’s projected tasks include:

- King County, as lead agency, will provide a review of the Environment Impact Statement (EIS) conditions as part of the MIMP process.

- Following NOI and completion of King County lead agency review, King County will formally submit to SDCI draft amendments to the MIMP and EIS.

Milestone 3: Issue new tower request for proposal (RFP)

Following the completion of Milestone 2, the Bond Program’s projected tasks include:

- Verifying program information from HMC to ensure Program Plan continues to meet the growing needs of the King County and UW Medicine spaces;

- Utilizing program to define the scope the full scope of bond program improvements;

- Establishing project delivery method and delineating that approach in the procurement documents for the new tower RFP.;

- Promoting the upcoming new tower RFP through digital and in-person outreach;

- Establishing project criteria for new tower; and

Acquiring approval of alternative project delivery method from in the State’s Capital Projects Advisory Review Board (CPARB).

Milestone 4 - Notice to proceed

- Milestone 4 is dependent on the completion of Milestones 1 to 3 and feedback from the MIMP process.

Milestone 5 - Design and City permitting

- Milestone 5 is dependent on the completion of previous milestones and feedback from the MIMP process.

Milestone 6 - Begin construction

- Milestone 6 is dependent on the completion of previous milestones

Milestone 7 - Occupy new tower

- Milestone 7 is dependent on the completion of previous milestones

## A Description of Stakeholder Engagement and Public Communications Over the Preceding Month Including Appearances on Agendas at Regional Meetings and Mailings

FMD conducts outreach and engagement around the Bond Program. Table 7 below provides a three-month summary outlook of known opportunities for community engagement activities. FMD expects that “to be announced” (TBA) events will have exact dates in following reports.

Table 7 – Bond Program Outreach and Engagement

| June 2023 | Event Description | Event Purpose |
| --- | --- | --- |
| Stakeholder Engagement | Attended eight community meetings: King County Immigrant and Refugee Commission, Behavioral Health Advisory Board, First Hill Improvement Association, Harborview labor partners, Pioneer Square Focus Group, Healthcare for the Homeless Network, Implementation Advisory Committee, and Yesler Terrace Community Council. | Held focus group to seek public feedback on project priorities due to cost analysis reports. This feedback was used to help determine the OWG recommended Program Plan. |
| Associated General Contractors (AGC) | Co-hosted a project briefing with the Associated General Contractors members | Share project information and seek feedback from the contracting community on bond program plans and construction industry issues. |

Bond outreach and engagement team members also attend small events and community health fairs across the Puget Sound to increase community awareness.

## A Description of Risks Including Newly Identified Risks and Realized Risks

Ordinance 19583 requires this report to include the “description of risks including newly identified risks and realized risks since the preceding monthly report, with a focus on risks that may have significant impacts on the program plan scope, schedule, or budget.” Table 8 below provides the required data.

Program and project risk refers to events or conditions that, if realized, would have a negative or positive effect. Individual risks may be known (e.g., aging infrastructure) or unknown (e.g., new regulatory requirements). Some very rare risks are considered “unknown unknowns” (e.g., a global pandemic). Realized risk can have significant impacts on program on capital project scope, schedule, budget, and quality, and can affect whether the project can meet its original objectives. By identifying and monitoring project and program risks, effective responses and mitigation can be planned and implemented with minimum impact on the project or program.

Risk management is primarily the responsibility of the program or project manager (PM) working with the project/program team, subject matter experts, and select stakeholders. A typical process is:

- Identify risks (if ‘x’ happens, then ‘y’ is a likely consequence);

- Assess risk probability and impact on scope, schedule budget, and/or quality; and

- Develop a mitigation plan for each risk.

This information is used to determine budget and schedule contingencies, communicate with sponsors and stakeholders, and inform decision-making. A common tool used to monitor risk is a risk register, which lists each risk, the associated probability and impact, risk ownership, and mitigation plan. Risks may be active, closed, or realized (i.e., point at which the risk will be managed as an issue). Risk registers are typically developed by the project team and should be updated at regular intervals or as new risks emerge or are realized. A narrative of the risk register will be included in future reports.

FMD began developing the risk register in August by identifying project risks, shown below in Table 8, and is planning a risk register workshop in September. The October report will include an updated Risk Register detailing risk categories, measurements, and mitigation planning. This will also identify high-risk items that may have significant impacts on the scope, schedule, and budget.

Table 8 – Risk Identification

# V. Conclusion

Since the approval of the $1.74 million bond funding, FMD has focused on establishing the structures and processes required to effectively implement the Bond Program. Foundational to that work has been identifying essential milestones for each phase of the project, informed by feedback from the program work group and key partners. Tasks accomplished to advance the Harborview Bond work beyond the foundational stages include:

- Participated on the campus master plan request for qualifications interviews and selection process with UW Medicine staff;

- Hosted work sessions for phasing, space programming, and sequencing;

- Completed all reporting to the IAC for the major amendment to the City of Seattle MIMP Standing Advisory Committee;

- Launched Infrastructure RFP work;

- Participated in community meetings;

- Developed agency partnerships;

- Updated cost modeling; and

- Provided monthly project updates to the Harborview’s CPOC, Board of Trustees, and King County Auditor’s Office.

Upcoming Activities Update: The upcoming activities provides a summarized outlook into scheduled work for the next two months. FMD expects to review a draft of IAC recommendations in August 2023. FMD is also preparing for community engagement on September 20, 2023, for the Regional Contractor’s Forum where team members will share status updates about the Bond Program and upcoming contracting opportunities with diverse contractors that provide services needed by the Program.

FMD team members remain committed to evaluating and implementing Bond Ordinance Work Group recommendations and mitigation strategies. This report provides details on FMD’s progress on those recommendations and identifies no changes to the OWG’s proposed Program Plan. Future reports will include progress updates as well as information regarding any changes from previous reporting.

# VI. Appendices

Appendix A – Ordinance 19583

Harborview Medical Center Mission Statement

Harborview Medical Center is a comprehensive healthcare facility dedicated to the control of illness and the promotion and restoration of health. Its primary mission is to provide healthcare for the most vulnerable residents of King County; to provide and teach exemplary patient care; to provide care for a broad spectrum of patients from throughout the region; and to develop and maintain leading-edge centers of emphasis. As the only Level I Adult and Pediatric Trauma Center in Washington, Harborview Medical Center provides specialized, comprehensive emergency services to patients throughout the region and serves as the disaster preparedness and disaster control hospital for Seattle and King County.

The following groups of patients and programs will be given priority for care:

- Persons who are non-English speaking poor

- Persons who are uninsured or underinsured

- Persons who experience domestic violence

- Persons who experience sexual assault

- Persons incarcerated in King County's Jails

- Persons with mental illness, particularly those treated involuntarily

- Persons with substance abuse

- Persons with sexually transmitted diseases

- Persons who require specialized emergency care

- Persons who require trauma care

- Persons who require burn care

Harborview's patient care mission is accomplished by assuming and maintaining a strong leadership position in the Pacific Northwest and the local community. This leadership role is nurtured through the delivery of health services of the highest quality to all patients and through effective use of its resources as determined by the Harborview Board of Trustees.

Harborview, in cooperation with UW Medicine, plans and coordinates with Public Health Seattle and King County, other County agencies, community providers, and area hospitals, to provide programs and services.

Harborview fulfills its educational mission through commitment to the support of undergraduate, graduate, post-graduate, and continuing education programs of the health professions of the University of Washington and other educational institutions, as well as programs relating to patient education.

Harborview recognizes that the delivery of the highest quality of healthcare is enhanced by a strong commitment to teaching, community service and research.

Appendix B – Harborview Mission Statement

Appendix C – Vanir Cost Study Report Updated Bond Project Cost Modeling

Appendix D – Phases of Construction

Attachment B – Harborview Medical Center Mission Statement

Harborview’s licensed number will increase to 40 to 540 when the Maleng Single Patient Bed Project is completed. The project will deliver up to 40 new single patient rooms by converting two floors in the Maleng Building into inpatient units. Bond funds are not used for the Maleng Project

The County-approved mission statement is incorporated into the Hospital Services Agreement via Ordinance 18232

The Involuntary Treatment Act (ITA) Court at Harborview Medical Center handles petitions for court-ordered mental health treatment which is not part of a criminal case.

Shelled Floor: An unfinished/non-occupiable floor with basic flooring, windows, and walls. It may also have some basic HVAC, plumbing, and electrical.

Infrastructure analysis started in August and update scheduled for 2024

These estimates are based on the data currently available. More detailed space needs calculations and analysis will be developed as part of the Bond program phasing and sequencing, and these numbers may change. Changes will be communicated in this report along with other established meetings and formats, such as Capital Projects Oversight Committee (CPOC).

This work is in progress, with the City DON Implementation Advisory Committee meeting since February 2023. Staff work has been ongoing.

As noted in the report transmitted to the Council on August 1, 2023, this schedule is predicated on working with the City of Seattle to expedite its MIMP and permitting processes, particularly items denoted with * in Table 4.

Appendix A - Ordinance 19583 lines 142-143

Note: Budget Adopted Ordinance:

- Ordinance No. 19293=$22,539,969_6/17/2021; and

- Ordinance No. 19546=$44,800,000_11/29/2022.

Note that this report was completed in August, therefore tasks for August are noted as “projected”. The October report will include August tasks completed with projected September tasks.

The Capital Projects Advisory Review Board (CPARB) process is mandated by RCW 39.10 to review alternative public works contracting procedures.

Appendix D - Phases of Construction diagram