King County Channel Migration Public Rule Update and Revisions

January 2022 Report per Ordinance 17485, Section 50.O

Introduction

Channel migration, a type of flood hazard from riverbank erosion and channel shifting, can threaten people and property. King County regulates land uses within mapped channel migration hazard areas to reduce these risks. Channel migration can be present outside of the mapped floodplain areas.

In 1999, King County adopted criteria for mapping channel migration hazard areas, and mapped four river areas (Raging, Tolt, Middle Green, and the area of the Three Forks of the Snoqualmie) that were most at risk of channel migration. Other major rivers were not mapped at that time. The County also adopted development regulations to control development within these mapped channel migration hazard areas.

This report includes a summary of work accomplished since June 2021 and lists upcoming milestones for the first and second quarters of 2022.

Ordinance Text

Ordinance 17485, Section 50.O included a King County Comprehensive Plan work program item directing that:

By June 1, 2013, the executive shall provide a report detailing the progress of the rule making process, as required by this ordinance, which will develop the criteria for the designation and mapping of the channel migration zone areas in unincorporated King County. Additional reports to provide updates on the progress on the rule making process and implementation of the designation and mapping of channel migration zones shall be provided each January 1 and June 1, until the mapping is completed. The reports required by this subsection shall be transmitted to the council in the form of a paper original and an electronic copy with the clerk of the council, who shall retain the original and provide an electronic copy to all councilmembers and to the lead staff for the transportation, economy and environment committee, or its successor.

Background

In 2012, the County updated its Shoreline Master Program and the King County Code with respect to channel migration zones (CMZ) as required by the Washington State Department of Ecology to comply with the Shoreline Management Act, RCW Chapter 90.58. With these code changes, the Department of Local Services (DLS), formerly the Department of Permitting and Environmental Review, and the Department of Natural Resources and Parks (DNRP) were required to adopt, by public rule, criteria for channel migration designation, classification and mapping, and also to adopt, by public rule, channel migration zone studies and maps (K.C.C. 21A.24.274A). Both functions were accomplished by updating the existing King County channel migration public rule in March 2014.

CMZ studies on the Cedar, South Fork Skykomish, Tolt, Raging, and Middle White rivers were completed and adopted in 2015, 2017, 2018, and 2020 respectively.

Once adopted via the public rule process, the studies are deemed “effective” and used to review land-use proposals. Studies of the remaining rivers are proceeding using the new mapping criteria specified in the public rule. Studies of the Greenwater and Lower Snoqualmie rivers have been in progress since the second quarter of 2020.

This report constitutes the required progress report.

Summary

Accomplishments during the third and fourth quarters of 2021 include the following:

The public rule serves as the administrative mechanism for adopting completed channel migration studies and the resulting mapping. DNRP applied the mapping criteria in the public rule to prepare a CMZ study and maps for applicable King County river segments along the Greenwater River in 2021. As the study and mapping were prepared, DNRP and DLS presented information at a public meeting to engage the landowners and stakeholders in the areas covered by the CMZ study and maps.

Greenwater River CMZ

- WLRD prepared a draft report and mapping, prepared presentation materials for a public meeting in coordination with DLS and hosted an online meeting in the fourth quarter of 2021.

Lower Snoqualmie River CMZ

- WLRD completed technical analyses during the third quarter of 2021 and prepared draft mapping and report during the fourth quarter of 2021.

Issaquah Creek CMZ

- WLRD staff prepared a draft Work Program Description and Outreach/Communications Plan for the Issaquah Creek CMZ study for approval.

Next Steps

- In coordination with DLS, WLRD will prepare responses to public comments received during the Greenwater River CMZ public meeting and formal comment period. Written responses will be provided in the first quarter of 2022.

- WLRD staff will finalize the draft study for the Greenwater River and provide a final study report and mapping to DLS for adoption in the first quarter of 2022. The mapping will be in effect and used for land-use review 30 days after the adoption by DLS.

- In coordination with DLS, WLRD staff will prepare public meeting materials in the first quarter of 2022. A public meeting for the Lower Snoqualmie River CMZ study is tentatively planned to occur in the second quarter of 2022.

- In coordination with DLS, WLRD will prepare responses to public comments received during the Lower Snoqualmie River CMZ public meeting and formal comment period.

- WLRD staff will finalize the draft study for the Lower Snoqualmie River and provide a final study report and mapping to DLS for adoption in the latter part of 2022. The mapping will be in effect and used for land-use review 30 days after the adoption by DLS.

- Upon approval of a Work Program Description and Outreach/Communications Plan for the Issaquah Creek CMZ study, WLRD staff will initiate field work and technical analyses in the first quarter of 2022.

- The next required status report, due to the King County Council on June 1, 2022, will include a schedule update of draft study reports and mapping to be conducted during 2022.

Information prepared in these CMZ studies is being used in conjunction with flood and landslide hazard mapping to improve information about flood-related hazards along river corridors. The studies also provide information about dynamic habitat-forming river processes and may be useful in planning efforts for regional habitat restoration.

Link to Ordinance 17485

Link to Public Rule LUD-17-1-3-PR