## STAFF REPORT

| Agenda Item: | 7 | Name: | Rachelle Celebrezze |
| --- | --- | --- | --- |
| Proposed No.: | 2016-B0007 | Date: | January 12, 2016 |

SUBJECT

A briefing on the status of Puget Sound Emergency Radio Network (PSERN) implementation as required by Motion 14437.

SUMMARY

The PSERN project will replace and upgrade the county's current emergency radio network.  King County is responsible for leading and implementing the PSERN project through completion, which is expected sometime in late 2020.  The PSERN project will be a complex undertaking, with multiple tasks over the course of the implementation period, including radio site design, acquisition and construction, as well as the acquisition of radios, consoles, and data systems.

Motion 14437, enacted in October 2015, requires the Executive to brief the Law, Justice and Emergency Management Committee (or its successor) on a quarterly basis on the status of the PSERN project in relation to the project’s identified milestones.  This briefing would represent the first required quarterly briefing under Motion 14437.

BACKGROUND

On April 28, 2015, King County voters approved a nine-year, $273 million property tax levy to fund PSERN, the replacement of the King County emergency radio communications system.

PSERN will replace and upgrade King County's nearly 20-year old emergency radio communications system, which is used to dispatch responders to incidents and allow responders to communicate with each other at those incidents.  Countywide, the current system consists of 26 transmitter sites and multiple interconnecting microwave and fiber systems, and it supports over 100 agencies and approximately 16,000 radio users, each with a portable radio handset and/or installed mobile radio in a vehicle.  The current system is owned in equal shares by King County, the City of Seattle, Valley Communications Center (ValleyCom), and the East Side Public Safety Communications Agency (ESPCA).

Once completed, PSERN will replace the current countywide emergency radio network.  PSERN will improve and upgrade the countywide emergency radio network by providing increased system reliability, increasing coverage capacity from 94 percent coverage to 97 percent coverage, providing better security on the network, and nearly doubling the number of radio transmitter sites.

PSERN Implementation.  Under the terms of the PSERN Implementation Interlocal Agreement ("Implementation ILA"), King County will be responsible for leading and implementing the PSERN project on behalf of the four owners of the current emergency radio network through completion of the project.  Oversight during that implementation period, which is expected to take approximately 5 years, will be conducted by a Joint Board, composed of 1 non-voting chair (the Executive or the Executive's designee) and 4 voting representatives, 1 representing each of the current system's owners.  The 4 voting members of the Joint Board may appoint two additional non-voting participants: a chief of a police agency and a chief of a fire agency.

The PSERN project management team includes a project director and IT and construction managers, a communications manager, a government relations official, technical support technicians and inspectors.  KCIT's Business & Finance Section and the Office of Performance, Strategy and Budget will provide financial support.  Under the terms of the $112 million, 20-year contract between Motorola and the County, Motorola will provide design, development, implementation, testing and ongoing support, maintenance and upgrade services for the PSERN project.  In addition to the primary contract with Motorola, the Executive has hired a consultant to develop the site design and intends to retain a firm to provide construction management oversight.

Under the terms of the Memorandum of Agreement Regarding Future Operation of The Puget Sound Emergency Radio Network ("Operations MOA"), ownership and operation and maintenance of PSERN after completion would be vested in a new, nonprofit organization governed by a Board of Directors.

Council Oversight of PSERN Implementation.  Motion 14437, enacted in October 2015, requires the Executive to brief the Law, Justice and Emergency Management Committee (or its successor) on a quarterly basis on the status of the PSERN project in relation to the project’s identified milestones (Attachment 1).

Table 1 below shows the 13 major milestones identified in the report transmitted by the Executive in September 2015 (2015-RPT0134) that remain to be completed during the PSERN implementation process, along with expected date of completion.

Table 1: Future PSERN Implementation Milestones and Expected Completion Dates

| Milestone | Date |
| --- | --- |
| Group 1 Site Leasing and Final Site Design | March 2016 |
| Construction Permitting | August 2016 |
| Site Construction Mid-point | September 2016 |
| Group 2 Site Leasing | August 2017 |
| Factory Acceptance Testing | September 2017 |
| Site Construction Complete (all sites) | October 2017 |
| Backhaul System Implementation | November 2017 |
| Land Mobile Radio System Implementation | September 2018 |
| System Optimization and Testing | May 2019 |
| PSERN Non-profit Operator Formation | September 2019 |
| Transition Users to PSERN System | March 2020 |
| Full System Acceptance | September 2020 |
| Project Closeout | September 2021 |

King County Auditor, Capital Projects Oversight.  On November 10, 2015, the Capital Projects Oversight Program of the King County’s Auditor’s office released a report on PSERN (Attachment 1).  The report focused on project schedule and cost risks.  The Auditor’s Office presented the report to the Government Accountability and Oversight Committee on November 10, 2015.

ATTACHMENTS:

- 2015-RPT0134 King County Auditor’s Office Report dated November 10, 2015 “Puget Sound Emergency Radio Network: Project Schedule and Cost Risks”

- PowerPoint Presentation “Puget Sound Emergency Radio Network (PSERN), Law, Justice and Emergency Management, January 12, 2016”

ATTENDEES:

- David Mendel, PSERN Project Manager, King County Information Technology

The milestones were identified in a report transmitted to Council on September 1, 2015 (2015-RPT0134).

Ordinance 18075.

The existing system is owned in equal shares by King County, the City of Seattle, Valley Communications Center (ValleyCom), and the East Side Public Safety Communications Agency (ESPCA).

Ordinance 18074.