Metropolitan King County Council

Natural Resources and Utilities Committee

## STAFF REPORT

| Agenda Item: | 4 | Name: | Peggy Dorothy |
| --- | --- | --- | --- |
| Proposed No.: | 2005-0236 | Date: | June 9, 2005 |
| Attending: | Kevin Kiernan, Manager, Engineering Services, Solid Waste Division |

SUBJECT:  Proposed Ordinance 2005-0236 would amend Ordinance 14971, the Solid Waste Export Framework Ordinance, to extend the deadline for three major work items and the final waste export plan from December 31, 2005 to April 30, 2006.

SUMMARY:  This legislation would extend the deadlines for the following work items required under Ordinance 14971, the Solid Waste Export Framework Ordinance:

- The final Waste Export System Plan;

- The report from the Interjurisdictional Technical Staff Group (ITSG) on its findings and recommendations on the potential modification or replacement of the solid waste interlocal forum, identification of dispute resolution options, development of a framework for financial policies and host city mitigation, and other issues;

- The Solid Waste Interlocal Forum’s recommendation on the continuation of the ITSG; and

- The ending date of the period during which the ITSG will advise the Metropolitan Solid Waste Management Advisory Committee (MSWMAC).

The deadlines are being extended, at the recommendation of the ITSG, the MSWMAC, and the Solid Waste Advisory Committee (SWAC) and with the approval of the Regional Policy Committee.  The intention of extending the deadlines is to provide all of these entities more time to review and evaluate options and form recommendations to the King County Executive, the King County Council and the Solid Waste Interlocal Forum on the plan to implement waste export and other issues governing the regional solid waste utility.

BACKGROUND:

On July 26, 2004, the council approved Ordinance 14971, which sets in place a framework for developing and approving the solid waste export system plan and setting a deadline for the plan of December 15, 2005.  The ordinance recognizes the interjurisdictional technical staff group (ITSG) and creates the Metropolitan Solid Waste Management Advisory Committee (MSWMAC) to work with the Solid Waste Division in development of the waste export system plan.  The waste export plan is to include a business plan addressing issues such as emergency capacity, system reliability, impact of future system choices on employees, and strategies to encourage competition and preserve service levels.

Ordinance 14971 sets deadlines for a number of important activities specified in the Ordinance.  For example, Section 6 requires the Solid Waste Division to submit a waste export system plan to the council and the solid waste interlocal forum or its successor by December 15, 2005.

The Ordinance also identifies work products for the ITSG with corresponding deadlines.  The ITSG is to assist the MSWMAC through December 31, 2005 to support the MSWMAC’s first year of work.  Similarly, the ITSG is to provide a report of findings and recommendations concerning the potential modification or replacement of the solid waste interlocal forum, identification of dispute resolution options, development of a framework for financial policies and host city mitigation, and evaluation of the impact of the proposed waste export plan on each of the provisions of the solid waste interlocal agreement between the cities and King County.  The deadline for this work product is December 31, 2005.

Ordinance 14971 includes a section that identifies important milestone reports that the division is required to make to the council.  These reports include (1) transfer system level of service standards and criteria; (2) review of system capacity and needs; (3) analysis of options for public and private ownership and operation of solid waste facilities; and (4) preliminary transfer and waste export facility recommendations and a review of estimated system costs, rate impacts and financial policy assumptions.  These milestone reports are to be submitted for council approval by motion.

Finally, the Ordinance provides for the Solid Waste Interlocal Forum to make recommendations to the Executive and the King County Council on the continuing role of the ITSG.  These recommendations would be provided on or before December 31, 2005.

The ITSG was formed in August, 2004 and regular meetings were held to develop the first milestone report and subsequently provide recommendations on the formation of the MSWMAC.  Since the formation of the MSWMAC, the ITSG has continued to function in its role as a technical forum for providing input to the Solid Waste Division for review and development of the second milestone report and providing staffing assistance to the MSWMAC.  Cities participating in the ITSG include:  Auburn, Bellevue, Federal Way, Kirkland, Redmond, Renton, Shoreline, Tukwila and Woodinville.

The MSWMAC held its first meeting in January, 2005 and has continued to meet monthly since then.  The MSWMAC is comprised of elected and staff representatives from the following cities:  Algona, Auburn, Bellevue, Bothell, Burien, Covington, Federal Way, Kirkland, Lake Forest Park, Mercer Island, Newcastle, Redmond, Renton, SeaTac, Shoreline, Tukwila and Woodinville.  The MSWMAC elected Councilmember Jean Garber, City of Newcastle, as the Chair and Councilmember Joan McGilton, City of Burien, as Vice-Chair.

The Solid Waste Division is also soliciting input during this planning process from the Solid Waste Advisory Committee (SWAC) representing those who receive solid waste services, public interest groups, labor, recycling businesses, solid waste collection companies, and local elected officials.

The ITSG, MSWMAC and the SWAC have been very active and engaged in looking at planning and development of waste export options.   The members of the ITSG, MSWMAC and the Solid Waste Advisory Committee (SWAC) have all recommended the deadlines for the following products be extended from December 31, 2005 to April 30, 2006:

- The final Waste Export System Plan;

- The ITSG’s report on its findings and recommendations on the potential modification or replacement of the solid waste interlocal forum, identification of dispute resolution options, development of a framework for financial policies and host city mitigation, and other issues;

- The Solid Waste Interlocal Forum’s recommendation on the continuation of the ITSG; and

- The ending date of the period during which the ITSG will advise the Metropolitan Solid Waste Management Advisory Committee (MSWMAC).

The recommended change in deadlines for these products would allow all three groups more time to provide for preparation, review and comment on the milestone reports and related work.

Proposed Ordinance 2005-0236 was transmitted to the Council on May 19, 2005.  The legislation was introduced on May 31st and dually referred to the Regional Policy Committee and the Natural Resources and Utilities Committee.  The Regional Policy Committee considered the legislation at its meeting on June 1, 2005 and reported it out unanimously with a “Do Pass” recommendation.

NEXT STEPS:

The next step in the waste export process is the preparation and transmittal of the third milestone report required under Ordinance 14971, which is due to the Council on June 30, 2005.  The third report will identify and analyze public sector and private sector alternatives for meeting the county’s solid waste transfer and intermodal waste export facility requirements.  This third report also will identify policy questions for consideration when analyzing alternatives in the fourth milestone report.

ATTACHMENTS:

1.  Proposed Ordinance 2005-0236

2.  Transmittal letter dated April 20, 2005