Brightwater Cost Update

Current Conditions and Trends

January 2011

Department of

Natural Resources and Parks

Wastewater Treatment Division

This information is available in alternative formats upon request by calling 206-684-1280 (voice) or Relay Service 711 (TTY).

Contents

Executive Summary	1

Background	1

Conveyance System	2

Accomplishments in 2010	3

Expected Accomplishments in 2011	4

Brightwater Cost Estimates	4

Current Cost Compared to the Baseline Budget	5

Cost Changes Since January 2010	6

M&E Sales Tax Exemption	6

Treatment Plant	6

Conveyance System	7

Uncertainties Potentially Affecting Cost	8

Disputed Costs	8

Appendix A	11

This page intentionally left blank.

# Executive Summary

The January 2011 Brightwater Cost Update describes construction trends through January 2011, identifies the costs associated with these trends, and compares costs to those presented in the January 2010 Brightwater Cost Update.

- The Brightwater lifetime cost estimate as of January 2011 is $1.849 billion.

- This represents a $33.4 million (or 1.8 percent) increase over the cost estimate presented in the January 2010 Brightwater Cost Update.

- This represents a $59.3 million (or 3.3 percent) increase over the baseline budget established in 2004 assuming 5 percent inflation.

- Based on the current lifetime cost estimate as of January 2011 and expenditures to date, the overall Brightwater project budget is 93 percent spent.

- The treatment plant is 96 percent complete.

- The conveyance system is 91 percent complete.

- King County recently reached agreement with the Washington State Department of Revenue (DOR) to secure a refund of $9.55 million based on the manufacturing and equipment (M&E) sales tax exemption.

- King County has initiated a lawsuit against the Central Tunnel contractor due to the delay in completing the work and the need to hire another contractor to complete BT-3 tunneling. The total costs shown in this report are reduced by the disputed amounts the County seeks to recover.

- The new contractor for the BT-3 Tunnel is currently mining ahead of schedule.

# Background

The 1999 Regional Wastewater Services Plan identified the need for a 36-million-gallon per-day (mgd) treatment plant and associated conveyance facilities to provide additional wastewater treatment and conveyance capacity for the northern portion of King County’s wastewater service area. The Brightwater Treatment Plant will allow for regional economic growth while protecting the environment. The January 2010 Brightwater Cost Update provides a detailed description of the Brightwater project; the following is a summary of the project’s major elements.

Treatment Plant

The treatment plant site is located in unincorporated Snohomish County near the City of Woodinville. The treatment plant will have the capacity to treat 36 mgd when it is commissioned in 2011 and will have the capability to be expanded to 54 mgd by 2040. The facility will provide advanced treatment using membrane bioreactors, which allows the County to produce and distribute up to 21 mgd of Class A reclaimed water. The treatment plant will also generate Class B biosolids that support the Wastewater Treatment Division’s current program to provide material for agricultural/forestland application as well as compost production. In addition, reclaimed water produced at the treatment plant will be sold to customers for uses such as irrigating athletic fields and golf courses.

The Brightwater Treatment Plant’s odor control system is designed to achieve the nation’s most stringent odor control standards. Construction of the treatment plant began in 2006 under two separate contracts: Site Preparation/Liquids Facilities constructed by Hoffman Construction Company for $300 million, and Solids/Odor Control Facilities constructed by Kiewit Pacific Construction for $166 million.

## Conveyance System

The conveyance system is comprised of three main components: the influent/effluent tunnels and pipelines, including the East, Central, and West Tunnels; the Influent Pump Station (IPS); and the Marine Outfall. These facilities and their construction status are described below.

- East Tunnel (BT-1). The East Tunnel includes 14,050 feet of 16.3-foot internal diameter tunnel with four pipelines installed inside that carry untreated wastewater, treated effluent, and reclaimed water between the Influent Pump Station and the treatment plant. The construction contract was awarded to the joint venture Kenny/Shea/Traylor in December 2005 for $131 million. Construction was completed in July 2010. The contract value as of December 31, 2010, is $138 million.

- Central Tunnel (BT-2 and BT-3). The Central Tunnel includes two 14.3-foot internal diameter tunnels: the eastbound BT-2 Tunnel, which runs 11,600 feet from the North Kenmore Portal to the IPS, and the westbound BT-3 Tunnel, which runs 20,100 feet from the North Kenmore Portal to the Ballinger Way Portal. The construction contract was awarded to the joint venture Vinci/Parsons RCI/Frontier Kemper (VPFK) in July 2006 for $211 million. Both tunnel boring machines (TBMs) experienced substantial delays attributed to extensive damage to the cutter heads. The BT-2 TBM was repaired and completed tunneling in July 2010.

- Central Tunnel Completion (BT-3C). Mining of the remaining 9,900 feet of the BT-3 Tunnel is being completed by the joint venture Jay Dee/Coluccio using the West Tunnel (BT-4) TBM. Mining is ahead of schedule as of March 2011.

- West Tunnel (BT-4). The West Tunnel includes 21,100 feet of 13-foot internal diameter tunnel from Point Wells to the Ballinger Way Portal. The construction contract was awarded to the joint venture Jay Dee/Coluccio/Taisei in October 2006 for $102 million. Mining was completed in the first quarter of 2010. After all adjustments to account for the Central Contract tunneling delays, the final contract value is $106 million.

- Influent Pump Station. The IPS is designed to pump up to 130 mgd of wastewater to the Brightwater Treatment Plant with the capability for future expansion. The IPS also includes standby power generation facilities. The IPS contract was awarded to Kiewit Pacific Construction in October 2006 for $92 million. The influent structure was substantially redesigned in 2009-2010 to accommodate the late completion of the BT-2 Tunnel. The project is approximately 75 percent complete.

- Marine Outfall. The Marine Outfall comprises twin outfall pipes about one mile long and 600 feet deep in Puget Sound off Point Wells, with a 500-foot-long diffuser section at the end of each pipe. The design-build contract was awarded to Triton Marine in 2007 for $28 million. Construction was completed in December 2008. The final contract value is $29.8 million. A separate contract for about $500,000 will be awarded to remove diffuser caps prior to conveyance system startup in 2012.

Ancillary Facilities

- North Creek Pump Station Modifications. This contract included a flow diversion structure, reclaimed water facility, flow monitoring, and odor control. The Brightwater portion of the construction contract cost was $8.3 million. Work has been completed and the contract is closed.

- Hollywood Pump Station Improvements. This contract included a 450-square-foot chemical injection facility with storage tank, feed pumps and containment structure, electrical controls work, and standby power generation. The Brightwater portion of the construction cost was $825,000. Work has been completed and the contract is closed.

- Kenmore and Ballinger Odor Control Facilities. Construction of odor control facilities at the Kenmore and Ballinger Way Portals is scheduled to begin in 2012 with completion in 2013 at an estimated cost of $2.3 million.

- Mitigation. Mitigation refers to the various measures taken to address construction and operational impacts associated with Brightwater construction in host communities. These host communities encompass the five construction sites that make up the Brightwater project: the treatment plant site, three conveyance portals, and a fourth combined portal and Marine Outfall location adjacent to Puget Sound. The total mitigation budget of $148.6 million is unchanged from the budget first presented in the January 2007 Brightwater Cost Update. Certain mitigation expenditures have also come in under budget.

## Accomplishments in 2010

King County, its contractors, and its consultants accomplished a significant amount of work on the Brightwater project in 2010. Some of the major accomplishments are listed below.

#### Treatment Plant

- Liquids facilities: completed the construction of all structures and installation of equipment and treatment systems with the exception of the membrane cassettes. Began component testing including instrumentation and control (I&C) systems.

- Solids facilities: completed construction of all structures and installation of equipment and treatment systems. Began component testing including I&C systems.

- Completed startup planning and began equipment and system testing. Assigned operating staff to the plant and began their training.

#### Conveyance System

- East Tunnel (BT-1): completed all contract work.

- Central Tunnel (BT-2): completed tunnel mining of the BT-2 Tunnel in July and began the installation of pipes and top slab in the tunnel.

- Central Tunnel (BT-3): deleted tunneling of remaining 9,900 feet of BT-3 Tunnel from this contract.

- Central Tunnel Completion (BT-3C): refurbished the BT-4 TBM at the Ballinger Way Portal and began mining from the Ballinger Way Portal toward Kenmore in late September. Mining progressed on the planned schedule through year’s end.

- West Tunnel (BT-4): completed mining of the West Tunnel; achieved substantial completion in April 2010, which allowed King County to execute a new contract for completion of the BT-3 mining using the BT-4 TBM.

- Influent Pump Station: nearing completion on construction of the pump station structure and installation of mechanical equipment. Construction is well underway on the generator building, odor control facilities, and the influent structure.

#### Mitigation

- Continued construction on the Environmental Education Community Center and began landscape installation along the perimeter of the treatment plant.

- Through 2010, most of the mitigation budget was expended while implementing projects in the communities neighboring Brightwater Construction. At present, some budgeted mitigation funds remain unexpended, and the potential exists for mitigation to come in under budget.

## Expected Accomplishments in 2011

Table 1 shows the expected accomplishments for the Brightwater project in 2011.

Table 1

Expected Brightwater Project Accomplishments in 2011

| Activity | Expected Completion |
| --- | --- |
| Treatment Plant |  |
| - Complete clean water operational testing in treatment plant and Influent Pump Station | May |
| - Begin wastewater treatment | August |
| - Close out liquids and solids contracts | December |
| Conveyance System |  |
| Central Tunnel (BT-2) |  |
| - Complete tunnel pipe installation in BT-2 Tunnel | September |
| Central Tunnel Completion (BT-3C) |  |
| - Complete mining of the BT-3 Tunnel | September |
| Influent Pump Station |  |
| - Begin pumping wastewater to treatment plant | August |
| Mitigation |  |
| - Host treatment plant and Environmental Education Community Center opening ceremony | September |

# Brightwater Cost Estimates

King County has prepared 10 cost updates for the Brightwater project, each at key points in the project’s lifecycle. Each estimate incorporates additional information that has increased the amount of certainty about the final cost of the Brightwater project. A summary of each cost estimate is provided in Appendix A. The current lifetime cost estimate for the Brightwater project is shown in Table 2. Note that these costs do not reflect disputed costs associated with the Central Tunnel construction delays, which are discussed in the section titled “Uncertainties Potentially Affecting Costs.” In the January 2010 Brightwater Cost Update submitted previously, the costs were expressed as a range to reflect the difference between securing a full refund for the M&E sales tax exemption on biosolids and reclaimed water equipment ($41 million refund was initially requested) and receiving no refund. On February 25, 2011, the County reached agreement with DOR and will receive a $9.55 million sales tax refund for machinery and equipment used to produce biosolids. The agreement resolves the uncertainty around this issue, so the cost estimate presented in this update report is not expressed as a range.

Table 2

Comparison of Brightwater Cost Estimates Since January 2010 (Millions)a

| Brightwater Component | January 2010 | January 2011 | Dollar Change | Percent Change | December 2010 OMCb Estimate |
| --- | --- | --- | --- | --- | --- |
| Treatment | $884.2 | $885.1 | $0.9 | 0.1% | $895–$904 |
| Conveyance | $931.6 | $964.1 | $32.5 | 3.5% | $919–$951 |
| Total | $1,815.8 | $1,849.2 | $33.4 | 1.8% | $1,814–$1,856 |

a Totals may not add due to rounding.

b Oversight monitoring consultant.

## Current Cost Compared to the Baseline Budget

In October 2004, the County developed a baseline cost estimate for the Brightwater project of $1.483 billion (2004 dollars). Table 3 shows the baseline estimate escalated for inflation at 3 and 5 percent per year and compares them against the current Brightwater estimate with inflation.

Table 3

Brightwater Baseline Costs Compared to the January 2011 Estimate (Millions)a

| Brightwater Component | Baseline Cost (2004$) | Baseline Cost with 3% Inflation | Baseline Cost with 5% Inflation | January 2011 Inflated | Dollar Change with 5% Inflation | Percent Change with 5% Inflation |
| --- | --- | --- | --- | --- | --- | --- |
| Treatment | $578.4 | $639.6 | $684.4 | $885.1 | $200.7 | 29.3% |
| Conveyance | $904.7 | $1,020.5 | $1,105.5 | $964.1 | ($141.4) | (-12.8%) |
| Total | $1,483.1 | $1,660.1 | $1,789.9 | $1,849.2 | $59.3 | 3.3% |

a Totals may not add due to rounding.

Table 3 shows that the January 2011 inflated cost estimate is about $59.3 million, or

3.3 percent above the baseline budget forecasted in 2004 with 5 percent inflation. A comparison of past Brightwater cost estimates against the baseline budget is shown in Figure 1.

Figure 1

Brightwater Cost Estimates (Inflated) 2001–2011

Compared to the Baseline Budget (Inflated)

$ 1 . 625 $ 1 . 584 $1.549 $ 1 . 660 $ 1 . 753 $ 1 . 767 $ 1 . 802 $ 1 . 799 $1.816 $ 1 . 849 $ 1 . 789 $ 0 . 00 $ 1 . 00 $ 2 . 00 2001 Phase II Siting 2002 Draft Environmental Impact Statement 2003 Final 2004 Predesign (Baseline Budget) w/ 3 % Inflation Dec 2005 Update Jan 2007 Update Jan 2008 Update Jan 2009 Update Jan 2010 Update Jan 2011 Update 2004 Baseline Budget w/ 5% inflation Billions

# Cost Changes Since January 2010

Compared to the January 2010 Brightwater Cost Update, the current cost estimate represents an increase of $0.9 million in treatment plant costs and an increase of $32.5 million in conveyance costs, for a net increase of $33.4 million. The factors contributing to these changes are explained below.

## M&E Sales Tax Exemption

King County paid sales tax on the machinery and equipment that will be utilized in the manufacturing of biosolids and reclaimed water at Brightwater. The County subsequently requested a ruling from the DOR that entitles the County to a refund based on a statutory exemption for machinery and equipment used in a manufacturing process. The DOR denied King County the exemption. In August 2010, the County sued DOR in state court for a refund of the taxes paid. On February 25, 2011, the County reached an agreement with DOR for $9.55 million of the $41 million initially requested. This agreement was made in light of pending legislation that would eliminate the M&E exemption for biosolids and reclaimed water retroactively.

## Treatment Plant

Table 4 lists the significant changes in the lifetime cost estimates for the treatment plant since January 2010. The increase in construction costs is related to change orders to both the liquids and solids contracts, totaling $5.2 million and $1.2 million respectively. Increases in the liquids and solids contracts included (1) costs for required electrical and instrumentation revisions; (2) structural, architectural, and mechanical conflicts and revisions; (3) mechanical and electrical changes required by code agencies; and (4) specific King County selected instrument escalation costs. These costs were offset by the use of construction contingency. The prior year’s sales tax calculation was adjusted to reflect the final amount of treatment plant machinery and equipment costs eligible for the exemption per agreement with DOR, as discussed. Additional costs for owner furnished equipment of $2 million were a result of requiring additional work by the controls contractor to support the complexity of the I&C systems and testing by the liquids and solids contractors.

Table 4

Brightwater Treatment Plant Cost Changes Since January 2010 (Millions)a

| Treatment Plant Element | January 2010 with 3% Inflation | January 2011 with 3% Inflation | Dollar Change |
| --- | --- | --- | --- |
| Construction Costs |  |  |  |
| Liquids contract | $242.4 | $247.7 | $5.2 |
| Solids contract | $168.6 | $169.7 | $1.2 |
| Construction contingency | $19.0 | $11.8 | ($7.2) |
| Sales tax | $30.2 | $29.8 | ($0.4) |
| Owner furnished equipment | $28.5 | $30.5 | $2.0 |
| Outside agency costs | $5.9 | $5.9 | $0.0 |
| All other construction costs | $59.7 | $57.9 | ($1.9) |

Table 4 continued

Brightwater Treatment Plant Cost Changes Since January 2010 (Millions)a

| Treatment Plant Element | January 2010 with 3% Inflation | January 2011 with 3% Inflation | Dollar Change |
| --- | --- | --- | --- |
| Non-Construction Costs |  |  |  |
| Engineering services | $76.6 | $77.3 | $0.7 |
| Construction management | $16.2 | $16.9 | $0.7 |
| Credits and revenues | ($3.1) | ($3.1) | ($0.0) |
| Other | $240.2 | $240.7 | $0.5 |
| Total | $884.2 | $885.1 | $0.9 |

a Totals may not add due to rounding.

Increases in non-construction costs for engineering services, construction management, and staffing included in the “other” category resulted primarily from the reassessment of resources required to complete the project.

## Conveyance System

Table 5 lists the significant changes in the lifetime cost estimates for the conveyance system since January 2010, which total to an overall increase of about $32 million. In terms of construction costs, the largest increase comes from a recalculation of the M&E sales tax exemption which resulted in a $31.2 million increase in sales tax. Conveyance facilities were largely removed from the calculation based on an updated assessment of eligible costs made in preparation for litigation with the DOR. There were also increased costs of about $21 million and $2.6 million for the tunneling and IPS construction respectively. These increases were primarily attributable to (1) change orders and claims resulting from differing site conditions; and (2) change orders for the IPS related to controlling groundwater leakage, differing site conditions, and construction of the redesigned influent structure. These construction cost increases were offset largely by the use of construction contingency.

Table 5

Brightwater Conveyance Cost Changes Since January 2010 (Millions)a

| Conveyance Element | January 2010 with 3% Inflation | January 2011 with 3% Inflation | Dollar Change |
| --- | --- | --- | --- |
| Construction Costs |  |  |  |
| East, central, west, ancillary contracts | $467.1 | $488.1 | $21.1 |
| Influent Pump Station contract | $95.7 | $98.3 | $2.6 |
| Marine Outfall contract | $26.1 | $26.0 | ($0.1) |
| Construction contingency | $55.1 | $34.0 | ($21.1) |
| Sales tax | $27.7 | $59.3 | $31.6 |
| All other construction costs | $29.2 | $28.0 | ($1.2) |
| Non-Construction Costs |  |  |  |
| Engineering/planning & mgmt. services | $80.5 | $83.6 | $3.1 |
| Construction management | $58.4 | $51.2 | ($7.2) |
| Other | $91.8 | $95.6 | $3.8 |
| Total | $931.6 | $964.1 | $32.5 |

a Totals may not add due to rounding.

The primary change in non-construction costs was an increase of $3.1 million in engineering costs including geotechnical engineering. The increase was due to an evaluation of the resources needed to complete the project because of the Central Tunnel construction delay. Other costs increased due to additional legal and technical resources and additional staffing totaling $3.7 million. Construction management costs decreased by $7.2 million as a result of identifying costs which are now disputed but were included in the prior estimate. This reduction is related to the disputed Central Tunnel contract delay costs.

# Uncertainties Potentially Affecting Cost

During the past year, King County continued to make significant progress in completing construction of the Brightwater project. All construction contracts, except the North Kenmore and Ballinger Odor Control Facilities and the outfall diffuser cap removal (approximately $2.3 million), have been awarded. The East Tunnel, West Tunnel, and Marine Outfall contracts have been completed. However, there are still important uncertainties facing the project:

- The final level of engineering services during construction, construction management staffing, and materials testing that will be required to complete the project.

- The disposition of the disputed costs related to the Central Tunnel litigation involving the County and VPFK, including the cost of the BT-3 completion contract.

## Disputed Costs

Due to the delay in the performance of the Central Tunnel contract, the County filed a lawsuit against VPFK and its sureties to recover the cost of hiring a different contractor to complete the BT-3 Tunnel. The County's claims in the lawsuit will also encompass all costs across the project related to the late completion of the contract. Table 6 presents two categories of disputed amounts: (1) costs that King County has paid or will pay, and seeks to recover, and (2) those amounts that King County has denied and will not pay unless by court order or agreement.

Table 6

Disputed Amounts for Central Tunnel (BT-3) Contract

| Source | Description | Costa (Millions) |
| --- | --- | --- |
| King County Seeks Reimbursement for Following Costs |  |  |
| Paid as of January 31, 2010 |  |  |
| Vinci/Parsons RCI/Frontier Kemper | Conditional Change Orders (CO) 13, 15, & 18 | $20.0 |
| Jay Dee/Coluccio/Taisei | COs 12, 14, 16, & 20 | $5.4 |
| Jay Dee/Coluccio | BT-3 completion contract payment | $38.4 |
| Vinci/Parsons RCI/Frontier Kemper | CO 21 scope reduction to Central Tunnel contract to delete construction of BT-3 Tunnel | ($16.0) |
| Jay Dee/Coluccio/Taisei | CO 15 scope reduction to West Tunnel (BT-4) contract to delete selected work activities | ($11.0) |
| Kiewit Pacific Construction | Influent Pump Station COs 16, 23, & 25 | $6.0 |
| Hoffman Construction Company | Request for Change Proposal 15, Maximum Allowable Construction Cost Change Proposal 513 | $0.1 |

Table 6 continued

Disputed Amounts for Central Tunnel (BT-3) Contract

| Source | Description | Costa (Millions) |
| --- | --- | --- |
| Sales tax | 9.5% of above costs | $4.1 |
| Subtotal |  | $46.9 |
| Contractual Obligation to Pay in Future |  |  |
| Jay Dee/Coluccio | BT-3 completion contract: completion of mining on BT-3 | $31.0 |
| Unknown | Estimated cost to complete remaining West Tunnel contract work | TBD |
| Hoffman Construction Company | CO 64 extension of Hoffman contract through 12/31/11 | $0.6 |
| Jay Dee/Coluccio/Taisei | RCO 19 increased costs of pipe for BT-4 completion | $0.6 |
| Kiewit Pacific Construction | Extension of contract through 12/31/11 | $2.6 |
| Sales tax | 9.5% of above costs | $3.3 |
| Subtotal |  | $38.1 |
| Non-Construction Costs |  |  |
| Engineering support |  | $2.1 |
| Construction management support |  | $19.0 |
| Owner Controlled Insurance Program costs |  | $3.2 |
| King County staff costs |  | $1.8 |
| Subtotal |  | $26.1 |
| King County Claims Total |  | $111.0 |
| Requests for Change Order/Claims/Appeals Denied by King County |  |  |
| Vinci/Parsons RCI/Frontier Kemper | Pending RCOs, claims, and appeals | $87.1 |
| Sales Tax | 9.5% of above costs | $8.3 |
| Vinci/Parsons RCI/Frontier Kemper Counterclaim Total |  | $95.4 |
| Total amounts at issue (King County claims and Vinci/Parsons RCI/Frontier Kemper counterclaims) |  | $206.4 |

a Totals may not add due to rounding.

Table 6 shows that the total disputed amount is about $206 million. VPFK has brought its disputed claims into the lawsuit as counterclaims. The eventual net result in terms of cost may not be determined until trial, which is currently set for September 2012.

This page intentionally left blank.

# Appendix A

Brightwater Cost Estimates 1998–2010: Primary Drivers of Cost Changes

| Base Year | Brightwater Cost Estimate | Constant Dollars (Millions) | Nominal Dollars (Millions) | Primary Drivers of Cost Changes |
| --- | --- | --- | --- | --- |
| 2001 | Brightwater Phase II Siting Estimate | $1,332 | $1,625 | Conveyance cost increases - Preferred Brightwater site was located about 13 miles inland which required additional influent/effluent pipe. - Outfall was longer and deeper in Puget Sound. - Conveyance tunnel required intermediate portals. Treatment plant cost increases - New treatment technologies were utilized. - Odor control levels were increased significantly. - Treatment optimization at peak flow was added. - Plant site increased from 40 to 100 acres per King County Council direction. |
| 2002 | Brightwater Draft Environmental Impact Statement (EIS) Estimate | $1,349 | $1,584 | Route 9 treatment plant location selected for evaluation in environmental impact statement, conveyance costs decrease due to 3 miles less tunnel and fewer portals, treatment plant costs increase due to increased odor control and Influent Pump Station (IPS) at the treatment plant. |
| 2003 | Brightwater Final EIS Estimate | $1,349 | $1,549 | Treatment plant costs decrease due to shift of IPS to North Creek, conveyance costs increase due to IPS, overall costs remain stable. |
| 2004 | October 2004 Brightwater Predesign Estimate (Baseline Budget) | $1,483 | $1,660b | County Council-adopted Baseline Budget for Brightwater Cost increases - 95 percent of cost increase was due to inflation. - Treatment plant cost increase due to replacing ballasted sedimentation with chemically enhanced primary clarification, and increasing the number of odor control units and grit processing. - Conveyance cost increase due to revised (lowered) tunneling productivity and stronger tunnel boring machines resulting from better geotechnical information. |
| 2005 | December 2005 Brightwater Cost Estimate | $1,621 | $1,753b | Cost increases - Inflation (including contractor markups). - Treatment plant increases due to underestimation of material quantities and design refinements of headworks, odor control, aeration basins, and instrumentation and control. - Significant increase in mitigation payments. |
| 2007 | January 2007 Brightwater Cost Estimate | NAa | $1,767b | Cost Increases - Inflation, both general and premium, accounted for 70 percent of construction cost increases. - Treatment plant: inflation, insurance, design refinements, and new contracting package for solids. - Conveyance system: inflation, insurance costs. |
| 2008 | January 2008 Brightwater Cost Estimate | NAa | $1,802b | Cost Increases - Inflation and market conditions on liquids and solids contracts and the conveyance IPS contract. - Higher costs for support services during construction based on an increased level of service required. - Reduction in actual revenues for sale of surplus equipment. |
| 2009 | January 2009 Brightwater Cost Estimate | NAa | $1,799–$1,844b | Cost Increases - Inflation and market conditions on treatment plant liquids subcontracts awarded. - Higher costs for support services during construction based on an increased level of service required. - Low range assumes use of the manufacturing and equipment (M&E) sales tax exemption; high range assumes no M&E exemption. |
| 2010 | January 2010 Brightwater Cost Estimate | NAa | $1,815–$1,856b | Cost Increases - Changes are primarily associated with a refined assessment of system components eligible for the M&E sales tax exemption, thus reducing the total recoverable amount. |

a Constant dollars were not used in the January 2007 through 2010 updates.

b Inflated at 3 percent per year.