Metropolitan King County Council

Budget & Fiscal Management Committee

| Agenda Item No.: | 2, 3 & 4 |  | Date: | August 18, 2004 |
| --- | --- | --- | --- | --- |
| Proposed No.: | 2004-0377 2004-0376 2004-0186 |  | Prepared By: | David Layton |

STAFF REPORT

SUBJECT:	Today’s discussion is on three pieces of legislation for the proposed New County Office Building (NCOB).  They are:

- Proposed Ordinance 2004-0377:  An ordinance to approve the NCOB lease and development documents.  Lease and development documents are the legal instruments associated with the proposed “63-20” Tax exempt lease project delivery methodology and is the final step in authorizing the Executive to proceed with construction.

- Proposed Ordinance 2004-0376:  A supplemental appropriation of $7.1 million in expenditure authority to proceed into final design (Phase III), secure property rights, and authorize acquisition of an alternate site for the county’s automotive maintenance function.

- Proposed Motion 2004-0186:  A motion to approve the reassessment of the proposed central steam plant which was necessitated by a challenge by Seattle Steam on the Executive’s 2003 analysis.  Approval of this motion will release $150 thousand of proviso restricted funds.

BACKGROUND:

Today’s discussion on the three pieces of legislation summarized above is the next steps in a series of legislative review, approval and decision points for the proposed new county office building (NCOB).  The following table illustrates how these pieces fit into the overall NCOB approval process.

| Legislation | Summary | Council Action |
| --- | --- | --- |
| Ordinance 14420 | Approval to initiate Phase I effort to evaluate options for a new/purchased office building & Phase II Central Steam Plant | 07/15/02 |
| Ordinance 14812 | Ordinance to approve Phase I recommendation to build a new office building and approved supplemental appropriation of $1.2 million to proceed into the next phase. Phase II includes site evaluation, site selection, preliminary design, engineering and Master Use Permit application | 12/08/03 |
| Proposed Motion 2004-0186 | Reevaluation of the central steam plant proposal. | 05/19/04 BFM Committee Briefing |
| Motion 11925 | Motion to approve the project plan. The plan includes Phase II scope, schedule, budget and recommendation for recovery of land value. | 05/24/04 |
| Motion 11931 | Motion to approve the Executive recommended Automotive Center Site as the location for the NCOB. | 06/07/04 |
| Proposed Motion 2004-0268 | Motion to approve the report on Work Release report Feasibility Study – Relocate and Backfill. Work Release. | 07/28/04 BFM Committee Briefing |
| Proposed Ordinance 2004-0378 | Ordinance to approve proposed 2004 Space Plan. Transmittal dated July 23, 2004. |  |
| Proposed Ordinance 2004-0377 | Ordinance to approve NCOB Lease Documents and Development Agreement. Transmittal dated July 22, 2004 |  |
| Proposed Ordinance 2004-0376 | Ordinance to approve supplemental appropriation for the next phase of NCOB design (Phase III) and explore acquisition of an alternative site for the automotive maintenance function. Transmittal dated July 22, 2004. |  |

Previous committee discussions on the various Phase II Propose New County Office Building legislation occurred on March 24th, April 7th, May 19th, May 26th and June 2nd.  Additionally, executive staff have conducted a series of design review sessions to acquaint members with the status of the design.

On June 7, 2004 Council approved Motion 11931 which approved the executive’s recommended Automotive Center site as the site for the NCOB and the Goat Hill site as the site for the parking garage.  The Council amended the motion to request a report responding to a series of issues relating to the project.  The report was to include the following:

- Property Entitlements:  Confirm current property entitlements and develop a plan to secure necessary property rights to implement the project as proposed;

- Alley Vacation:  Analyze cost and programmatic benefits of an alley vacation on the Goat hill site to allow the proposed parking structure to extend across the entire site with fewer floors.  Indicate project schedule adjustments if required;

- Reduced Garage Height:  Analyze cost and programmatic benefits of a reduced height of the Goat hill parking structure along Fifth Avenue to achieve a more pedestrian scale and consider design alternatives to maximize the setback along Fifth Avenue;

- Stepped Garage:  Analyze cost and programmatic benefits of stepping the proposed parking structure to align with the natural slope of the Goat hill site;

- Pedestrian Tunnel:  Analyze cost and programmatic benefits of extending the pedestrian tunnel connection between the King County automotive center site and the Goat hill site;

- Automotive Maintenance Function:  Finalize a relocation plan for the automotive maintenance shop function;

- KCCF Sally Port Access:  Investigate feasibility of improving access by the inmate bus to the King County Corrections Facility sally-port from the Goat hill site;

- Skybridge Relocation:  Provide a feasibility study to relocate the existing inmate skybridge function to a below grade tunnel and circulation system connection between the King County corrections facility and the King County courthouse;

- Parking Garage Operation:  Provide a parking plan to clarify how the proposed new parking structure will operate;

- Parking Revenue Policy:  Review King County Code parking ordinances to determine if policies, rates or dedication of revenues should be changed.  Make recommendations and transmit legislation to dedicate some additional parking revenues achieved through increased efficiency of the new parking facilities to debt service on the new county office building, while allowing revenues diverted to the children and family set-aside fund to grow over time;

- Financing Plan:  Provide a financing plan for the proposed parking structure on Goat hill and a separate plan for the proposed new county office building on the automotive center site; and

- Land Value Recovery:  Provide a revised financing plan which incorporates any impacts caused by any of the proposed changes listed above.  The financing plan shall include two scenarios, one to include the possibility of achieving land value recovery and the other without land value recovery.

Changing Market Conditions:  During review of the motion to approve the site selection, public testimony was heard regarding changing market conditions.  In response to the testimony FMD sought an update analysis from the real estate consulting firm of Kinzer Real Estate Services.  Kinzer evaluated market shifts in July 2004 and updated their previous analysis.  Kinzer representatives have been invited today to present an update on their analysis of the current real estate market conditions.

1. LEASE DOCUMENTS/DEVELOPMENT AGREEMENT	Proposed Ordinance 2004-0377

Today is the first review of the legislation to approve the NCOB lease documents and the development agreement which was transmitted on July 22, 2004.

The unique project delivery methodology proposed for this project utilizes a “63-20” provision of the IRS tax code.  This delivery method is a lease-leaseback arrangement rather than the traditional design-bid-build or GC/CM delivery methods used for typical capital improvement projects (CIP).  Previous “63-20” projects include the Patricia Bracelin Steel Memorial Building which opened in June 2004 and the King Street Center Building.

Specifically, under this proposed methodology will utilize the following process:

- King County will long term master lease (ground lease) the approved sites to the non-profit entity (Goat Hill Properties - GHP) created for the purpose of expediting and financing the project.

- The non-profit (GHP) would enter into a guaranteed maximum price development agreement with a developer (Wright Runstad) to design and construct the project.

- GHI will issue tax-exempt bonds in an amount sufficient to pay for the project costs.

- The developer (Wright Runstad) will draw upon the bonds to pay for construction costs.

- Upon completion of the construction, the developer (Wright Runstad) will “lease back” the project to the county.

- At the end of the lease term the non-profit (GHP) will convey title to the buildings to King County.

The legislation includes documents for three separate leases as follows:

- Goat Hill (parking garage) site ground lease

- Automotive Center (building) site ground lease

- Project lease

Approval of the lease documents and the development agreement will be Council’s last opportunity for a formal approval of the project.  However, executive staff are committed to continue with the informal project review sessions to provide council participation throughout design.

ANALYSIS:

Legal Review:  Council’s legal counsel review of the leases and development agreement resulted in a few minor legal questions and comments regarding missing items and blanks.  Aside from these minor issues the documents appeared legally acceptable.  These lease and development documents are modeled after previously approved similar documents for the King Street Center Project and the Patricia Bracelin Steel Memorial Building.  It is anticipated that the missing items will be provided as soon as final information becomes available but prior the final Council action on the legislation.

Phase II Follow-up:  The report entitled New County Office Building:  Phase II Follow-up which includes responses to the questions requested by Council in Motion 11931 was transmitted as an attachment to proposed ordinance 2004-0377.  Staff analysis of the findings is summarized in the following outline. The full text of the responses is included in this staff report in Attachment #7.

- Property Entitlements:  A strategy for securing necessary property rights is available for discussion in an executive session.  A supplemental appropriation funding request has been transmitted under proposed ordinance 2004-0376.

- Alley Vacation:  Under the current proposed design, the parking garage does not require an alley vacation and thereby avoids the additional cost and prohibitive time constraints of an alley vacation process.

- Reduced Garage Height:  In response to City of Seattle and county councilmember concerns the parking garage has been shifted east from Fifth Avenue to the east half of the site in order to create a more pedestrian friendly landscaped edge along Fifth.  This alternative location negated the need to reduce the height of the garage.

- Stepped Garage:  Same response as item “C” above.

- Pedestrian Tunnel:  Preliminary designs indicate that the existing secure pedestrian access system could be extended from the new office building to the parking garage.  Pending approval, the secure access would connect the lower lobby of the new office building via a tunnel under 5th Avenue to a secure proximity card controlled elevator lobby at the SE corner of 5th and Jefferson Street.  From this lobby pedestrians would access a covered secure horizontal tunnel to the parking garage elevator lobby.  Preliminary estimates for the pedestrian tunnel are approximately $870,000 (annual debt service approximately $60k) which is not currently included in the project.  Additionally, because the tunnel is not on county owned property the construction costs cannot be financed within the IRS tax code “63-20” lease-lease back program.  However, the tunnel could be included in the construction project assuming financing could be reimbursed from other revenue sources such as increased parking revenues.

- Automotive Maintenance Shop Function:  Previous financing models included a $2 million allowance as a placeholder to address what to do with the existing maintenance shop function.  Council requested a specific relocation plan.  Relocating the shop function to the proposed new county parking garage does not represent a highest and best use and is not cost effective.  Based on an assessment of acquisition opportunities and parking garage construction costs it is more cost effective to relocate the automotive shop function elsewhere.  The response proposes a supplemental appropriation (Proposed Ordinance 2004-0376) of $3.5 million to fund real estate market research, due diligence on acquisition opportunities, and acquisition of a new site for the automotive shop.  Discussions of acquisition opportunities would require an executive session.

- KCCF Sally Port Access:  Preliminary design documents indicate that the alley on Goat Hill is directly across from the KCCF drive through sally port.  This alley will be widened at Jefferson Street to provide a 36 ft wide level access to facilitate improved DOC inmate bus maneuverability and provide direct alignment with the KCCF sally port.

- Skybridge Relocation:  Preliminary concepts to relocate inmate transport from the skybridge to a tunnel access varied widely.  The most aggressive concept included a direct deep tunnel from KCCF to the Courthouse ($30 million).  A more modest concept utilized an indirect connection through the Administration Building of shallow tunnels and elevators ($6 million).  The study was preliminary and did not include operational impacts to DAJD Court Detail and any other impacted agencies.  Due to the complexity required to complete a thorough analysis, the Executive recommended that the skybridge relocation feasibility study be separated from the New County Office Building and considered as a separate CIP project as part of the 2005 budget.

- Parking Garage Operation:  A summary of the existing parking revenues and costs are shown in the following two tables:

Current Parking Rates

|  | Automotive Center Garage | Goat Hill Surface Parking |
| --- | --- | --- |
| Total Parking | 568 Spaces | 162 Spaces |
|  | Annual | Per Space/Month | Annual | Per Space/Month |
| Gross Revenues | $900,000 | $132 | $362,232 | $186 |
| Expenses/Month | ($230,000) | ($34) | $75,247 | ($39) |
| Net Revenue | $670,000 | $98 | $286,985 | $148 |

Current Parking Revenue Distribution

|  | Gross | Net | Human Services | Current Expense |
| --- | --- | --- | --- | --- |
| Automotive Center | $362,000 | $287,000 | $126,000 | $161,000 |
| Goat Hill Surface | $900,000 | $670,000 | $396,000 | $274,000 |
| Total | $1,262,000 | $957,000 | $522,000 | $435,000 |

J.	How the parking garage will be operated:  The follow-up response provides a clarification of how FMD proposes to operate the new parking garage.  The operations plan is summarized as follows:

  - NCOB site:  The 170 new parking spaces on the new county office building site (Automotive Center site) will be dedicated for the exclusive use of King County employees and county vehicles.  This parking will be a combination of reserved and festival (unreserved) spaces.

  - New Parking Garage site:  The remaining 816 parking spaces on the will be open to the public as well as employee and county agency vehicles.  Parking will accommodate a combination of monthly, daily, and hourly parking on a festival basis (unreserved space).  Monthly customers will be given priority to ensure that parking will always be available.  Daily and hourly users will be available on a “space available” basis.  The parking plan will utilize overbooking techniques used by private sector parking garage operations to ensure maximum efficiency.

  - Strategy for Establishment of Parking Rates:  The report recommends that parking rates be established based the following prioritized sequence:

- Establish daily and hourly rates based on market conditions.

- Use the daily and hourly rates to establish an equivalent monthly festival parking rate.

- Use the monthly festival parking rate to establish an equivalent rate for monthly reserved parking rate.  The reserved parking rate would be priced to reflect the sufficient to recover the inability to the county to utilize this space when vacant (i.e. inability to overbook).

The report further recommends that the new parking garage be operated like a business and that fees and charges would be regardless of the user’s status.  Assignments, labor agreements, or other special conditions that would require or justify reduced or no payment would become the responsibility of the benefiting program or agency with appropriate justification and controls on those payments.  Under this proposal the parking garage operation would no longer subsidize reduced rate users.  With the exception of individual ADA patrons groups currently receiving special treatment would have to be subsidized by the benefiting program.

The original NCOB pro-forma assumed the NCOB debt service would be generally covered by a combination of assumed allocation of revenue sources of tenant lease cost savings and other revenue sources related to the NCOB.  The only parking revenue assumptions in the proforma were the revenues generated by the addition of approximately 250 new parking spaces created by the project (i.e. $460,000 annually).  The Council requested a separate financial plan for the proposed new parking garage to confirm if parking revenues could cover the proportional debt service for the parking structure.  According to the Follow-up report, assuming current parking rates, and commitments to human services and CX remain unchanged; the added revenues resulting from the addition of 250 new spaces plus increased efficiencies would be inadequate to cover the debt service the new parking garage (see following table).

Parking revenues would be adequate to cover the parking garage debt service assuming the average monthly parking rates for 2007 were increased by approximately $37 per month (24%) to $190 per month.

Parking Financial Plan – Distribution Alternatives

|  | Existing Parking Conditions 2004 | Follow-up Report Financial Plan | Rate Adjustment Necessary to Cover Debt Service | Comments |
| --- | --- | --- | --- | --- |
| Total Parking | 730 | 986 | 986 |  |
| CX | $435,000 | $435,000 | $435,000 | Assumed Unchanged |
| Human Services | $522,000 | $522,000 | $522,000 | Assumed Unchanged |
| Expenses | $305,000 | $305,000 | $305,000 | Assumed Unchanged |
| Project Cost (NPV) |  | $13,100,000 | $13,100,000 |  |
| Annual Debt Service (2007) |  | $1,187,338 | $1,187,338 |  |
| Parking Revenues |  | $757,460 | $1,187,338 |  |
| Average Net Rev./Space/Month | $148 Goat Hill | $153 (escalated 2007) | $190 (escalated 2007) |  |
| Average Net Rev./Space/Month | $98 Auto Center |  |  |  |
| Net Revenue (1st year) |  | ($429,877) | $0 |  |

A preliminary parking market analysis was conducted by the developer’s parking consultant indicates that current market parking rates for structured parking facilities in the area are considerably higher than the county’s current parking rates.

Proposed Revenue Distribution:  FMD recommends that market rates be used for pricing both NCOB office space and parking and proposes the following prioritized revenue distribution for the parking garage:

- Priority 1:  Minimum a net distribution to debt service of $460,000 annually based on the anticipated additional revenues for 250 new parking spaces added by the project (i..e. as proposed in the original proforma).

- Priority 2:  Operating Costs to maintain the parking garage including Major Maintenance contributions (MMRF).

- Priority 3:  Maintain the current contribution to Human Services of $522,000 but adjust for inflation.

- Priority 4:  Allocate any remaining net revenues to the Current Expense fund.

It should be noted that the above revenue distribution assumes that the revenues to human services would maintain the current dollar contribution to human services (escalated for inflation) but would not increase the contribution based on a higher revenue producing parking facility (i.e. would not maintain the current percentage (44%) based contribution ).

Ultimately it is the Council that establishes parking rates and policies; however, construction of a new parking garage represents an opportunity to revisit the county’s current parking policies to determine whether or not the current parking rates, policies, and revenue distribution should be revised.  The report recommendations above would require a change to the county’s parking policies.

Parking Revenue Policy:  As a reminder, parking revenues for all King County facilities are dedicated by K.C.C. 3.32.090 (Ordinance 14639 May 12, 2003) as follows:

- 44% of parking revenues shall be distributed to the children and family set aside fund for support of health and human services activities and the remainder (56%) shall be distributed to the current expense fund.

- It is the intent of the council to annually, during the budget process, identify a portion of the revenue going to the current expense fund to be transferred to the major maintenance reserve fund to support major maintenance projects at the garage and other parking facilities, taking into account the major maintenance model and financial plan;

- The department of executive services, facilities internal service fund shall be reimbursed by the current expense fund for expenses associated with the operation of the parking program.

K& L	Revised Financial Plan:  A revised financial plan has been provided that reflects the following adjustments to the program:

- Building Increase:  The office building has been increased by 27,000 RSF from the original proforma of 261,000 to 288,000 RSF (i.e. two additional floors).  This increase is based on an economic analysis of several alternative building options (Attachment # 8) as well as the recommendation by the Properties Expert Review Task Force (PERT) that if the county builds a new building it should build the largest development permitted by code.

- Parking Garage Location:  The parking garage has been shifted to front on 6th Avenue.

- Tunnel Option:  The option includes an option to include a pedestrian secure access tunnel from the NCOB to the parking garage.  The estimate premium cost for the pedestrian tunnel is approximately $876,000.

- Vehicle Maintenance Shop:  The current proposal is to relocate the existing vehicle maintenance shop to a more cost effective location.  The original proforma included a $2 million allowance to address maintenance shop issues.  Proposed Ordinance 2004-0376 includes a $3.5 million CIP to provide real estate market research, due diligence, and acquire a new site for the vehicle maintenance shop.

- Hot Water System Changes:  The revised proforma also reflects a change in the recommendation to provide a central hot water system for the county’s downtown complex of buildings.  Assuming the hot water system will serve only the new county office building and possibly the Administration Building (excluding the Courthouse and the King County Correctional Facility) anticipated cash savings have been deleted from the proforma.

Program Approval:  The 27,000 RSF increase in project scope is unprogrammed space.  According to the project schedule, the follow-up report (Attachment #7), and discussions executive staff, final programming will not be finalized until later in the project.  Under this proposed sequence the final decision on who will occupy the NCOB would not be made until after council has approved the lease documents & development agreement.  According to the King County Code the authority to approve building programs resides with the Council.   This authority is defined under applicable Capital Improvement Projects (CIP) sections.  However, the code appears to be less clear on the approval process where leases are concerned.  According to the PAO the “63-20” Lease-Lease Back process is a lease.  As such the Council’s last approval point for the NCOB appears to be the approval of the lease documents and the development agreement.

Absent a council policy direction on the occupants (i.e. the program) the final decision on who will occupy the NCOB will likely be made by the executive without a mandated council approval process.

Financial Plan:  Assuming the guaranteed maximum price (GMP) will be within the budget, the revised financial model incorporates the variables noted above and demonstrates a positive cash flow after four years and if cash savings from a central hot water system is eliminated positive cash flow will occur after the sixth year (Attachment # 9).

Reasonableness								Not ready for Action

Despite limited time constraints, executive staff have made significant progress on the proposed NCOB lease and development agreement legislation.  However, as noted above in the legal review section, the documents as transmitted still lack several important key elements which would preclude committee action on the proposed legislation at this time.

A summary of these missing items are:

- Miscellaneous blanks in the leases and development agreement.

- The guaranteed maximum price (GMP).

- The Tenant Improvement Allowance.

- The “not to exceed” Average Monthly Rent figure.

- King County Risk Management response to several PAO questions.

- Lease Agreement, Exhibit B; Plans & Outline Specifications.

- Lease Agreement, Exhibit C; Project Schedule.

- Development Agreement, Tenant Contingency Amount.

- Development Agreement, Exhibits A & B; Legal Descriptions

- Development Agreement, Exhibit C; Project Lease Agreement

- Development Agreement, Exhibits D & E; Base Shell & Core Costs

- Development Agreement, Exhibits F; Project Budget

- Development Agreement, Exhibits G; Preliminary Plans & Specifications.

- Development Agreement, Exhibits H; Project Schedule.

- Final Project Financial Plan

Guaranteed Maximum Price:  The key missing element is the guaranteed maximum price (GMP).  The GMP is the key to all other final cost elements including the proforma, project budget, financial plan, monthly rents, shell & core costs, tenant allowances, and ultimately project scope.  The GMP will not be finalized by the developer until August 31st and executive staff will need until the first part of September before final documents can be transmitted to council for consideration.

Approval of Lease Documents & Development Agreement is Not Time Critical:  Council approval of the lease documents and development agreement is not mandatory at this time.  Assuming council approves the supplemental appropriation request to provide expenditure authority to proceed with NCOB Phase III design prior to budget (Proposed Ordinance 2004-0376 - $1.5 million) the project schedule will not be impacted.  Approval of the lease documents and development agreement will need to be approved prior to the start of construction in early 2005.

Next Steps:

- Finalize Guaranteed Maximum Price (GMP).

- Finalize Lease Documents and Development Agreement.

- Confirm Council policy on NCOB tenants.

- Delete Follow-up Report reference from the proposed ordinance (Attachment G).

2. SUPPLEMENTAL APPROPRIATION REQUEST		Proposed Ordinance 2004-0376

Proposed Ordinance 2004-0376 is a supplemental appropriation request for $7.1 million to do four things:

- Phase III NCOB Project:  Provide expenditure authority of $1.9 million to secure the Master Use Permit and to complete final design of the NCOB necessary to construct the project.

- Relocate Automotive Maintenance Function:  Provide expenditure authority of $3.5 million to fund real estate market research and to acquire an alternative site for the automotive maintenance shop function currently located in the Automotive Center Parking structure.

- Property/Development Rights:  Provide expenditure authority of $1.6 million to secure property/development rights related to the NCOB.

- Unreleased or Underfunded Phase II Work:  Two of the proviso restrictions of the ordinance that approved NCOB Phase II expenditure authority (Ordinance 14812) have to be released by the Council.  These two restrictions equate to $400,000 of the total $1.2 million appropriated and have created a cash flow problem for the work of Phase II.  The $1.9 million requested to fund Phase III above includes an additional $400,000 to cover the current shortfalls in Phase II.

PHASE III NCOB PROJECT:  								$1.9 Million

Phase III consists of the effort necessary to complete the Master Use Permit process scheduled for December 2005 and the completion of final design and construction documents necessary to construct the NCOB.  A summary of the scope of work tasks and budget is included in Attachment #10.

RELOCATE AUTOMOTIVE MAINTENANCE FUNCTION:  			$3.5 Million

This request is based on the results of an analysis that evaluated the most cost effective location for the automotive maintenance shop function currently located in the Automotive Center Parking Garage.  The analysis was precipitated by the NCOB project, which proposes to demolish the existing Automotive Center Parking Garage and replace the parking in a new parking structure on Goat Hill.  The original NCOB proforma included a $2 million allowance as a placeholder to address the maintenance function until a final decision could be developed.  This supplemental request is the result of a recommendation by the executive to relocate the maintenance function to an alternative site.  The request will cover real estate market research, due diligence, and acquisition of an alternative site.

The financial analysis to locate the automotive maintenance function in the Goat Hill parking structure resulted in an equivalent cost and loss of parking revenue of $3.8 million over 25 years (excluding maintenance equipment costs).

PROPERTY/DEVELOPMENT RIGHTS:						$1.6 Million

Discussion of this item deals with real estate issues, which will need to be addressed in an executive session.

UNRELEASED OR UNDERFUNDED PHASE II WORK:				$400,000

Included in the $1.9 million request are sufficient funds to cover the proviso restricted funds ($400,000) from phase II (Ordinance 14812) for two reports for which the council has yet to take action.  Release of these restricted funds was the subject of a letter from the Executive to the BFM committee chair dated July 15, 2004 which clarified a Phase II cash flow shortfall.

- New County Office Building Central Steam Recommendations – Reassessment:  $250,000 restricted until the council approves by motion a report on the reevaluation of the central steam plant recommendation.  This report was transmitted on March 31, 2004 (Proposed Motion 2004-0186) and was first heard in committee on May 19, 2004 and is on the committee agenda for consideration today.  Council has not taken action to approve this motion as the recommendation was preliminary pending a final recommendation concurrent with the transmittal of the GMP in July.  Even though the energy system is still not finalized the final recommendation will not include a central steam system, therefore, release of the restricted funds at this time appears reasonable.

- New County Office Building Work Release:  $150,000 restricted until council approves by motion a report on the relocation of Work Release (WER).  This report was transmitted on June 30, 2004 (Proposed Motion 2004-0268) and was scheduled to be heard in committee on July 28, 2004 but was postponed due to time limitations.  Committee discussion of the WER report is tentatively scheduled for September 22nd.

Options for Release of Restricted Funds:  Council has three options to address release of the proviso restricted funds

- Approve Proviso Report Motions:  Approve the original reports by motion as required by the provisos to Ordinance 14812 (Proposed Motion 2004- 0196 and Proposed Motion 2004-0268).  The timing of approvals of these two motions may take some time which would perpetuate the cash flow problem.

- Approve Release of Funds via Separate Legislation:  Release the proviso restrictions via a different legislation such as the 2nd Quarter Omnibus Ordinance currently scheduled for committee action on August 25th.  Given the schedule implications of #1 & #3 this option may be the most direct and responsive of the three options.

- Approve this Supplemental Appropriation Request:  Approve this ordinance (Proposed Ordinance 2004-0376) as proposed.  This action would provide expenditure authority for $400,000 and would negate the need for council to take action on the two proviso motions listed above.  However due to the delay in receipt of the final GMP final action on this legislation is likely to be postponed until sometime in September.  If the release of restricted funds is accomplished under either #1 or #2 above then the Phase III supplemental request of $1,982,500 could be reduced by $400,000 to $1,582,500.

Reasonableness							Not Ready for Action

Consideration of the proposed legislation to move into Phase III should be postponed until Phase II is finalized sometime in September.

Next Steps

- Consider Release of Steam Plant Restricted Funds:  Consider an alternative legislative vehicle to release expenditure restricted funds ($250,000) and not taking action to approve the steam plant reevaluation report.

- Consider Release of Work Release Restricted Funds:  Consider an alternative legislative vehicle to release expenditure restricted funds ($150,000) on the Work Release report until the committee can take action to approve the report in September.

- Amendment:  If the release of funds is accomplished under #1 and #2 above then Proposed Ordinance 2004-0377 would need to be amended to reduce the request for Phase III by $400,000.

3. CENTRAL STEAM PLANT REEVALUATION		Proposed Motion 2004-0186

The only previous committee discussion on the Central Steam Plant Reevaluation report occurred on May 19, 2004.  It was reported at that meeting that the report recommendations were preliminary and that a final decision would not be made until the design was finalized and the guaranteed maximum price (GMP) was determined in late July.  As a result the committee postponed action on the motion until the recommendations were finalized.

During the review of the NCOB site recommendation (Motion 11931) the Council requested numerous additional work items which caused several new work items and some Phase III work to be accelerated.  The Executive informed the Council of a cash flow shortfall in a letter to the BFM Committee Chair dated July 15, 2004.

Consideration for a central steam plant for King County has occurred in three phases.  The final recommendation to move forward with a central steam plant serving the county’s downtown complex of buildings and Harborview Medical Center was transmitted concurrent with Phase I of the New County Office Building in September 2003.  Energy savings from the county-owned central steam plant were projected to be $8.2 million over a 25-year period.

At the December 3, 2003, BFM Committee briefing on the report, the results of the Executive’s analysis were challenged by Seattle Steam Company in a report by funded by Seattle Steam (A.E. Associates).  A subsequent joint meeting on December 4, 2003 between Facilities Management Division (FMD), Seattle Steam Company representatives and BFM Committee staff confirmed that the findings of the two reports would require additional time to reconcile.

Reassessment Proviso:  In response to this the Council approved the Executive’s request for a supplemental appropriation request for the NCOB phase II but added a proviso restriction requiring a reassessment of the central steam plant recommendation in order to give executive staff time to resolve the steam plant issue.  The text of the proviso is:

“Of this appropriation for CIP project number 395210. King County Office Building Feasibility $250,000 may not be expended or encumbered until the executive submits a report and council approves by motion the following report:  A reevaluation report of the central steam plant feasibility study by R.W. Beck, contained in the report entitled An Approach to Reducing King County Office Space Costs, dated September 15, 2003.  The report shall include a response to the report prepared by Seattle Steam Company entitled Analysis of King County Steam Plant Reports, dated December 2, 2003.  The report shall also be coordinated with Seattle Steam Company contract agreements with King County and Harborview Medical Center and include a legal interpretation of the terms of these agreements.”

The reassessment report was transmitted on March 31, 2004.  Based on a review of the report New County Office Building Project Central Steam Recommendations - Reassessment it is clear that the original recommendation was overstated and that the economic benefits of a central steam plant are substantially less than originally forecast. Several key areas of the central steam plant contributed to this conclusion are summarized below:

- Core Plant and Required Storage

- Piping/Steam Distribution

- Interim Construction Costs

- Harborview Retrofit

- Energy Efficiency

The reassessment report also challenged several key assertions contained in the Seattle Steam report.

Reassessment Report Recommendation:  The reevaluation report Executive Summary concludes that:

“…the county not move forward with a central steam plant serving both King County and Harborview Medical Center”

Preliminary Recommendation:  The report further stated that the recommendation is preliminary in order to comply with the proviso requirements contained in Ordinance 14812.  And that FMD expects to make a final recommendation on the alternative approach as the new building is designed and the maximum construction cost is determined.

Reasons given for the reversal of the previous recommendation include construction risks, market risks, and uncertainties of purchasing steam from an unregulated vendor.  The current recommendation is that:

“FMD… recommends pursuing an option that would provide similar economic benefits to the County as the central steam plant but at much lower outcome risk.”

The recommended option included an increased boiler size for the NCOB sufficient to provide hot water to the County’s downtown core buildings in lieu of steam.  The boiler room was proposed to be located in the NCOB rooftop mechanical equipment space.  The downtown core buildings include: the Courthouse, Administration Building, King County Corrections Facility, and the Proposed New County Office Building.  Harborview Medical Center is no longer included in the reassessment recommendation. Under this recommendation Harborview would continue to rely on Seattle Steam as a vendor for the foreseeable future but the county would reduce its reliance on Seattle Steam.

Expenditures:  Expenditures to date for the steam plant feasibility studies and reevaluation report are:

| Description | King County | Consultants | Total |
| --- | --- | --- | --- |
| Phase I (Harris Group/Notkin) | - | $26,995 | $26,995 |
| Phase II (R.W. Beck) | $31,436 | $65,409 | $96,845* |
| Reassessment | $12,457 (estimate to date) | Included in WR scope of work for new office bldg. | $12,457 |
| Total | $43,893 | $92,404 | $136,297 |

* Harborview contributed $50,000 to the phase II analysis.

Current Status:  The final decision will not be made until the Guaranteed Maximum Price (GMP) is finalized in early September.  However, according to discussions with executive staff the current direction will likely be a stand alone central hot water system serving only the NCOB and possibly also the Administration Building.  Hot water systems for the Courthouse and the King County Corrections Facility (KCCF) and possibly the Administration Building will no longer be included in this project.  The current plan is that these buildings would be provided with idividual hot water boilers located in each building as part of a series of separate stand alone CIP projects.

Reasonableness:  								Not Ready for Action

The central steam plant reevaluation report as transmitted provided only a preliminary recommendation.  The final recommendation will not be complete until early September and according to executive staff the final recommendation appears to be headed toward a traditional stand alone hot water system.  Since the current design is a complete departure from a central steam plant concept and since the preliminary recommendations are no longer current; approval of the report appears mute.  However, given the cash flow problem noted above it appears reasonable to release the restricted expenditure authority.

Next Steps:.

- See Next Steps for Proposed Ordinance 2004-0376 above

INVITED:

- Kathy Brown, DES Director, Facilities Management Division

- Dave Preugschat, DES Deputy Director, Facilities Management Division

- Jim Napolitano, DES Capital Projects Manager

- Tom Kuffel, King County Deputy Prosecuting Attorney

- Craig Kinzer, Kinzer Real Estate

ATTACHMENTS:

- Proposed Ordinance 2004-0377

- Proposed Ordinance 2004-0376

- Transmittal Letter Dated July 22, 2004

- Fiscal Note

- Proposed Motion 2004-0186

- Transmittal Letter, dated March 31, 2004

- New County Office Building Phase II Follow-up; Section 2

- Comparison of Building Options

- Revised Financing Plan

- Phase III Scope & Budget

# Footnotes

Note:  the phase II follow-up report was attached to the proposed ordinance as Attachment G.  Given that the report includes numerous alternatives and proposed executive policy recommendations that the report should have been more appropriately attached to the transmittal letter rather than the ordinance.  Staff suggests amending proposed ordinance to delete the report reference.