Metropolitan King County Council

#### Regional Policy Committee

Revised Staff Report

| Agenda Item No.: | 6 | Name: | Kelli Carroll |
| --- | --- | --- | --- |
| Briefing No.: | 2009-0239 | Date: | June 10, 2009 |

Committee Action: On June 10, 2009, the Regional Policy Committee amended and passed Proposed Motion 2009-0239 with a do-pass substitute recommendation to the King County Council.

SUBJECT

Proposed Motion 2009-0239 adopts the Mental Illness and Drug Dependency Annual Report for 2008. The staff report also discusses proposed amendments to Motion.

PURPOSE

The purpose of this briefing is to review the information contained in the Mental Illness and Drug Dependency (MIDD) annual report for 2008 to enable the Regional Policy Committee to take action on Proposed Motion 2009-0239 and its amendments.

This is the Regional Policy Committee’s second briefing on the proposed Motion. The first briefing was held on May 27, 2009.

SUMMARY

The 2008 MIDD annual report is the first annual report on the progress of the MIDD programs.  Implementation of several of MIDD strategies began on October 16, 2008.  The data contained in the annual report reflects roughly two and a half months of funding MIDD contracts.

Despite the late start in 2008, over 75 percent of the 2008 revenues were committed to community agencies, therapeutic courts, and new housing units dedicated to people with mental illness and chemical dependency.  In less than three months, 65 entities received contracts for MIDD programming and over 1,500 individuals and entities were directly impacted by MIDD programs in 2008.

Though funding was approved in October, the MIDD Oversight Committee worked diligently on several MIDD related projects throughout 2008.  Ten discreet planning work groups were initiated from the Oversight Committee to generate or review plans or respond to required work plan items.  Some of the areas that the work groups were involved with included MIDD housing, the Crisis Diversion Facility, Mental Health Court, the new strategy process, the City of Seattle strategies, and an evaluation planning work group.

In future years, it is expected that MIDD annual reports will contain more data on program utilization, performance measurement, recommendations on program and process changes, and revisions to performance measures and performance targets.

BACKGROUND

State Establishes the Sales Tax

In 2005, the Washington state Legislature authorized counties to implement a one-tenth of one percent sales and use tax to support new or expanded chemical dependency or mental health treatment programs and services and for the operation of new or expanded therapeutic court programs and services.

Authorizing the Sales Tax in King County

In 2007, the King County council adopted Ordinance 15949 authorizing the levy and collection of an additional sales and use tax of one-tenth of one percent for the delivery of mental health and chemical dependency services and therapeutic courts.  The ordinance also established a policy framework for measuring the effectiveness of the public's investment in MIDD programs, requiring the King County executive to submit oversight, implementation and evaluation plans for the programs funded with the tax revenue.  Ordinance 15949 adopted five policy goals for the programs supported with MIDD funds show in the below.

MIDD Adopted Policy Goals: Ordinance 15949

Policy Goal 1:  A reduction in the number of mentally ill and chemically dependent people using costly interventions, such as, jail, emergency rooms, and hospitals

Policy Goal 2:  A reduction in the number of people who recycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency.

Policy Goal 3:  A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults.

Policy Goal 4:  Diversion of mentally ill and chemically dependent youth and adults from initial or further justice system involvement.

Policy Goal 5:  Explicit linkage with, and furthering the work of, other Council directed efforts including, the Adult and Juvenile Justice Operational Master plans, the Plan to End Homelessness, the Veterans and Human Services Levy Service Improvement Plan and the King County Mental Health Recovery Plan.

Housing

In 2008, the Washington state Legislature amended RCW 82.14.460.  The amendment added housing that is a component of a coordinated mental health or chemical dependency treatment program or service to the list of  programs and services that are authorized for funding by the sales tax.  The statute also amended the nonsupplanting provision to allow the sales tax funds to be used for replacement of lapsed federal funding previously provided for mental health, substance abuse and therapeutic court services and programs.

Oversight Committee

In April 2008, the King County council adopted Ordinance 16077 establishing the King County Mental Illness and Drug Dependency Oversight Committee. The Oversight Committee is an advisory body to the King County executive and the council.  The purpose of the Oversight Committee is to ensure that the implementation and evaluation of the strategies and programs funded by the tax revenue are transparent, accountable and collaborative.  The Oversight Committee reviews and comments on quarterly, annual and evaluation reports as required in Ordinance 15949.  It also reviews and comments on emerging and evolving priorities for the use of the MIDD sales tax revenue.  The Oversight Committee members bring knowledge, expertise and the perspective necessary to successfully review and provide input on the development, implementation and evaluation of the tax funded programs.

Implementation Plan

In October 2008, the MIDD Implementation Plan was adopted via Ordinance 16261.  It is a roadmap for executing the programs and strategies funded with MIDD revenues.  It contains individual implementation plans for each of the 37 MIDD strategies.  The Implementation Plan also includes a schedule of the implementation of MIDD programs and services, a spending plan (for 2008), financial plan, and milestones for implementation of the programs.  The ordinance that adopted the MIDD Implementation Plan established a new strategy reserve to be included in the MIDD fund.  It stipulates that the new strategy reserve funds are to be spent on new MIDD strategies that are not specified in the adopted MIDD Implementation Plan.

New Strategy Process

Ordinance 16261 directed the MIDD Oversight Committee, with input from the Council and the Executive, to propose a process and a schedule for new strategies and programs to be considered for funding by the new strategy reserve.  The Oversight Committee's recommendation for a new strategy process was submitted to the Council along with the MIDD annual report on April 1, 2009.  The proposed new strategy process is included in this staff report as Attachment E to the annual report that is attached to Proposed Motion 2009-0239 that is attached to this staff report.  The proposed new strategy process is highlighted in a subsequent section of this staff report.

Mental Health Court Strategy 11b

The MIDD Implementation Plan that was adopted by ordinance 16261 did not include a completed, finalized mental health court strategy.  Instead, a placeholder for the Mental Health Court Strategy 11b was included in the adopted Implementation plan.  Ordinance 16261 directed the MIDD Oversight Committee to review options for enhancing the delivery of mental health court services and recommend a proposed strategy to provide MIDD funds for mental health courts in King County.  The Oversight Committee was charged with developing a mental health court strategy that provided mental health court services to more residents of King County, in more locations throughout the county, without further fragmenting of the justice system for vulnerable, mentally ill clients.

The Oversight Committee's recommendation for MIDD supported health courts was submitted to the Council along with the MIDD annual report on April 1 2009.  The proposed Mental Health Court Strategy 11b is included in this staff report as Attachment D to the annual report that is attached to Proposed Motion 2009-0239 that is attached to this staff report. The proposed revised Mental Health Court Strategy 11b is highlighted in a subsequent section of this staff report.

Evaluation Plan

In October 2008, the MIDD Evaluation Plan was adopted via Ordinance 16262.  The MIDD Evaluation Plan provides the public and policy makers with the tools to evaluate the effectiveness of the MIDD strategies, as well as to ensure transparency, accountability and collaboration and effectiveness of the MIDD funded programs and strategies.  Ordinance 16262 adopted a framework for evaluating the core MIDD strategies.  It species what data will be collected. It also specifies that recommended revisions to the Evaluation Plan and processes, recommended performance measures and performance targets, and new or revised performance measures and performance measurement targets for the strategies are to be identified and included in the April 1, 2009, annual report and in each annual report thereafter. The ordinance also stipulates that there will be a comprehensive review and analysis of the evaluation measures, targets, benchmarks and data related to the MIDD programs and strategies. The first such review will occur in 2011.

Annual Report

Ordinance 15949 that authorized the MIDD sales tax, Ordinance 16261 that adopted the MIDD Implementation Plan, and Ordinance 16262 that adopted the MIDD Evaluation Plan each specifies that annual reports on MIDD activities are to be provided to the Council.  Ordinance 16262 calls for the annual reports to be reviewed and accepted by motion.

There are a number of attachments to the MIDD 2008 annual report.  Three of the attachments are included in response to the Council’s direction in the above named ordinances.  In particular:

- Attachment D-Mental Health Court Strategy Recommendation

- Attachment E-New Strategy Request Process

- Attachment F-Historical Control Group Recommendation

These attachments will be highlighted in subsequent sections of this staff report.

MIDD Key Facts

- Current estimates indicate that the tax will generate $44 million in 2009, down from a projected $48.4 estimate in the fall of 2008.

- The tax became effective on April 1, 2008.  It expires on January 1, 2017. State statute does not establish an expiration date for this tax; it was established by the Council via Ordinance 15949.

- The MIDD Oversight Committee was established by Ordinance 16077 on April 28, 2008.  There are 30 members on the Oversight Committee, representing a wide array of stakeholders and policy makers.

ANALYSIS

MIDD Strategies: 2008 Achievements

MIDD funds were released in October 2008 with the adoption of Ordinances 16261 and 16262.  In less than three months, MIDD funds were used to achieve the following:

- Over 950 people served by MIDD programs between October 16 and December 31, 2008.

950 people who needed mental health and chemical dependency treatment services in King County were served by the MIDD through strategy 1a, designed to increase access to outpatient mental health and substance abuse services for individuals not on Medicaid.  Community-based mental health and chemical dependency service providers provided services to:

- 650 adults for mental illness

- 214 adults for chemical dependency

- 100 youth for substance abuse

- 65 community providers were contracted with for the implementation of MIDD programs associated with 22 different MIDD strategies.

- $16 million of MIDD funding dedicated to housing will create 335 housing units of permanent supportive for high need homeless individuals with mental illness and/or chemical dependency.

MIDD capital funds (strategy 16a) were used to support the following projects:

- Plymouth Housing Group (81 units)

- Downtown Emergency Service Center (83 units)

- Sound Mental Health (18 units)

- Transitional Resources (16 units)

- Archdiocesan Housing Authority (92 units)

- Valley Cities Counseling and Consultation (24 units)

- Community House Mental Health (23 units)

- 22 MIDD strategies initiated program implementation in 2008:

- 1a1 – Increased Access to Community Mental Health Treatment

- 1a2 – Increased Access to Community Substance Abuse Treatment (outpatient and opiate substitution therapy)

- 1c –  Substance Abuse Emergency Room Early Intervention services

- 1d –  Mental Health Crisis Next Day Appointments

- 1e –  Chemical Dependency Professional Education and Training

- 1h –  Expand the Availability of Crisis Intervention and Linkage to On-Going Services for Older Adults

- 2a –  Mental Health Caseload Reduction

- 2b –  Employment Services for Individuals with Mental Illness and Chemical Dependency

- 3a –  Supportive Services for Housing Projects

- 4d –  School Based Suicide Prevention

- 5a –  Increase Capacity for Social and Psychological Assessments for Juvenile Justice Youth

- 6a –  Wraparound Support Services for Emotionally Disturbed Youth

- 10a – Crisis Intervention Training – First Responders

- 11a – Increase Jail Liaison Capacity

- 12a – Increase Jail Re-Entry Program Capacity

- 12b – Hospital Re-Entry Respite Beds

- 12c – Increase Capacity for Harborview’s Psychiatric Emergency Services to Link

- Individuals to Community Based Services

- 13a – Domestic Violence and Mental Health Services and Systems Coordination

- 13b – Domestic Violence Early Intervention/Prevention

- 14a – Sexual Assault and Mental Health Services

- 15a – Drug Court Expansion and Enhancement of Recovery Support Services

- 16a – Housing Development

- MIDD Oversight Committee members contributed over 1,000 hours to committee business in 2008 including leading and/or participating in subcommittees and strategy planning workgroups.  Subcommittee and workgroup involvement included discussions and recommendations on the following issues:

- Housing needs (MIDD Strategy 16a)

- Crisis Diversion Facility strategy planning workgroup (MIDD Strategy 10b)

- Mental Health Court Strategy (MIDD Strategy 11b)

- New Strategy Request workgroup;

- School Based Mental Health and Substance Abuse Services Strategy (MIDD Strategy 4c)

- Medical Respite advisory committee (MIDD Strategy 12b)

- Domestic Violence and Sexual Assault planning workgroup (MIDD Strategies 13a, 13b and 14a)

- City of Seattle new strategies development workgroups (MIDD Strategies 17a and 17b)

- Evaluation Planning workgroup.

- Historical Control Group workgroup

See Attachment B for Program Utilization Statistics for each of the 37 MIDD strategies for 2008.

Evaluation and Performance Measures: 2008 Progress

The adopted Evaluation Plan provided preliminary performance measurement targets for five broad MIDD policy goals. Ordinance 16262 that adopted the Evaluation Plan specifies that preliminary performance measurement targets contained in the Evaluation Plan are to be revised over time as programs develop and change. The ordinance directs that new or revised performance measures and performance measurement targets for the strategies are to be identified and included in the April 1, 2009, annual report and in each subsequent annual report.

The MIDD Evaluation Plan adopted by Ordinance 16262 contains a framework for evaluating each of the MIDD’s 37 strategies; however, all of individual strategies do not yet have individual performance measurement targets established. The evaluation plans for individual strategies are still under development. The Department of Community and Human Services (DCHS) indicates that once finalized, the specifics of each intervention and the population it is targeting will determine which outcome(s) will be impacted in the short-term and how much additional time will be necessary before other longer-term outcomes will be seen.

Included in Attachment C to the annual report which is attached to Motion 2009-0239 are recommended performance measures and performance measurement targets for the MIDD strategies. Some performance measures were updated to reflect the performance targets specified in the approved implementation plan or updated to be consistent with the funding allocated to strategies.  For example, some performance targets were created based on early budget proposals and needed to be adjusted to be consistent with the funding allocated that strategy.  Subsequent MIDD Annual Reports will include updated performance measure targets for the following year of the programs.

Targets for the broad MIDD policy goals were developed assuming that a set of programs has been operational for one full year and has enrolled enough participants to detect significant changes. The annual report states that strategies must be operational for a minimum of one year before outcome data can begin to be collected and analyzed, and an additional four to six months is needed for data collection and analysis.  As implementation of the MIDD strategies did not begin until October 16, 2008 and 22 out of the 37 strategies began implementation in 2008, there are no recommendations based on measurement and evaluation data for any of the strategies until late in 2010.

2008 Financial Overview

The MIDD sales tax will generate more than $40 million per year for eight years.  By the end of 2008, $36 million of sales tax funding was available.  Of the $36 million, $27 million or 75 percent, was committed to community based mental health and substance abuse service providers, therapeutic courts, other community based human service providers and to new dedicated housing units.  In this case, “committed” means funding expended through reimbursement process, funding commitment via letter of award, memorandum of agreement with one of the many community based agencies, or through internal King County implementation.

The annual report states that “the MIDD fund expended $22 million”.  To clarify, $16.3 of the “expended” amount is dedicated to housing development.  The MIDD fund “expended” the $16.3 by virtue of transferring the funds to the Housing Opportunity Fund to execute the housing development contracts, the housing funds will be expended over time. The same applies to $2 million dedicated to supporting housing services which was also transferred to the HOF.  Therefore, of the $22 million, $3.7 million was expended on programs, services and administration.  Attachment A to the annual report that is attached to proposed Motion 2009-0239 provides information on MIDD expenditures.

The balance of the total funds less amount expended was $13.7 million.  Those funds were designated to reserves for future new strategies, revenue stabilization, and fund balance.

An updated financial status report is included with the staff report as Attachment 5.  The updated report includes a column showing expenditure by MIDD strategy.

Mental Health Court Strategy Recommendation

Ordinance 16261 directed the MIDD Oversight Committee to revise the MIDD Mental Health Court strategy 11b and submit a recommendation to council in the April 1, 2009 MIDD annual report.

The MIDD Oversight Committee formed a workgroup to draft the recommendation to bring before the full MIDD Oversight Committee in February 2009 for action.  Workgroup members included representatives from:  City of Auburn, City of Auburn Municipal Court, King County Office of Budget and Management, Council staff, King County District Court, King County Superior Court, City of Seattle, City of Seattle Municipal Court, King County Prosecuting Attorney’s Office, King County Office of Public Defense, Public Defense, and King County Department of Community and Human Services.  Judge Barbara Linde chaired the workgroup and the Mental Health, Chemical Abuse and Dependency Services Division provided staff support.

The Mental Health Court workgroup met six times to complete and then forwarded its revised mental health court strategy to the MIDD Oversight Committee. The revised strategy that was approved by the MIDD Oversight Committee is outlined below.

Currently, accessing King County District Court Mental Health Court services for misdemeanor offenders is limited to individuals who commit offenses in unincorporated King County. The city of Seattle and the city of Auburn are the only jurisdictions in King County that provide mental health court services through their respective municipal courts.

The MIDD Oversight Committee proposes that the King County District Court expand its current Mental Health Court (MHC) and make it available to any misdemeanor offender in King County who is mentally ill, regardless of where the offense is committed.  In summary:

- A misdemeanor case originating in a municipality in King County that does not have a mental health court would be referred by the respective municipal prosecutor to the King County Prosecuting Attorney for a direct filing of the case into the District Mental Health Court.

- The referral could take place before charges are filed, or later in the proceedings but prior to disposition, whenever it is determined that the individual’s mental illness makes the Mental Health Court the best place for the individual to be served.

- This strategy, along with that of maintaining or increasing the MHC’s capacity to serve the “felony drop down” population, would create regional mental health court without borders.

- The strategy also includes expansion for the City of Seattle Mental Health Court and City of Auburn Mental Health Court.

A copy of the Mental Health Court MIDD Strategy 11b recommendation is included as Attachment D to the annual report which is attached to Motion 2009-0239.

New Strategy Process Recommendation

Ordinance 16261 directed the MIDD Oversight Committee to create a process by which interested parties could propose new strategies to be considered for MIDD funding. The ordinance specified that the process would have the following characteristics:

- Be easily accessible and transparent to the potential proposers of new strategies and programs

- Provide clear and simple directions for the potential proposers of new strategies and programs

- Specify the key elements required in any proposal or request for funding

- Include a schedule and timeline for the proposal process

- Provide at least two dates during the calendar year when new strategies and any necessary supplemental appropriation ordinances would be sent to the council for consideration.  One of those dates shall be April 1, when the MIDD annual report is due

In response to the direction of the ordinance, the MIDD Oversight Committee created a workgroup to develop and recommend a new strategy process. Workgroup members included representatives from:  King County District Court, King County Superior Court, the Committee to End Homelessness, Domestic Violence and Sexual Assault agencies, Harborview Medical Center, Youth and Family Service groups, DCHS and Council staff.  Barbara Miner, Director of Judicial Administration, chaired the workgroup and the Mental Health, Chemical Abuse and Dependency Services Division provided staff support.

The MIDD Oversight Committee recommendation for the New Strategy Process, Recommendation Form and Rating Form are Attachment E to the annual report that is attached to proposed Motion 2009-0239.

New Strategy Recommendations will be considered by the MIDD Oversight Committee at least twice each year. The annual submission due dates are proposed to be October 31 and April 30. These due dates were selected to enable review, recommendation and transmittal of the proposals to the Council for consideration during the 1) annual budget process and 2) along with the annual report due April 1.

Interested parties will be able to obtain forms and instructions for submitting proposals on line. After submitting the materials, the will receive a letter acknowledging receipt of the proposal and outlining the timeframe for review. The materials will be reviewed by a subcommittee of the MIDD Oversight Committee and by DCHS staff. The criteria used to evaluate the proposed new strategies include:

- Whether the proposal meets existing State statute for expenditure of MIDD funds

- Achieves the goals of Ordinance 15949:

  - A reduction of the number of people with mental illness and chemical dependency using costly interventions like jail, emergency rooms and hospitals

  - A reduction of the number of people who cycle through the jail, returning repeatedly as a result of their mental illness or chemical dependency

  - A reduction of the incidence and severity of chemical dependency and mental and emotional disorders in youth and adults

  - Diversion of youth and adults with mental illness and chemical dependency from initial or further justice system involvement

  - Explicit linkage with, and furthering the work of, other council directed efforts including, the Adult and Juvenile Justice Operational Master Plans, the Ten-Year Plan to End Homelessness in King County, the Veterans and Human Services Levy Service Improvement Plan and the Recovery Plan for Mental Health Services

- Enables the implementation of a full continuum of treatment, housing and case management services

- Builds on or integrates with existing services

Once the review of proposed new strategies is complete, the subcommittee will prepare and forward a report to the MIDD Oversight Committee. The report will contain all new strategy proposals and a recommendation, if any, of new strategies to be forwarded to the Executive for potential forwarding by to the Council. The MIDD Oversight Committee will recommend to the Executive which new strategies should be forwarded to the Council. The recommended process also indicates that all new strategy proposals will be included in the reports transmitted through the approval process.

The propose New Strategy Process specifies that the entity proposing a new strategy will not necessarily be selected as the provider of services for the proposal. Once new strategies are recommended by the MIDD Oversight Committee and adopted by the King County Council, established county policies on procurement will be followed.

Historical Control Group Recommendation

Ordinance 16262 directed the MIDD Oversight Committee to review and study the concept of establishing a historical control group for evaluative purposes and make a recommendation on establishing a control group to measure recidivism in the King County jail in the April 1, 2009 annual report.  Representatives from the Department of Adult and Juvenile Detention, DCHS, and Council staff met in order to draft a recommendation to assist the MIDD OC with its analysis.

The annual report states that MIDD Oversight Committee does not recommend creating a historical control or comparison group. It does indicate that the MIDD Evaluation Team will continue to look at each strategy as it is implemented to look for opportunities for concurrent (contemporaneous) “natural” comparison groups and include these results in the evaluation reports.

The annual report does not clarify that the Oversight Committee made this determination based on the following information that was provided at the February 29, 2009 MIDD Oversight Committee meeting

- The MIDD is not a single intervention – it is a very complex set of interventions serving a wide variety of individuals.  As such, creating a single comparison group would be very difficult.

- Historical comparison groups rely on environmental/contextual conditions to remain constant.  State and local laws, rules, and law enforcement and prosecutorial practices have changed so much over the last few years that any historical comparison would be meaningless.  For example, the jail population has radically changed, resulting in much fewer low-end offenders.

- It would be very difficult to determine a group (or groups) of individuals that are truly comparable to those being served by the MIDD.  This was attempted for the evaluation of the King County Criminal Justice Initiative on a much smaller scale and the groups were not comparable enough to draw conclusions about any differences in recidivism.

- Generating a historical comparison group, and conducting the additional work necessary to analyze all the variables involved in comparing outcomes would be very costly for the Department of Adult and Juvenile Detention and DCHS, and it is not apparent that there would be any value added by this extra work and cost.

The MIDD Oversight Committee recommendation for the Historical Control Group is included as Attachment F to the annual report.

Interim Loan Report

The MIDD 2008 annual report notes that members of the MIDD Oversight Committee along with representatives from DCHS, the Prosecuting Attorney’s Office, and Council staff collaborated on the development of an interim loan program report. The interim loan report was not included as an attachment to the MIDD 2008 annual report. The report and a motion to accept the report were transmitted to the Council for review and action on April 1. The interim loan report was referred to the Council’s Budget and Financial Management Committee.

Proposed Amendment to 2009-0239

The amendment to Proposed Motion 2009-0239 is Attachment 3. The proposed amendment to 2009-0239 would do four things:

- Add language providing the legislative history of the Mental Health Court Expansion and New Strategy Process proposals that are attached to the MIDD annual report.

- Clarify that adoption of the motion does not constitute approval of Attachment D, Mental Health Court Expansion proposal and Attachment E, the New Strategy Process, which are attachments to the annual report.

- Specify that the Council will consider approval of the Mental Health Court Expansion and New Strategy Process proposals through subsequent legislative action.

- Corrects the terminology of the motion to reflect the Council’s action on the annual report from “adopt” to “accept”, per Ordinances 16261, 16262, and 15949.

Though the Mental Health Court Expansion and New Strategy Process recommendations were transmitted with the 2008 MIDD annual report, separate legislative action is necessary to effectuate the recommendations.

The adopted MIDD Implementation Plan has a placeholder for the Mental Health Court Strategy 11b and should be updated to reflect a revised strategy when it is adopted. Likewise, while the New Strategy fund was established through the adoption of the MIDD Implementation Plan, the Plan does not provide information on the process for proposing a new strategy.

Proposed Ordinance 2009-0342 introduced on May 19th. It would amend the adopted MIDD Implementation Plan to include the Mental Health Court Expansion and New Strategy Process. The Regional Policy Committee will be briefed on the proposed ordinance under a separate agenda item and staff report.

There is also a title amendment.

Changes to MIDD: State Legislative Changes and Supplantation

Prior to the 2009 State Legislative session, monies collected under the sales and use tax for chemical dependency or mental health treatment services must be used to provide new or expanded chemical dependency, mental health treatment, or expanded therapeutic court programs and services. With very limited exceptions, those funds must not be used to supplant existing funding.

During the 2009 Legislative session, Washington State Legislators approved a change to the state statue that partially eliminated the non supplantation language from the law. The partial elimination of non-supplant language is phased out over 5 year period. The changes are as follows:

Section 3.  Moneys collected under this section shall be used solely for the purpose of providing for the operation or delivery of ((new or expanded)) chemical dependency or mental health treatment programs and services and for the operation or delivery of ((new or expanded)) therapeutic court programs and services. For the purposes of this section, "programs and services" includes, but is not limited to, treatment services, case management, and housing that are a component of a coordinated chemical dependency or mental health treatment program or service.

Section 4.  All moneys collected under this section must be used solely for the purpose of providing new or expanded programs and services as provided in this section, except a portion of moneys collected under this section ((shall not)) may be used to supplant existing funding for these purposes ((, provided that)) in any county as follows: Up to fifty percent may be used to supplant existing funding in calendar year 2010; up to forty percent may be used to supplant existing funding in calendar year 2011; up to thirty percent may be used to supplant existing funding in calendar year 2012; up to twenty percent may be used to supplant existing funding in calendar year 2013; and up to ten percent may be used to supplant existing funding in calendar year 2014.

The effect of the change is that in addition to continuing to fund new and expanded mental health, chemical dependency, and therapeutic court services and programs, MIDD funds may be used to replace (supplant) funds lost to those services and programs. Supplantation is allowed for five years, ending by 2015. Beginning in 2010, up to 50 percent of the MIDD tax collected can be used to supplant other lost funds. There is a ten percent reduction to the amount of funds used each year, ending at 10 percent in year 2014. At the writing of this staff report, the bill was awaiting the Governor’s signature.

It is anticipated that any changes to funding of MIDD strategies would be proposed by the Executive to the Council for consideration during the 2010 budget process that commences in September. Ordinance 16262 specifies that concurrent with the Executive’s annual budget proposal, a report on MIDD program expenditures and revenues, along with an updated financial plan and detailed spending plan are required to be included in the transmitted budget documents. Ordinance 16261 also acknowledges that the strategies contained in any future implementation plans may be expanded, revised or eliminated by ordinance based on, but not limited to, the following reasons: changes to State law or County policy; performance data from the evaluation of sales-tax funded programs and strategies; recommendation from the County Executive or the Oversight Committee; or County budgetary constraints.

In response to anticipated reduced revenues to the MIDD fund, the MIDD Oversight Committee initiated a Prioritization Sub-Committee. The Sub Committee was charged with developing a process for prioritization of MIDD strategies. The purpose of the Committee’s work is to assist the Department, Executive and Council with making potentially difficult decisions around funding MIDD strategies as available funding levels change.

The Prioritization Sub-Committee presented its recommended process and prioritization tool to the MIDD Oversight Committee on April 23rd, where it was reviewed and accepted. The next step is to apply prioritization tool and share the results with the MIDD Oversight Committee at the June 25th meeting. After that, the tool and its results will be forwarded to both the Executive and the Council with a recommendation to consider the prioritization process during the upcoming budget process.

The Regional Policy Committee may wish to consider having a briefing on the MIDD prioritization process once it is communicated to the King County Council.

MIDD Integration with Countywide Human Services Plans

The MIDD policy framework was developed to complement and integrate with King County’s other health and human services policies and planning efforts. One of the five MIDD policy goals expressly states that that the MIDD programs and strategies are to provide:

MIDD Policy Goal 5:  Explicit linkage with, and furthering the work of, other Council directed efforts including, the Adult and Juvenile Justice Operational Master plans, the Plan to End Homelessness, the Veterans and Human Services Levy Service Improvement Plan and the King County Mental Health Recovery Plan. (Ordinance 15949)

Attachment 6 contains a table showing the County’s adopted human service policies and plans that link with the MIDD. The table also includes the primary goals and objectives and the target population or priority areas of the plan or policy.

DCHS is the lead agency for all of the human service policy and planning efforts in King County, with staff from across its divisions working across program areas throughout county agencies sharing information and developing opportunities for additional collaboration. Those collaboration efforts include:

- Participating on sub-regional human services planning efforts

- Coordinating human services planning with the County’s criminal justice agencies through the County’s Criminal Justice Council and the Regional Law, Safety and Justice Committee,  the Juvenile Justice Operational Master Plan, and  the King County Systems   Integration Initiative Committee

- Coordinating with other human services planning efforts including Committee to End Homelessness in King County, Health Care for the Homeless Network Planning Council, Joint Recommendations Committee, King County Children and Family Commission, and many other regional and sub-regional human services organizations

- Managing the work of  ten citizen boards, commissions, committees and oversight groups  including:

- Advisory Council on Aging and Disability Services

- Alcoholism and Substance Abuse Administrative Board

- Board for Developmental Disabilities

- Community Organizing Program Advisory Board

- Mental Health Advisory Board

- Mental Illness and Drug Dependency Oversight Committee

- Regional Human Services Levy Oversight Board

- Veterans Citizen Levy Oversight Board

- Veterans' Program Advisory Board

- Women's Program Advisory Board

In addition, the Council monitors each of the human service plans through quarterly and annual reports as well as through the requesting of special reports via budget proviso. Finally, Council and Executive staff work closely with the human services community and its organizations.

Looking Ahead to 2009

In 2009, a number of strategies that were partially implemented in 2008 will be brought to full service delivery scale and other strategies that were not started in 2008 will be fully implemented by the end of the year. The MIDD Oversight Committee will continue meeting on a monthly basis to review and provide feedback on the implementation and effectiveness of MIDD-funded programs in meeting the goals established in Ordinance 15949.

As the MIDD 2008 annual report notes and the MIDD financial Plan (Attachment G to the annual report that is attached to Motion 2009-0239) shows, MIDD revenues are coming in lower than projected. Lower than anticipated revenue collection and reductions in state and federal funding for housing, mental health and substance treatment services, along with the potential of supplanting lost state and local mental health and substance abuse revenues with MIDD funds indicate significant challenges ahead.

It is likely that the spending plan contained in the Executive’s 2010 proposed budget will show changes to the funding levels of many, if not all, of the MIDD adopted strategies. The Council will review the any changes to MIDD spending as part of its annual budget process that begins in the fall.

Documentation on the historical control group can be found at: www.kingcounty.gov/healthservices/MHSA/MIDDPlan/MIDDCommittees.aspx

Section 2.3-4, Second Substitute Senate Bill 5433, Washington State 61st Legislature, 2009 Session