| NORMAL (non-emergency) Selection Design, Bid, Build 03-02-09 to 06-22-09 | ABBREVIATED Competitive Selection FMD proposed modified GCCM model 03-02-09 to 04-24-09 or less |
| --- | --- |
| 3/2 Appropriation Approved | Emergency Declared by Council |
|  | Construction Contractor | Project Reporting Consultant |
| 3/27 Construction Documents Completed (plans and specs) | 3/16 Letter for pre- qualification to 5 contractors | 3/16 Letter for personal services contract to 5 consultants |
| 4/3 1 week to prepare to advertise (ideally 10 days) | 3/23 5 days to send out request with call ahead for bonding, insurance, qualifications and determine interest | 3/23 Conference held with 5 consultants |
| 5/1 4 weeks to advertise | 3/26 3 days to review and notify with shortened list if possible | 3/31 5 days to respond Criteria: Fees Overhead Billing rates Who works Qualifications |
| 5/4 conduct bid opening 1-day | 4/1 Complete walk-throughs DAJD, A/E and FMD | 4/6 Evaluate and select - 3 days |
| 5/15 10 days to evaluate bids | 4/9 5 days to submit bid number and schedule | 4-23 Notice to Proceed Devel. Manager Estimators Schedulers Testing Procure for contractor Peer reviews Scheduler and coordinator |
| 5/18 1 day to give notice to selections (assumes no protests, no mistakes, no alternates, etc. on bid forms) | 4/15 Evaluate Bids |  |
| 5/29 10 days for contractor to return required documents (bid bond, certificate of insurance, domestic partnership, escrow, contract documents) usually requires 3 weeks | 4/15 Send notice of selection to the successful bidder. |  |
| 6/5 1 week to assemble forms into 4 contracts and mail out to contractor |  |  |
| 6/12 5 days for contractor to review contract and sign it |  |  |
| 6/19 5 days for procurement to distribute contract forms to KC agencies with stake (i.e. Risk Management etc.) |  |  |
| 6/22 Contract of record to FMD, signed, and Notice to proceed |  |  |