ATTACHMENT A

EXHIBIT C

KCDOT Description of NOVELTY HILL ROAD EIS AND CIP Process
and Estimated Schedule

EIS

King County Roads Services Division (RSD) is underway in the completing of a National Environmental Policy Act Environmental Impact Statement (NEPA EIS) for the Novelty Hill Road Project CIP Nos. 100992 and 100901.  The NEPA process has several requirements that RSD must follow.  These include:

- Federal Highways Administration (FHWA) is the lead agency for the EIS and has final approval authority for the EIS.

- FHWA requires that all documents, drafts, studies and reports be submitted to the Washington State Department of Transportation (WSDOT) for review and approval prior to WSDOT submitting the above material to FHWA.  FHWA then will review, comment prior to their approval of the documents submitted.

- Given that this project will likely impact more than ½ acre of wetlands an Individual Army Corps of Engineers (ACOE) permit will be required. The need for an individual ACOE permit coupled with the NEPA process requires that King County enter into the NEPA/404 Signatory Agency Committee (SAC) process as part of the EIS.

- The SAC process requires that King County submit and receive approval of three concurrence points in developing and approving the EIS.  The EIS cannot move forward until agreement on the respective concurrence points has been reached.

- FHWA will sign a Final EIS when a Biological Opinion or a concurrence letter has been signed by the federal regulatory services USFWS and NOAA.

The King County Comprehensive Plan update for 2004 clarifies policy language (T-207 and T-208) regarding potential capacity improvements to urban connectors.  Urban connectors are arterials that provide connections between urban areas while including segments within the rural area.  The Comprehensive Plan policies allow for such connections through the rural area to serve the needs of urban areas provided any capacity increases to these urban connector arterials are designed to serve mobility and safety needs of the urban population while discouraging development in the surrounding Rural Area or Natural Resource lands.  The Comprehensive Plan policies allow for urban connectors to be included as alternatives in the EIS. This allows the consideration of two additional alternatives: the connection of 196th Ave NE between Novelty Hill Road and Union Hill Road and a separate alternative that would improve 208th Ave NE between Novelty Hill Road and Union Hill Road.  The City of Redmond made the request to include these alternatives in the EIS.

The project has completed the first two of the three SAC concurrence points.  This includes:

- Concurrence Point One:  Purpose & Need and Screening Criteria for the Alternatives.

- Concurrence Point Two:  The range of alternatives for the Draft EIS.

The project team is currently working on the Draft EIS. The Build Alternatives in the EIS are:

- Alternative 1 - NE Novelty Hill Road:  NE Novelty Hill Road would be widened to a maximum of five lanes from 243rd Avenue NE to Avondale Road NE.

- Alternative 2 - NE Novelty Hill Road, 196th Avenue NE, and Union Hill Road (referred to from here on as the 196th Avenue NE Alternative):  NE Novelty Hill Road would be widened to a maximum of five lanes from 243rd Avenue NE to 196th Avenue NE and then would taper for approximately 1,000 feet back to two lanes to Avondale Road NE. 196th Avenue NE would be widened from two to three lanes from NE Novelty Hill Road to NE Union Hill Road with approximately 800 feet of a new roadway linking NE Novelty Hill Road and NE 95th Street. NE Union Hill Road would be expanded to five lanes from 196th Avenue NE west to the Redmond City limits.

- Alternative 3 - NE Novelty Hill Road, 208th Avenue NE, and NE Union Hill Road (referred to from here on as the 208th Avenue NE Alternative): NE Novelty Hill Road would be widened to a maximum of five lanes from 243rd Avenue NE to 208th Avenue NE and would continue west as three lanes for approximately 3,000 feet with an appropriate taper to two lanes to Avondale Road NE. The purpose of the continuation of the widening on Novelty Hill Road beyond 208th Avenue NE is to address safety issues in this area of the roadway. 208th Avenue NE would be widened from two to three lanes from NE Novelty Hill Road to NE Union Hill Road, and NE Union Hill Road would be expanded to five lanes with the exception of a four-lane hill segment for approximately 2,000 feet to the Redmond City limits.

The current schedule for the project is as follows:

- Issuance of the Draft EIS March 2007.

- Preferred Alternative Selection June 2007.

- Issuance of the Final EIS June 2008.

- Issuance of the Record of Decision December 2008

- Phase One design, permitting and ROW complete June 2009.

- Phase One construction contract to be awarded and construction anticipated to start by the end of 2009.

CIP

The adopted Roads 2006-2011 Capital Improvement Program (CIP) includes two projects on the Novelty Hill Road corridor.  Project #100901 is Novelty Hill Road-Redmond between Avondale Road and the Redmond city limits.  Project #100992 is Novelty Hill Road between the Redmond city limits and 244th Avenue NE.

Project # 100901 has $1,000,000 programmed in 2009.  The revenues backing this expenditure assumption are developer contributions, either through a fair share or Mitigation Payment System (MPS) fees.

Project #100992 has a total of $32,530,000 programmed in the 2006-2011 six year CIP as follows:

| 2006 | $1,148,000 | Ultimate project EIS |
| --- | --- | --- |
| 2007 | $4,981,000 | Ultimate project EIS and Phase I Design, R/W acquisition |
| 2008 | $7,044,000 | Phase I Design, R/W acquisition |
| 2009 | $19,357,000 | Phase I R/W acquisition, construction |

The County Council, in adopting the 2006-2011 CIP, has continued its support of the sale of bonds in the amount of $20 million as funding for the project.  This $20 million of bond funds combined with a reasonable assumption of $8,430,000 of future state and/or federal grants, $2,635,025 of developer contribution via the Mitigation Payment System (MPS) and a contribution of $1,281,000 from the Road Fund, and $184,000 remaining from an existing federal grant provides the revenue for the project as programmed.

In addition to the funding programmed in the 2006-2011 CIP, the county has already spent or appropriated in prior years a total of $8,795,574 to complete the EIS for the ultimate project and acquire right of way in the vicinity of 208th Avenue NE.