King County

Community Garden Program

Implementation Plan

11/02/2010

Revised March 1, 2011

Prepared by the King County Inter-Departmental Team on Community Gardens:

Frana Milan, DNRP/Parks and Recreation Division

Jeremy Valenta, Office of Strategic Planning and Performance Management

Diana Vinh, Public Health – Seattle & King County/Office of the Director

Richard Gelb, DNRP/Director’s Office

Karen Kinney, DNRP/Water and Land Resources, King County Agriculture Program

Kate Donley, Department of Executive Services/Real Estate Services

Table of Contents

- Executive Summary ......................................................................................................... 1

- Background and Context ……………………………………………………………………………………………. 2

- Recommendations for the Implementation of a Community Garden Program on King County-owned Property ……………………………………………………………………………………….. 4

Attachment A: Motion 13221 ………………………………….……………………………………………….. 10

Attachment B: Inventory of Potential Community Garden Sites on King County-owned Properties ……………………………………………………………….…………..………………………….….. 14

Attachment C: Inter-Departmental Team on Community Gardens – List of Participation King County Agencies ……………………………………………………….…………………………………. 17

Attachment D: Community Garden Program Models in Other Jurisdictions ……….…….. 18

Attachment E: Existing Community Gardens on King County-owned Properties …….…. 20

# I. Executive Summary

The King County Community Garden Program Implementation Plan is in response to Motion 13221, which requested that the King County Executive develop an implementation plan for creating and managing community gardens on King County-owned property.  It is an internal operational plan that explores the context of community gardening and recommends how King County could work with community partners and other jurisdictions to promote the establishment and operation of community gardens.

A “community garden” is typically defined as any land that is gardened by a group of people, allowing individuals to grow food for themselves or their community.  Nationally, community gardening has been recognized for its many benefits, such as promoting healthy eating, providing an outdoor recreational activity, addressing food security, and building vibrant communities.  In our region, community gardening has a long tradition and has shown strong demand in recent years, as evidenced by the growth of formal and informal local groups promoting gardening and food cultivation as well as significant wait lists to participate in two major local gardening programs, Seattle’s P-Patch program and Marymoor Park’s community garden.

The development of this document involved representatives from multiple King County agencies, including DNRP/Parks and Recreation Division; Office of Strategic Planning and Performance Management; Public Health – Seattle & King County/Office of the Director; DNRP/Director’s Office; DNRP/Water and Land Resources, King County Agriculture Program; and Department of Executive Services/Real Estate Services. In the process of developing this implementation plan, this team studied other community garden program models, identified potential garden sites on King County-owned properties, and consulted with community garden stakeholders, including representatives from community gardening groups, food security groups, city jurisdictions, and gardening enthusiasts, among others.

This plan recognizes that King County has very limited resources to advance a community garden program at this time, and as such, recommends a program model that leverages the County’s expertise and other potential non-financial contributions.  The recommended program model relies upon partnerships with community-based organizations and other entities to establish, manage, and sustain the garden sites.  King County’s limited role would involve coordinating use agreements and helping to connect interested parties with potential sites on County-owned properties.

A program at this limited scale could be launched immediately with new gardens in development by the end of 2011.  It should also be noted that a community garden coalition of public and community entities was recently begun in Tacoma-Pierce County, and this effort may provide a program model that could be replicated or adapted in King County in the future.  The Tacoma-Pierce County program will be evaluated at the end of 2012, and this plan recommends that King County and its partners explore the Tacoma-Pierce County findings in 2013 and re-evaluate its approach to community gardening at that time.

# II. Background and Context

Purpose and scope

The King County Community Garden Program Implementation Plan is an internal operational plan that explores the context of community gardening and recommends how King County could work with community partners and other jurisdictions to promote the establishment and operation of community gardens on King County-owned properties.

The plan proposes the potential roles and responsibilities that various King County agencies would assume should such a program be implemented.  This plan recognizes that King County has very limited resources to advance a community garden program, and as such, recommends a program model that leverages the County’s expertise and other potential non-financial contributions. The proposed plan recommends a program limited to low-cost or no-cost ways the County can advance community gardening on County-owned properties.

After evaluating a variety of community garden models, the recommended program model is built on the assumption that community-based groups, non-profit organizations and other public agencies will work in partnership with King County to identify, establish, manage, and sustain community gardens on King County-owned properties. This model supports strategies for service excellence in the King County Strategic Plan by strengthening King County’s collaborative role with cities and communities, and improving collaboration internally, including among the County’s elected leadership, across departments, and with employees.

Although an inventory of potential garden has been prepared, additional research will be necessary once interest is shown for gardening on a particular to confirm a site’s appropriateness for a community garden, including but not limited to testing soil, assessing other growing conditions, and accessing water.

The scope of the current plan also does not address criteria for evaluating the capacity of potential community partners in establishing, managing and sustaining community gardens on County-owned properties.  Should a King County community garden program be implemented, such criteria would be determined by an Inter-Departmental Team on Community Gardens - a group of King County staff members representing various agencies and described in more detail later in this document.

This plan assumes that King County would seek to collect fees from partnering organizations as a means of covering costs associated with administering the program.  Should a King County community garden program be implemented, such fees would be determined collaboratively by the pertinent King County agencies.

Authority

This document is guided by King County Council Motion 13221, which requested that the King County Executive develop an implementation plan for creating and managing community gardens on King County-owned property to grow fruits and vegetables for the purposes of improving public health, building community and addressing hunger.  Motion 13221 is included as Attachment A.

Previously, Ordinance 16263 required the Executive to conduct an inventory of county-owned or managed facilities and properties for the purpose of evaluating their feasibility for use in programs such as community gardens.  A preliminary inventory - developed with the help of a team of UW Urban Planning students - was sent to the King County Council in February 2010. A refined inventory is included as Attachment B.

Why support community gardening?

Community gardens provide people a place to grow produce or other crops on land that may be owned in trust by local governments or not-profit associations.  They may be divided into individual plots or tended in a communal fashion and are managed and maintained with the active participation of the gardeners themselves rather than tended only by a professional staff.

The American Community Gardening Association lists several potential benefits from community gardening:

  - Produces nutritious food

  - Reduces family food budgets

  - Improves the quality of life for people in the garden

  - Creates opportunity for recreation, exercise, therapy, and education

  - Provides a catalyst for neighborhood and community development

  - Stimulates social interaction

  - Encourages self-reliance

  - Beautifies neighborhoods

  - Conserves resources

  - Reduces crime

  - Preserves green space

  - Creates income opportunities and economic development

  - Reduces city heat from streets and parking lots

  - Provides opportunities for intergenerational and cross-cultural connections

Moreover, a literature review conducted as part of this implementation plan process examined relevant literature for scientific and epidemiologic evidence related to community gardens and positive impacts upon the public’s health.  The most prominent findings from the articles showed evidence of increased fruit and vegetable consumption and increased physical activity among community gardeners.  Other articles pointed out benefits such as community cohesiveness and individual feelings of well-being.

Regionally, community gardening has also been identified as an element in food systems and land use planning.  This is reflected in the 2010 King County Board of Health’s Guidelines for Healthy Communities as one of several strategies that encourages access to healthy, affordable foods for county residents.  It is also reflected in the Puget Sound Regional Council’s Vision 2040.

In the current fiscal climate, King County has very limited resources for advancing community gardening.  However, recognizing the many benefits of community gardens, the County can contribute in select ways and in partnership to achieve the intent of Ordinance 16263 and Motion 13221.

How the plan was developed

Multiple King County agencies came together and established an Inter-Departmental Team on Community Gardens to respond to Motion 13221.  A list of participating agencies is included as Attachment C.  This working group met regularly from April – November 2010 and carried out the following activities:

- Carried out a literature review of the nexus of public health benefits of community gardens

- Studied program models for operating community garden programs (see Attachment D)

- Refined list of potential sites on King County-owned properties

- Consulted with community garden stakeholders, including representatives from community gardening groups, food security groups, city jurisdictions, and gardening enthusiasts, among others

- Drafted an implementation plan, including the recommended program model for a King County Community Garden Program

# III. Recommendations for the Implementation of a Community Garden Program on King County-owned Property

After exploring the current situation of community gardening in King County and examining a variety of operational models, the Inter-Departmental Team on Community Gardens recommends that King County take some initial steps that would immediately promote community gardening on County-owned land.  The County should also continue to monitor community gardening efforts in and around King County, as well as remain engaged in the on-going discussions around regional food systems planning.

In the immediate near-term, King County could launch a community garden program in a way that empowers user groups to establish, manage, and sustain garden sites on County-owned land without resulting in significant new publicly-funded capital investments or on-going maintenance responsibilities.  The King County Community Garden Program would follow a strategy that would make County-owned land more available to interested groups who demonstrate capacity to manage all aspects of day-to-day operation of a community garden site and to collaborate with the County.

This model enables well-established gardening organizations as well as informal gardening groups to access sites on King County-owned properties.  In some instances, County-owned sites are located within the jurisdiction of other local governments and partnerships would be sought with the pertinent jurisdiction.

Under such a model, King County would play a limited role that:

- identifies County-owned properties with garden potential;

- facilitates partnerships among non-profit organizations, community groups, King County agencies, and other jurisdictions;

- disseminates information about opportunities for community gardening on King County-owned property; and

- connects prospective community gardening groups with information and other resources.

Roles and responsibilities

Department of Natural Resources and Parks (DNRP)

Currently, there are six public community garden sites on King County-owned properties, plus the Goat Hill Giving Garden used by King County employees.  Four of the six public garden sites are located on properties under the custodianship of the Parks and Recreation Division.  These gardens were established opportunistically, and each operates under a different management model.  Attachment E includes a list of existing garden sites and partner organizations.

Considering the Parks and Recreation Division’s experience with community gardens and expertise in developing public-private partnerships and in executing use agreements, the Parks and Recreation Division is a natural fit to serve as lead agency for a King County Community Garden Program.

Responsibilities include:

  - Coordinating agreements between community gardening partners and King County;

  - Serving as a liaison between other King County agencies and community gardening partners;

  - Facilitating meetings of the Inter-Departmental Team and the Advisory Group;

  - Disseminating information about King County’s program, including but not limited to hosting and maintaining a web page; and

  - Responding to inquiries about King County’s program and connecting interested parties with community gardening partners.

The Parks and Recreation Division would work with potential community gardening partners to establish agreements to address items such as fees, on-going maintenance responsibilities, and any minor capital improvement needs.  Exhibit A to each agreement would be a King County Code required Special Use Permit establishing the terms and conditions for use of the County parcel on which the garden site is located.

The Parks and Recreation Division also operates the “Community Partnerships and Grants Program” (CPG Program). This program provides seed funding that empowers community groups, sports associations, environmental organizations, recreation clubs, and other non-profit entities to construct, develop, program, and maintain new or enhanced public recreational facilities on King County land in a manner that does not result in new publicly funded operations and maintenance costs.  Where appropriate, this program could be a possible source of funding to help organizations establish gardens on King County-owned properties.

Inter-Departmental Team on Community Gardens (IDT)

An inter-departmental team was assembled to draft this report and review and refine an inventory of potential community gardening sites on King County-owned properties.  This team would continue to meet on an ad-hoc basis to provide guidance and expertise should a King County Community Garden Program be implemented.

Responsibilities include:

- Review and approve siting criteria

- Revise and refine list of potential garden sites on King County-owned properties

- Identify and address any requirements or issues related to King County policies and codes that affect King County’s community gardens program

- Provide informational and other resources to support the program

At minimum, the IDT should consist of representatives from the following agencies:

- Parks and Recreation Division, DNRP

- Water and Land Resources Division, DNRP

- Real Estate Services Section, Facilities Management Division

- Road Services Division, DOT

- Office of the Executive

- Public Health - Seattle & King County

- Department of Development and Environmental Services

Community Garden Advisory Group

In accordance with Motion 13221, the IDT convened an advisory group to help draft this plan. The Community Garden Advisory Group is made up of representatives from community-based organizations, food security organizations, other jurisdictions, and gardening enthusiasts, among others.  Coordinated by the IDT, this group will continue to meet on an ad-hoc basis to provide information regarding best practices in operating community garden programs, offer feedback on the County’s program, and help disseminate information to the broader community about opportunities to garden on King County-owned properties.

Costs

An objective of the proposed model for a King County Community Garden program is to minimize the financial investment required by the County to offer such a program, while still enabling the County to promote community gardening on County-owned properties.

This plan proposes improved collaboration between county agencies for coordinating community gardens, including the establishment of a single point of contact in the County’s Parks and Recreation Division.  This would entail the modification of a current work program, not the addition of a new position.  To operate the program, it is estimated that 0.15 of staff time in existing position would be required for the Parks and Recreation Division’s program lead.

In addition, as interested groups pursue new sites to establish gardens, the program will periodically require collaboration with staff from other County agencies, such as risk management, real estate services, PAO, and parks and recreation.  Staff time will also be required by IDT participants in ad hoc meetings, estimated at three per year.

In order to help recover the costs of operating such a program and address any potential state accountancy act issues, the IDT recommends the next phase of program development consider the collection of usage fees as part of any agreement established with the respective partner organizations.  Based upon this analysis, fees could encompass use of the garden site and take into consideration factors such as the size of the garden site, program administration, and other enterprise fund constraints.

Each partnering organization would determine its own rental policies for the individual garden plots and would be allowed to retain plot rent.

Launching the Program: Actions and Milestones

In 2011, King County would take the following actions to implement the King County Community Garden Program:

Action 1: Based upon the inventory of County-owned sites listed in Attachment C, work with local governments to incorporate the potential community garden sites owned by the County and located in their boundaries into their community gardening programs.

Milestone:

- Community gardening agreement with the City of Seattle regarding incorporating two King County-owned sites located within city boundaries into the city’s existing community gardening program (May 2011)

Action 2: With the guidance of the Inter-Departmental Team on Community Gardens and the Community Garden Advisory Group, refine criteria for evaluating and approving a potential site’s appropriateness for hosting a community garden and refine criteria for evaluating and approving community gardening proposals from potential partners.

Milestones:

  - Community garden site evaluation criteria/checklist (May 2011)

  - Community garden proposal evaluation criteria (July 2011)

Action 3: Conduct analysis of cost recovery options that takes into consideration such factors as the size of garden sites, program administration, and other issues as identified by the PAO or custodial agencies.  This document will provide the structure informing the fee section of the agreements established with each partner entity.

Milestone:

- Cost recovery analysis completed (July 2011)

Action 4: Develop and publish a webpage dedicated to the King County Community Garden Program that includes information such as a list and map of potential county-owned sites, information on how to start partnering with King County, links to non-profit organizations with community gardening programs, funding resources for community gardening activities, and other community gardening resources.  Promote the King County Community Garden Program utilizing no-cost channels such as press releases, social media, and communications with partners.

Milestone:

- Webpage published (May 2011)

- Communications materials prepared (July 2011)

Performance Measures

The initial performance measures used to evaluate the King County Community Garden Program in the program’s first two years include:

- Number of agreements executed with partners for community garden sites on King County-owned properties

- Number of active, occupied plots located on community garden sites on King County-owned properties

- Cost analysis

Program Evolution: Evaluating the Implementation of the Tacoma & Pierce County Community Gardens Plan

“Action Communities for Health, Innovation, & Environmental Change” (ACHIEVE) introduced a three-year Community Gardens Plan for Tacoma and Pierce County in June 2010.  Through a collective effort, Pierce County organizations identified funds and offered in-kind services to hire and maintain a full-time staff person to coordinate and implement the plan.  The position, hosted by Cascade Land Conservancy, will implement the goals and objectives of the plan and the ACHIEVE community gardens coalition.

The Community Gardens Plan for Tacoma and Pierce County includes a monitoring element and each of the plan’s goals and objectives will be measured at the end of 2012.  This will be completed by the Tacoma-Pierce County Health Department in conjunction with the Community Garden Coordinator and related partners.

In 2013, the Inter-Departmental Team on Community Gardens would work with Community Garden Advisory Group to review the Tacoma and Pierce County program’s findings and evaluate whether or not that model is appropriate for King County.  The Community Garden Advisory Group would be asked to recommend a course of action for the future of King County’s community garden program at that time and to define what their roles and contributions could be.

Attachments

- Attachment A:		Motion 13221

- Attachment B:	Inventory of potential garden sites on King County-owned properties

- Attachment C:	Inter-Departmental Team on Community Gardens: List of Participating Agencies

- Attachment D:	Community Garden Program Models in Other Jurisdictions

- Attachment E:	Existing community gardens on King County-owned properties

# Attachment A: Motion 13221

# Attachment B: Inventory of potential community garden sites on King County-owned properties

| Custodian | Description | Address (approx.) | City/Unincorp. KC | Zip Code | Council District | Parcel Number | Potential Garden Area (s.f.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Property Services Division | BALCHS SIERRA HEIGHTS | 126th Ave SE and SE 100th St | Unincorporated King County | 98056 | 6 | 0428000290 | 56,000 |
| Property Services Division | FAIRLANE WOODS TR A | 131st Pl SE and SE 159th St | Unincorporated King County | 98058 | 6 | 2460701090 | 37,500 |
| Property Services Division | TOTEM ESTATES TR B | 121st Ave NE and NE 160th St | Unincorporated King County | 98011 | 3 | 8663200870 | 24,840 |
| Property Services Division | FOREST GLEN SO TR B | 137th Ave SE and SE 200th St | Unincorporated King County | 98042 | 9 | 2592300530 | 4,000 |
| Property Services Division | LAKE WEST TR A | 191st Ave SE and SE 42nd Pl | Issaquah | 98027 | 3 | 4123400430 | 24,000 |
| Property Services Division | NORTHPEAK CREST TR A | 137th Ave SE and SE 237th St | Kent | 98042 | 9 | 6187100710 | 30,000 |
| Property Services Division | FIRWOOD GLEN - TR A | 126th Ave NE and NE 114th Pl | Kirkland | 98033 | 6 | 2564900550 | 45,000 |
| Property Services Division | MOUNT VISTA TR A | 3rd Ave SW and Mt. Vista Pl SW | Pacific | 98047 | 7 | 5702330130 | 2,500 |
| Property Services Division | DUWAMISH - RIVER PARK | 10th Ave S and S Elmgrove St | Seattle | 98108 | 5 | 7327901195 | 2,000 |
| Wastewater Treatment Division | RENTON EFFLUENT TRANSFER | 7th Ave S and S Sullivan St | Seattle | 98108 | 5 | 7883600720 | 8,500 |

| Custodian | Description | Address (approx.) | City/Unincorp. KC | Zip Code | Council District | Parcel Number | Potential Garden Area (s.f.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Wastewater Treatment Division | ALKI TRANSFER/CSO CONTROL | Harbor Ave S and SW Harbor Ln | Seattle | 98126 | 8 | 6911200255 | 5,000 |
| Wastewater Treatment Division | ALKI TREATMENT PLANT | Benton Pl SW and Beach Dr SW | Seattle | 98116 | 8 | 0148000272 | 6,400 |
| Parks & Recreation Division | TOLT-MACDONALD PARK | 31020 NE 40th St | Unincorporated King County | 98014 | 3 | 1625079016 | 38,651 |
| Parks & Recreation Division | WINDSOR VISTA PARK | 111th Ave NE and NE 141st St | Unincorporated King County | 98034 | 3 | 9477200640 | 6,473 |
| Parks & Recreation Division | WINDSOR VISTA PARK | 110th Ave NE and NE 141st St | Unincorporated King County | 98034 | 3 | 9477101350 | 3,000 |
| Parks & Recreation Division | SKYWAY PARK | 7121 S 120th Pl | Unincorporated King County | 98178 | 5 | 7812801985 | 10,959 |
| Parks & Recreation Division | SKYWAY PARK | 7121 S 120th Pl | Unincorporated King County | 98178 | 5 | 7812801960 | 41,485 |
| Parks & Recreation Division | LAKE GENEVA PARK | Military Rd S and S 344th St | Unincorporated King County | 98001 | 7 | 5066400521 | 32,212 |
| Parks & Recreation Division | NORTH GREEN RIVER PARK | 94th Pl S and Green River Rd | Unincorporated King County | 98030 | 7 | 3022059015 | 112,720 |
| Parks & Recreation Division | LAKEWOOD PARK | 10th Ave SW and SW 108th St | Unincorporated King County | 98146 | 8 | 0623049237 | 17,966 |
| Parks & Recreation Division | NORTH SHOREWOOD PARK | 24th Ave SW and SW 102nd St | Unincorporated King County | 98146 | 8 | 0123039004 | 8,607 |
| Parks & Recreation Division | BOULEVARD LANE PARK | 1250 SE 188th Pl | Unincorporated King County | 98058 | 9 | 3323059057 | 10,700 |
| Custodian | Description | Address (approx.) | City/Unincorp. KC | Zip Code | Council District | Parcel Number | Potential Garden Area (s.f.) |
| Parks & Recreation Division | PETROVITSKY PARK | Parkside Way SE and SE Petrovitsky Rd | Unincorporated King County | 98058 | 9 | 3623059007 | 26,588 |
| Parks & Recreation Division | SOOS CREEK/GARY GRANT PARK | SE 204th Way and SE 208th St | Unincorporated King County | 98042 | 9 | 0322059266 | 8,469 |

# Attachment C: Inter-Departmental Team on Community Gardens – List of Participating King County Agencies

- Executive Office/Office of Strategic Planning and Performance Management

- Department of Natural Resources and Parks (DNRP)/Parks and Recreation Division

- DNRP/Director’s Office

- DNRP/Water and Land Resources Division

- Department of Executive Services/Facilities Management Division/Real Estate Services

- Public Health – Seattle & King County/Director’s Office

# Attachment D: Community Garden Program Models in Other Jurisdictions

Managed by County:

Fairfax County, Virginia

http://www.fairfaxcounty.gov/parks/gsgp/plots.htm

Description:  The Fairfax County Park Authority (FCPA) provides Fairfax County residents the opportunity to participate in a positive community gardening experience through the Community Garden Plot program. More than 650 garden plots in nine County parks are rented on an annual basis. Most plots are 30’x20’; 18 plots at Grist Mill Park are 10’x20’. Beginning April 1, large plots will rent for $65 and smaller plots will rent for $60.

Funding: Through plot rentals they are able to hire seasonal staff to work part time

Managed by Extension Service:

Brown County, Wisconsin

http://www.co.brown.wi.us/departments/?department=68d3c3d55278&subdepartment=b2b33ee26bfc

Description:  For a number of years, Brown County UW-Extension has supported the development of urban community gardens throughout the Green Bay area. The gardens are managed cooperatively by Brown County UW-Extension, the Brown County Food & Hunger Network, the City of Green Bay, and local volunteers. Financial support comes from the UW System, the United States Department of Agriculture, and local private donors.

Funding:  Public and private

Managed by a municipal community garden program:

Seattle, WA

http://www.seattle.gov/neighborhoods/ppatch/

http://www.ppatchtrust.org

Description:  The P-Patch Community Garden Program, the not-for-profit P-Patch Trust works in conjunction with Seattle P-Patch to acquire, build, preserve and protect the gardens. The P-Patch Trust provides advocacy, outreach and educational programs to P-Patch gardeners.

Funding:  City of Seattle general funds, fundraising and grants through the P-Patch Trust, gardener plot rental fees

Managed by a municipally funded not-for-profit organization to support community gardens:

Chicago, IL

http://neighbor-space.org

Description:  NeighborSpace is a nonprofit organization funded through and operating in the city of Chicago, the Chicago Parks District, and the Cook County Forest Preserve District, which is empowered to acquire property to preserve land for community gardens. NeighborSpace acts as a land-trust for community gardens and accepts liability for the site. Since 1996, NeighborSpace has acquired more than 50 sites throughout Chicago for preservation as community garden space.

Funding:  the City of Chicago, Chicago Park District, Forest Preserve District of Cook County and fundraising by community based organizations.

Tacoma & Pierce County, WA

http://www.healthypierce.org/projects-programs/achieve-community-gardens-committee/

http://www.cascadeland.org

Description:  Pierce County’s ACHIEVE Coalition, a broadly based community initiative sponsored by the YMCA and the Tacoma-Pierce County Health Department, spearheaded the community gardens effort, making it what it is today –  a program that provides gardening opportunities for the physical and social 	benefit of people and their neighborhoods.

Funding:  A coalition of public and private partnerships and a Center for Disease Control ACHIEVE grant

# Attachment E: Existing Community Gardens on King County-owned Properties

| Garden Site | Custodian | Managing Entity | Notes |
| --- | --- | --- | --- |
| Marymoor Park | Parks and Recreation Division, DNRP | Marymoor Community Gardeners Association | 154 garden plots (60,000 sf); established in the 1970s. |
| White Center Heights Park | Parks and Recreation Division, DNRP | White Center Food Bank | 6 raised beds; established in 2007. |
| North Green River Park | Parks and Recreation Division, DNRP | Parks and Recreation Division | 133 garden plots, (53,200 sf); established in the 1980s. Parks took over management of the gardens in 2008, when the partner entity disbanded. |
| Mirrormont Park | Parks and Recreation Division, DNRP | Mirrormont Community Association | 8 raised beds, 14 garden plots (6,825 sf); established in 2009 as part of a CPG project. |
| University District P-Patch (Seattle) | Wastewater Treatment Division , DNRP | City of Seattle Department of Neighborhoods P-Patch Program | 48 garden plots (14,400 sf); established in 1976. |
| Greg’s Garden P-Patch (Seattle) | Metro Transit Division. DOT | City of Seattle Department of Neighborhoods P-Patch Program | 20 garden plots (2,500 sf); established in 1999. |

*Notes:

- Since the Goat Hill Giving Garden is restricted to King County employees, it is not included in the inventory of existing community gardens.

- There is a demonstration garden (raised beds) in Skyway Park.  The garden is part of a temporary project, so it is not included in the inventory of existing community gardens.