| Agenda Item No.: | 8 | Date: | December 1, 2015 |
| --- | --- | --- | --- |
| Proposed No.: | 2015-0501 | Prepared by: | Scarlett Aldebot-Green |

SUBJECT

A MOTION accepting the Department of Community and Human Services (DCHS) Behavioral Health Integration IT Data Consolidation project status report.

SUMMARY

Ordinance 18810, Section 60, Proviso P10, passed by the council on September 2015, required the executive to develop and submit for council review and approval two reports on the status of the Behavioral Health Integration IT Data Consolidation project. Specifically, the proviso required the report to include an enumeration of expenditures to date; the status of state of Washington dependencies and their impact on the IT project including the status of the state database and the status on guidelines around federal confidentiality rules; and the status and timeline of provider readiness.  The proviso encumbered $400,000 appropriated to DCHS for the behavioral health integration IT project, $200,000 of which shall be released for expenditure upon transmittal of each report.  The first of these reports, due Nov. 16, 2015, was transmitted to council before the deadline.  It meets the proviso requirements.

Background

In 2014, the Washington State Legislature passed Senate Bill 6312, which directed the state Department of Social and Health Services (DSHS) to restructure how it purchases chemical dependency and mental health services.  Presently, the process for purchasing mental health services and chemical dependency services are separate and different.  Per Senate Bill 6312, the state will be purchasing both of these services through regionally operated Behavioral Health Organizations (BHOs) via a managed care structure, or integrated purchasing, by April 1, 2016.

Pending state approval, the Mental Health, Chemical Abuse, and Dependency Services Division (MHCADSD) will serve as the Behavioral Health Organization for the King County Region.  To do so, MHCADSD must upgrade its system for managing mental health services (MH) to allow for client recordkeeping, authorization of benefits, billing and payment for Substance Use Disorder (SUD) providers contracting with the county under integrated care.  Additionally, the proposed project aimed to modify the system to facilitate its interfacing with new and modified databases.

The project proposed a range of changes to the mental health data system in order to adequately expand that system to serve the needs of the integrated BHO IT system.  Council approved a $982,633 appropriation request from DCHS to complete the project in September 2015.

Council provisoed $400,000 of this appropriation contingent on the transmittal of two reports on expenditure status, state dependencies that could potentially impact the project, and provider readiness.  Upon transmittal of each report, the first of which was due November 16, 2015, $200,000 of the encumbered funds shall be released for expenditure.  Proposed Motion 2015-0501 would accept the first of these reports.

ANALYSIS

The proviso required the status reports to include an enumeration of the expenditures on the project to date; the status of state dependencies and their impact on the project; and the status and timeline of provider readiness.  Below is an analysis of each of these requirements:

Expenditures to Date.  From June through October, $108,326.26 of the appropriated funds had been spent.  These moneys funded a Functional Analyst, a Project Manager and were used to purchase hardware/software.

Status of State Dependencies.  The proviso required a report on two state dependencies:  the status of the state database with which the county database must interface and state guidance to the county on federal confidentiality rules around patient information sharing.  DCHS reports that on September 1, 2015, the Washington State Division of Behavioral Health and Recovery released a draft of the data elements that would be required under the BHO contract.  There is no information on when the state will release final data elements.  King County also received a draft of the ProviderOne State Encounter Reporting Instruction (SERI) on October 16, 2015 and the state's timeline indicates that final SERI will be received by BHOs on February 1, 2016.  The county, therefore, does not yet have final information from the state to fully develop its database. DCHS notes that it has taken an iterative approach to development, prioritizing data transactions that will ensure the ability to authorize benefits and pay providers on April 1, 2016.

According to the report, the state has also not provided further guidance on the issue of confidentiality vis a vis sharing client data between substance use providers and mental health providers in light of more stringent Federal guidelines with respect to substance use provider data.  DCHS indicates that it has reviewed Federal law governing the confidentiality issues involved and, pending consultation with PAO, has concluded that it can receive substance use data and mental health data and store it in a single database but that the division is limited in what information it can share with the provider network without a Release of Information (ROI) from the client.

DCHS notes that there are also specialized Business Associate Agreements that need to be signed by providers.  Once PAO has weighed in on these two items, MHCADSD will work with providers to collect ROIs for clients currently receiving substance use services and for all new clients going forward.  A field will be added to the database to flag client files that do not have this document such that it will prevent sharing of client data across the provider network and its display on application screens, queries, and reports.

Status and timeline of provider readiness.  DCHS reports that the risk of Substance Use Disorder providers not being ready to successfully integrate in time to the database has increased since the council appropriated project funds due to significant delays in the delivery of State requirements.  To ameliorate that risk, DCHS has done the following: 1) begun gathering information through a provider survey to determine status and readiness to transmit authorizations for benefits by April 1, 2016; 2) expanded the Information System Advisory Committee (ISAC) -- technical staff from King County contracted behavioral health providers -- who meet and tackle technical implementation of system modifications needed in response to King County and State policy changes; 3) designated a team member to be a provider liaison to help with technical questions, system testing, etc.; and 4) analyzed the viability of providing a manual data entry solution while providers on-boarded.  On the latter, it was determined that a manual alternative was temporarily possible and the development of a manual solution has begun.

The information furnished in the report is complies with the proviso requirement.

INVITED

- Susan McLaughlin, Health and Human Services Integration Manager, DCHS

ATTACHMENTS

- Proposed Motion 2015-0501

  - Behavioral Health Integration IT Data Consolidation Project, Status Report 1

- Transmittal Letter, November 13, 2015

See Ordinance 18171 renaming the division the Behavioral Health and Recovery Division (BHRD) passed by the King County Council on Nov. 23, 2015.