## STAFF REPORT

| Agenda Item: | 10 | Name: | Hiedi Popochock |
| --- | --- | --- | --- |
| Proposed No.: | 2016-B0194 | Date: | November 29, 2016 |

SUBJECT

A briefing on the status of the Puget Sound Emergency Radio Network (PSERN) implementation.

SUMMARY:

The PSERN Project will replace and upgrade the County's current emergency radio network.  King County is responsible for leading and implementing the PSERN project through completion, which is expected in late 2020.

The PSERN Project is a complex project with multiple tasks over the course of the implementation period including radio site design, acquisition and construction, as well as the acquisition of radios, consoles, and data systems.

Council staff provided the Regional Policy Committee with its fourth quarter briefing of the PSERN Project on October 12, 2016.

Today’s briefing provides the Law and Justice Committee with a fourth quarter update on the status of the implementation of PSERN. There are no substantive changes to the PSERN Project milestone schedule since the last Law and Justice Committee quarterly briefing that occurred on September 13, 2016.

BACKGROUND:

On April 28, 2015, King County voters approved a nine-year, $273 million property tax levy to fund PSERN, the replacement of the King County emergency radio communications system.

In late 2018, the vendor for the current countywide emergency radio network, King County Emergency Radio Communications System (KCERCS), will no longer provide system support.  PSERN will replace and upgrade King County's nearly 20-year old emergency radio communications system, which is used to dispatch responders to incidents and allow responders to communicate with each other at those incidents. Countywide, the current system consists of 26 transmitter sites and multiple interconnecting microwave and fiber systems, and it supports over 100 agencies and approximately 17,000 radio users, each with a portable radio handset and/or installed mobile radio in a vehicle.  The current system is owned by King County, the city of Seattle, Valley Communications Center (ValleyCom), and the Eastside Public Safety Communications Agency (EPSCA).

Once completed, PSERN will replace the current countywide emergency radio network.  PSERN will improve and upgrade the countywide emergency radio network by providing increased system reliability, increasing coverage capacity from 94 percent coverage to 97 percent coverage, providing better security on the network, and nearly doubling the number of radio transmitter sites.

Implementation Interlocal Agreement.  Under the terms of the PSERN Implementation Interlocal Agreement, King County will be responsible for leading and implementing the PSERN project on behalf of the four owners of the current emergency radio network through completion of the project.  Oversight during that implementation period, which is expected to take approximately five years, will be conducted by a Joint Board, composed of one non-voting chair (the Executive or the Executive's designee) and four voting representatives, one representing each of the current system's owners.  The four voting members of the Joint Board may appoint two additional non-voting participants: a chief of a police agency and a chief of a fire agency.

The PSERN project management team includes a project director and information technology and construction managers, a communications manager, a government relations official, technical support technicians and inspectors.  King County Information Technology's Business & Finance Section and the Office of Performance, Strategy and Budget will provide financial support.  Under the terms of the $112 million, 20-year contract between Motorola and the County, Motorola will provide design, development, implementation, testing and ongoing support, maintenance and upgrade services for the PSERN project.  In addition to the primary contract with Motorola, the Executive has hired a consultant to develop the site design and intends to retain a firm to provide construction management oversight.

Operations Memorandum of Agreement.  Under the terms of the Memorandum of Agreement Regarding Future Operation of the Puget Sound Emergency Radio Network, ownership and operation and maintenance of PSERN after completion would be vested in a new, nonprofit organization governed by a Board of Directors.

Council Committee Oversight.   Motion 14437, enacted in October 2015, requires the Executive to brief the Law, Justice and Emergency Management Committee (or its successor) on a quarterly basis on the status of the PSERN project in relation to the project’s identified milestones. The Regional Policy Committee has also requested quarterly briefings on the project implementation. Council staff provided the Regional Policy Committee with its fourth quarter briefing of the PSERN Project implementation on October 12, 2016.

Table 1 below shows the 13 major project milestones identified in the report transmitted by the Executive in September 2015 (2015-RPT0134) that remain to be completed during the PSERN implementation process, along with the original expected date of completion and the two revised expected dates of completion. The “site construction mid-point” and the “group 2 site leasing” milestones have been eliminated since the Executive’s initial transmittal of the 2015 report. PSERN Project staff indicate that the two milestones are no longer applicable to the PSERN project.

Table 1: Future PSERN Implementation Milestones including the Original Expected Completion Dates and the Revised Expected Completion Dates

| Milestone | Original Completion Date | Revised Completion Date (as of 8/8/16) | Revised Completion Date (as of 11/15/16) |
| --- | --- | --- | --- |
| Site Leasing and Final Site Design | March 2016 | April 2017* | May 2017* |
| Construction Permitting | August 2016 | No change | No change |
| Site Construction Mid-Point | September 2016 | Milestone eliminated | Milestone eliminated |
| Group 2 Site Leasing | August 2017 | Milestone eliminated | Milestone eliminated |
| Factory Acceptance Testing | September 2017 | August 2017 | No change |
| Site Construction Complete (all sites) | October 2017 | No change | No change |
| Backhaul System Implementation | November 2017 | November 2018* | No change |
| Land Mobile Radio System Implementation | September 2018 | November 2018* | No change |
| System Optimization and Testing | May 2019 | No change | No change |
| PSERN Non-profit Operator Formation | September 2019 | No change | No change |
| Transition Users to PSERN System | March 2020 | No change | No change |
| Full System Acceptance | September 2020 | No change | No change |
| Project Closeout | September 2021 | No change | No change |

*Expected completion date for Primary Bounded Area sites and SR410 site only

Revised Expected Completion Dates

As noted in Table 1, the expected date of completion for one milestone has changed since PSERN’s third quarter Law and Justice Committee briefing on September 13, 2016.

Site Leasing and Final Site Design.   According to PSERN Project staff, the “site leasing and final site design” milestone is expected to be completed in May 2017 for the Primary Bounded Area and SR410 radio tower sites. This milestone is expected to be completed one month later than the completion date reported previously by PSERN Project staff.

King County Auditor Capital Projects Oversight.  On November 10, 2015, the Capital Projects Oversight Program of the King County’s Auditor’s Office released a report on PSERN. The report focused on project schedule and cost risks.  The Auditor’s Office presented the report to the Government Accountability and Oversight Committee on November 10, 2015.

The report included five recommendations for the PSERN project:

Recommendation 1.  The PSERN project team should revise the project schedule and communicate it to stakeholders before the end of 2015 to include reasonable time to accomplish the remaining tasks necessary to finish tower site construction. The schedule should be based on progress to date and identify the impact on the remainder of the project schedule.

Recommendation 2.  The PSERN project team should improve reporting to clearly demonstrate to stakeholders the progress on leasing and constructing radio tower sites. Reporting should show how current cost and schedule forecasts compare to the assumptions used in the preliminary project estimate.

Recommendation 3.  The PSERN project team should establish and document a project baseline prior to signing any construction contract. The baseline should use the certainties from the Motorola contract, best available information for tower site costs and schedule, and refined estimates of other costs.

Recommendation 4.  The Finance and Business Operations Division (FBOD) should provide ongoing technical assistance to the PSERN project team to help manage the cost risks of any construction work order contracts for this project.

Recommendation 5.  Before seeking bids on a work order construction contract for the radio tower sites, the PSERN project team and FBOD should evaluate the relative benefits, costs, and risks specific to each site of inclusion in a work order contract or a traditional design-bid-build contract. This evaluation should be documented and result in a recommended approach for each individual site for consideration and approval by the project sponsor.

The PSERN Project staff indicate that the PSERN project generally agreed with these recommendations.

The Capital Projects Oversight Program staff indicate that they expect to release the next report on the PSERN project in late 2016 or early 2017.

INVITED:

- David Mendel, PSERN Project Director, King County Information Technology

ATTACHMENTS:

- PowerPoint Presentation “Puget Sound Emergency Radio Network (PSERN), Law and Justice Committee, November 29, 2016”

According to PSERN Project staff, King County owns just under 50 percent of KCERCS, the city of Seattle and Eastside Public Safety Communications Agency owns approximately 25 percent each and ValleyComm owns approximately 10 percent.

Ordinance 18075.

The existing system is owned in equal shares by King County, the City of Seattle, Valley Communications Center (ValleyCom), and the Eastside Public Safety Communications Agency (EPSCA).

As of May 2, 2016, the members of the Joint Board are as follows:  Fred Jarrett, non-voting Chair; Bill Kehoe, King County voting member; Patti DeFazio, Seattle voting member; Kurt Triplett, EPSCA voting member; Lora Ueland, ValleyCom voting member; Chris Elwell, non-voting fire agency member; and John Vinson, non-voting police agency member.

Ordinance 18074.

In 2016, the Law, Justice and Emergency Management Committee was changed to the Law and Justice Committee.

2015-B0210: A briefing on the Capital Projects Oversight Report regarding PSERN.