Metropolitan King County Council

Budget & Fiscal Management Committee

| Agenda Item No.: |  |  | Date: | August 24, 2005 |
| --- | --- | --- | --- | --- |
| Proposed No.: | 2005-0057 |  | Prepared By: | David Layton and Peggy Dorothy |

REVISED STAFF REPORT

Proposed Substitute Motion 2005-0057 was reported out of committee with a do-pass recommendation on August 24, 2005.

SUBJECT:	A MOTION approving a monthly report format and baseline budget for the $1.48 billion Brightwater project.

SUMMARY:

The subject of this agenda item is a motion that would approve the format for required reporting from the Wastewater Treatment Division on the Brightwater Treatment and Conveyance project.  The motion would also approve the baseline budget of $1.48 billion for the lifetime of the project (in 2004 dollars).  In addition, the committee will hear a Project Overview Report from R.W. Beck, the independent Oversight Consultant (OMC) on the project.  The report will include a review by the OMC of the proposed baseline budget.

BACKGROUND:

In 1999, the council adopted the Regional Wastewater Services Plan (RWSP).  The RWSP identified capital improvements needed for the regional wastewater system to handle projected growth in the area through 2030.  One element of the RWSP was the construction of a third wastewater treatment plant (Brightwater) to serve customers in the north King County and south Snohomish County service area.

To date, the Final Environmental Impact Statement has been released and the Executive has selected the site for the treatment plant, conveyance route and marine outfall.  Design for the project is underway and actual construction of the facilities is anticipated to begin in the first quarter of 2007.

During October 2004 the Council reviewed existing Brightwater cost estimates and estimating formats and reporting requirements.  Wastewater Treatment Division staff expressed concerns with overlapping and duplicate reporting requirements.  As a consequence, a 2005 budget proviso was initiated to coordinate and simplify reporting requirements and to establish a baseline budget for the Brightwater Project.  In addition, the 2005 budget contained a proviso requiring the Wastewater Treatment Division to hire a consultant to act as an independent Oversight Monitoring Consultant (OMC).

The response to the first proviso was transmitted on February 3, 2005 with Proposed Motion 2005-0057.  On February 23, 2005, the Budget and Fiscal Management Committee reviewed and discussed Proposed Motion 2005-0057.  Since the OMC had not yet been hired, the Committee deferred action on the motion so that the baseline budget could be reviewed by the OMC.

RW Beck, Inc. (“Beck”) was hired as OMC for the Brightwater project on March 14, 2005.  As part of their initial work program, Beck reviewed the proposed Brightwater baseline budget and provided their opinion in the Brightwater Program Overview Report dated June 2005 (Attachment #5).  Beck will be presenting their overview at the Committee meeting on August 24th.

SCOPE:  This project consists of the siting, planning, permitting and construction of a wastewater treatment plant and associated conveyance facilities in southern Snohomish County. The Brightwater system consists of three elements:

- Treatment Plant:  The treatment plant will be designed to provide treatment and disinfection to about 36 million gallons of wastewater a day.  The plant will be located on about 114 acres in unincorporated Snohomish County east of SR-9, just north of the intersection of SR-9 and SR-522 and the city of Woodinville, approximately 12.5 miles east of Puget Sound.  Treatment and support facilities will cover approximately 43.0 acres (with additional area for stormwater management).  The treatment plant will be built under the General Contractor/Construction Management (GC/CM) contract delivery methodology.  Hoffman Construction Company has been selected as the GC/CM for this project and is currently under contract providing predesign services.

- Conveyance Facilities:  These facilities are the pipelines and pumps that carry wastewater to and from the treatment plant.  The Brightwater system includes a pipeline to carry untreated wastewater into the Brightwater plant, and a pipeline to carry treated waste water from the plant to the outfall.  The system will also include conveyance facilities, such as pump stations, both above and below the ground.  The conveyance system will be built under a traditional Design/Bid/Build contract delivery methodology.

  - Marine Outfall:  The marine outfall will discharge treated wastewater form the plant into the Puget Sound.  An outfall consists of a long solid pipe that begins at the shoreline and extends deep into the water and a perforated section at the end of the pipe called a diffuser through which treated wastewater is released.  For the Brightwater system, the outfall will originate from a conveyance portal located at Point Wells and extend offshore for a distance of approximately 5,200 feet.  The contract delivery methodology for this portion of the project will be a Design/Build contract, and the contractor has not yet been selected for this work.

SCHEDULE:  The project is scheduled to be completed in 2010, though the division is looking at the potential for extending construction to 2012.

BUDGET:  The Brightwater Project currently does not have an approved project budget.  However, cost estimates have been provided on a regular basis since November 2003.  On June 17, 2004 the Council adopted Ordinance 14942 (adopting the 2005 sewer rate and capacity charge) which required quarterly Brightwater cost reports beginning with the first report due in August 2004.  The first report was transmitted on August 23, 2004.  A subsequent addendum transmitted on October 27, 2004 included the predesign cost estimate information.  The pre-design estimate is based on pre-design documents and incorporates the results of a formal Value Engineering (VE) process conducted between January and March of 2004.  The Council was briefed on the status of the Brightwater project in October 2004.

ANALYSIS

Brightwater Baseline Budget Review:

The legislation before the Committee would approve a baseline lifetime budget for the Brightwater project of $1.48 billion in 2004 dollars.  The baseline budget also estimates the total lifetime cost of the project assuming inflation at a rate of 3% and 5%.  The resulting costs estimates are in the following table:

Table 1

Brightwater Project Cost Trends

| Final EIS Estimate 11/03 | Predesign Estimate* 10/04 | Difference | Inflation & Market Conditions | Total Cost Assuming 3% Inflation** | Total Cost Assuming 5% Inflation** |
| --- | --- | --- | --- | --- | --- |
| $1.349 Billion | $1.483 Billion | $133.7 Million | $126.5 million | $1.660 Billion | $1.789 Billion |

*Predesign Estimate excludes future inflation

**Projected future costs by WTD are rough order of magnitude based on a range of possible inflation outcomes.

R.W. Beck, Inc., the Oversight Monitoring Consultant for the Brightwater project (Attachment #5), completed a detailed review of the proposed baseline budget.  Beck will present its findings and recommendations at the Committee meeting.  In brief, key conclusions in the Beck report include:

- Modifications to the baseline budget are not warranted at this time, although the overall budget appears somewhat low (5% to 6%) based on the level of contingencies built into the budget.

- The Wastewater Treatment Division should take action to establish a collaborative relationship between the project designer and the contractor to avoid future problems with scope of responsibility and authority as between the contractor and designer.

- The contract with the General Contractor/Contract Management (GC/CM) contractor should include specific requirements to address competition during bidding of subcontract packages.

Application of Escalation:  In addition to the budget in 2004 dollars, the Wastewater Treatment Division (WTD) provided information on inflated costs, assuming a 3% and a 5% rate of inflation over the project lifetime.  Because the rate and impact of inflation is variable and could change significantly over time, Committee staff requested Beck to provide additional analysis regarding the use of 3% and 5% for inflation in escalating the costs of the project over time.  Specifically, committee staff noted the following concerns with this method:

- Traditional estimating methods show total project costs including escalation.

- Extraordinary escalation should not be included in the base project estimate

- Consultants should be required to use their best professional judgment to estimate project including escalation.

- Assumed project escalation should be clearly identified in project estimates.

- Application of 3% and 5% escalation to every budget line item for every year through 2011 is too broad.  Not all budget items will escalate at the same rate as construction commodity prices (i.e. staff salaries, permitting & fees, land purchases, and executed contracts).

In a letter to committee staff dated June 29, 2005 (Attachment #6), Beck noted that it would be useful to have a line item budget showing project costs in escalated dollars.  Using the Division’s approach could lead to future confusion because:

- Expressing and tracking costs in 2004 dollars creates a discrepancy between actual costs and the stated project budget;

- Project components can vary substantially in terms of how they are affected by inflation, and applying a percentage escalation uniformly to all costs could be misleading; and

- If detailed assumptions regarding escalation are not clearly identified, it may be difficult to track how well the project is adhering to the original budget estimate.

The WTD response is that adjustments in the escalated cost estimates and the actual costs over time will be identified and evaluated in the monthly Brightwater reports, including any differences between the baseline budget assumptions and actual inflation.

Monthly Reporting Format:  A simplified reporting format was required by a 2005 budget proviso (Attachment #1A) and is patterned after other existing CIP reporting formats such as the Harborview Bond Project and the Courthouse Seismic Project monthly reports.  Committee staff completed a preliminary review of the proposed Monthly Report Format which is included in the staff report in Attachment #1B.

The following is a summary of several key items discussed between council staff and Wastewater Treatment Division (WTD) staff:

- On-Line Monthly Reports:  In February, WTD staff advised that they were working to publish the Brightwater monthly reports online.  The reports are now on online on the King County Intranet at http://dnr-web.metrokc.gov/wtd/reference/brightwater  Following the June 2005 report, the reports will be transmitted via e-mail notification to all distribution list addressees including Councilmembers and staff.

- Reporting on Changes:  Council staff has been working with WTD to develop a process under which the WTD will provide notification (in addition to the exceptions notification provisions in K.C.C. 4.04.020) of any known changes in scope, schedule, and budget that exceed specified thresholds.  The notification would be specifically highlighted in the Project Summary of the regular monthly project reports.  Notification will include a description of any scope, schedule, or budget change, an explanation of reasons contributing to the change, and any proposed mitigation strategies.

Proposed Amendment 1 (Attachment #1) includes provisions for notification of anticipated changes to the project that exceed the following thresholds:

- Design Phase Estimates at 60 %, 90 % and 100 % that deviate from the approved baseline budgets by 10% or more.

- Bid protests and bids received that deviate by 10 % (up or down) from the engineer’s estimate and/or the baseline construction budget.

- Changes to a major milestone in the schedule by 90 days or more.

- Single occurrence change orders that exceed 5% of construction contract value or cumulative change orders that exceed 10 % of construction contract value.

- Adjustments of project contingency budgets.

- Violations of permit conditions or regulations, work stoppages, significant safety problems, and significant community complaints.

- Significant deviations (+/- 15%) of annual accomplishment rate.

- Scope changes that may result in a negative or positive schedule change of 90 days or cost increase/decrease of 5% of the approved baseline budget.

REASONABLENESS:

A baseline budget will provide the Council and other decision makers with a tool to monitor the Brightwater Project cost changes over time.  The baseline budget is based on a detailed pre-design estimate provided in October 2004.  Given the design and purpose of the baseline budget for the Brightwater project, approving it in its current form would be a reasonable business and policy decision.

The monthly report on the Brightwater project is intended to keep the Council and other decision makers informed of the progress of the project and to alert decision-makers regarding significant changes in the scope, schedule and budget of the project.  The report format developed by WTD for the Brightwater project would provide this information, and approving the format would be a reasonable business and policy decision.

INVITED:

- Bob Bingham, R.W. Beck, Inc.

- Pat Tangora, R. W. Beck, Inc.

- Kathy Loland, Wastewater Treatment Division

- Pete Letourneau, Wastewater Treatment Division

- Tom Lienesch, Wastewater Treatment Division

ATTACHMENTS:

# Footnotes

Value Engineering:  Value engineering (VE) is a process that reviews and challenges a projects design elements including underlying assumptions and methodologies, to reduce costs without sacrificing value