Timeline for Community Crisis Alternatives Program

Phase Three

January 23, 2007

|  | Feb 28 | March 15 | Feb-May | May 2 | May 7 | May 15 | May 23 | June 1 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Milestones | Begin outreach to community stakeholders and recruit workgroup members | Prevalence profile completed | Regular meetings of planning workgroup; April 1 letter to council requesting delay | Complete first draft for review by workgroup | Complete final draft for review by Jackie and others | Report due to Executive | Present to CJ Council | Report due to Council |
| Work needed | Community forum style meetings with CD and MH providers, ESD, KC sheriffs, suburban cities | Gather info from DAJD, HMIS, CTU, MHCADSD database, TARGET, HCH, one-night count, UNC and national prevalence data | Prioritize intercept points and define key strategies for achieving comprehensive continuum of care, including system-wide changes needed. | Determine cost & time estimates for services to be implemented, present financing strategy, where and when to invest, & ensuring no supplanting | Include executive summary, documentation of process, references to national models, appendix showing costing methodology | Briefings needed before final report to Executive | Get on Agenda | Include transmittal letter |
| Staff | DCHS | DCHS | DCHS and OMB | DCHS and OMB | DCHS | DCHS | DCHS | DCHS |