Significant changes to the 2009 WTD Capital Program:

- Brightwater Treatment & Conveyance:

The latest 2008 trend estimate is the basis for the current Brightwater cashflow.  Project costs have increased from the prior year trend (2007) primarily due to the higher actual cost of contracts awarded for the Influent Pump Station ($20 million), Treatment Plant Solids Contract ($12.8 million) and Treatment Plant Liquids subcontract packages ($12 million).  Partially offsetting these increases were lower costs for the Outfall design-build contract of $4.4 million and reductions to overall program contingency of $19 million.  The net increase from the prior trend is estimated to be $33 million.  The majority of construction contracts are now awarded, thereby reducing risk associated with inflation and the bidding environment.

| Status | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
| 2008 Adopted | 348,886,132 | 468,816,639 | 151,401,286 | 144,727,498 | 0 |
| 2009 Proposed | 363,300,940 | 403,647,899 | 268,637,663 | 95,017,095 | 24,641,741 |

Non Brightwater Project Changes:

- 423515-007 CSO Control and Improvement – University:

The planning and design process to achieve capacity improvements to the University CSO was scheduled to begin in 2009.  Further analysis of this system indicates that the improvements can be delayed up to 2 years. This delay will permit further data collection on the Densmore Drain, where we lack reliable flow data.  This new data will help us determine the remaining CSO flow to be controlled at University.  By implementing other minor improvements else where in the system (the Duwamish drainage is proposed) we can keep the overall CSO program on track for system control by 2030.  Staff proposed a two year delay in University CSO, which results in $2.98M being moved out to 2011; and $3.29M moved to 2012.

| Status | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
| 2008 Adopted | 0 | 2,985,707 | 3,292,689 | 2,237,272 | 12,295,029 |
| 2009 Proposed | 0 | 0 | 0 | 2,985,707 | 3,292,689 |

- 423368 Sediment Management Plan:

We proposed moving $8M from the 2010 budget of the Sediment Management Program, and increasing the 2011 budget by the same amount.  This budget was established to pay for costs anticipated as part of the Superfund allocation process.  This process spreads the cost of Superfund cleanup activities among the 4 partners in the Lower Duwamish Work Group (Seattle, King County, the Port, and Boeing).  At present, we do not believe the allocation process will begin in 2010. The remaining budget in 2010 should be adequate to cover the other staff and consultant labor for planned sediment management activities scheduled for work in 2010.  Only the payments under the allocation formula (yet to be determined) are postponed.

| Status | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
| 2008 Adopted | 3,191,147 | 9,618,115 | 20,414,290 | 2,240,916 | 325,340 |
| 2009 Proposed | 4,374,737 | 2,703,148 | 5,015,562 | 24,293,471 | 956,835 |

- 423521, Bellevue Pump Station:

This project will modify the existing pump station in Bellevue and replace all the major mechanical and electrical equipment including the control system; and build a new 5,700 foot force main.  The pump station construction contract has been delayed until August 2008 due to a bid protest necessitating rebidding of the contract. This delay moves $4.9 million for construction from 2008-09 to 2010-2011.  The potential for an overflow is only increased by 3% with this delay.

| Status | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
| 2008 Adopted | 10,599,939 | 5,856,130 | 18,212 | 0 | 0 |
| 2009 Proposed | 1,300,000 | 3,800,000 | 5,700,000 | 3,230,000 | 0 |

- 423618, RWSP Local Systems I/I Implementation:

Inflow/Infiltration (I/I) reduction is intended to reduce peak flow demands within the regional conveyance system by repairing leaky side sewers and laterals in local systems.  If successful, the I/I reduction projects will reduce or eliminate the need for more costly capital improvements to the regional conveyance system.  The I/ I implementation project has been changed from 3 or 4 pilot system modifications to 2 or 3 pilot system modifications, reducing the overall budget by $ 5 million.  One of the areas identified in the planning process is indicating a low infiltration rate, supporting the reduction in pilot project areas.

| Status | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
| 2008 Adopted | 1,771,132 | 3,409,414 | 10,605,122 | 10,419,610 | 298,686 |
| 2009 Proposed | 1,544,381 | 1,168,000 | 2,654,546 | 1,258,818 | 6,699,327 |

- 423615, Black Diamond Storage Facility:

This project will fund the design and construction of a wastewater storage facility in Black Diamond (BD) upstream of the existing BD pump station.  Construction of the Black Diamond Storage Facility will be delayed from 2010 to 2012 shifting $9.7 million from 2010-11 to 2012-13. This delay should not have an immediate impact to local service due to the uncertainty of the planned development in the Black Diamond area.  Design effort has been extended to consider future water reuse.

| Status | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
| 2008 Adopted | 1,050,230 | 2,752,940 | 833,652 | 0 | 0 |
| 2009 Proposed | 829,700 | 764,000 | 340,000 | 1,075,000 | 3,466,000 |

- 2009-007 Sunset/Heathfield Pump Station Replacement and Forcemain Upgrade:

This project is intended to increase the peak pumping capacity of the two pump station system to utilize the maximum available capacity in the regional gravity sewer systems directly upstream and downstream of the pump stations and force main discharge point.  This project has been delayed 2 years as part of the effort to balance the financial plan.  Total project costs will be impacted by inflation and potentially changes in building codes and more stringent permitting requirements.  This delay shifts $5 million in project spending out of 2008-2011 to 2012-2013.  Delay of this upgrade will result in decreases in the year current peak flow level of service because of limitations of the existing pumps.  There is an increased risk of overflowing to Lake Sammamish.  Increased maintenance costs are anticipated to ensure continued operation of the stations’ large influent pumps.

| Status | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
| 2008 Adopted | 0 | 887,000 | 2,292,000 | 2,889,587 | 2,210,405 |
| 2009 Proposed | 0 | 0 | 0 | 887,000 | 2,292,000 |

- 423592, West Division Regulator and Four Pump Station Upgrade:

This project upgrades the West Division Offsite Facilities electrical and control systems as well as the HVAC systems. It replaces obsolete equipment which the manufactures no longer supports and spare parts are not inventoried. All low priority modifications have been removed from the scope of work. The deletion of the low priority work results in a decrease of about $2.95 million.

| Status | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
| 2009 Adopted | 2,390,266 | 3,360,771 | 2,137,418 | 1,499,865 | 173,891 |
| 2009 Proposed | 1,243,944 | 3,489,165 | 2,020,297 | 0 | 0 |