Metropolitan King County Council

Budget & Fiscal Management Committee

| Agenda Item No.: | 2, 3, 4, & 5 |  | Date: | April 7, 2004 |
| --- | --- | --- | --- | --- |
| Proposed No.: | 2003-0100 2004-0073 2004-0103 2004-0126 |  | Prepared By: | David Layton |

STAFF REPORT

SUBJECT:	Today’s briefing is on a series of interrelated legislation for the proposed New County Office Building (NCOB).  They are:

- Proposed Ordinance 2003-0100 adopting the 2003 Space Plan,

- Proposed Motion 2004-0073 approving the proposed NCOB Phase II Project Plan which will release an expenditure restriction of $400,000,

- Proposed Motion 2004-0126 approving the NCOB site selection recommendations,

- Proposed Ordinance 2004-0103 amending the proviso language in Ordinance 14812 and provide early release of $350,000 for phase II of the NCOB.

BACKGROUND:

The job of planning, acquiring and managing office space for county agencies resides with the Executive. Under the code, the Executive is required to determine the current and future space needs of county agencies and submit a county space plan update to the Council by August 1st of each year. The county adopted the initial space plan in 1993 and subsequent space plan updates were approved in 1997 and 2002.

Council approval and oversight of the Executive’s space planning efforts are vested in the authority to approve the space plan, approve long-term leases, adopt agency operating and capital budget appropriations, and through expenditure restrictions (provisos).  Under the Council’s organizational structure, the BFM Committee is responsible for reviewing the Executive’s proposed annual space plan update.

The BFM Committee has been briefed on the proposed 2003 Space Plan, but delayed action to review other space-related legislation such as lease renewals, the Courthouse Lobbies (3rd and 4th Avenue entrances) Project, and the New King County Office Building (NCOB).  The Council has since approved all pending lease renewals, the Courthouse Lobbies Project, and phase two of the NCOB (See Attachment 9 for a matrix of all space plan and NCOB related legislation and policy issues).

SUMMARY:

The purpose of today’s briefing is to provide the BFM Committee an opportunity to review a package of legislation pertaining to office space planning and new building construction that establishes policies as to where county agencies should be located and the location of a new county office building – decisions that   that will drive the “look and feel” of the public’s interaction with King County for decades to come.

The county continues to face budget challenges in the Current Expense (CX) Fund with projected deficits of $15 million to $20 million annually for the foreseeable future. While the county has contained jail costs and achieved over $6 million savings in 2003, the Council recognizes that without further reductions in operational costs, by 2009 the costs of the county’s criminal justice system would entirely consume the CX Fund.

Moving from leased office space to county-owned space and constructing a new office building could provide the county an opportunity to achieve additional, significant long-term savings. Further, constructing the new building on county property would demonstrate the county’s policy-driven commitment to improving the use and management of the county’s portfolio of assets, a policy consistent with the recommendations of the Budget Advisory Task Force and the Property Expert Review Task Force.

1. PROPOSED 2003 SPACE PLAN				Proposed Ordinance 2003-0100

The proposed 2003 Space Plan was reviewed in committee on two previous occasions; however, the following key issues directly affecting the proposed NCOB are summarized below:

- Proposed Policy Change:  One of the key changes in policy proposed for Courthouse is to “Retain, upgrade, and restore the King County Courthouse for functions requiring weapons screening or a heightened level of security throughout the building.”

The implementation plan for the proposed 2003 Space Plan further elaborates on the proposed policy by stating that the Courthouse is a:

“…specialty building serving those functions such as courts who require a high level of security.”  The implementation plan clarifies that “All non-specialty functions that do not require high levels of security are candidates for a future move to a new building as functions requiring a high level of security need more space.”

The proposed policy change is based on the high cost of security and the economic need to consolidate functions requiring security into the courthouse.  Consistent with this proposed policy the Council approved two CIP projects in 2003 to relocate PAO functions back to the Courthouse.

- Courthouse Space Use:  As the Courthouse Seismic Project nears completion a series of Courthouse space use issues are emerging.  The AFIS tenant improvement project on 1A allowed for relocation of Jury Assembly and opened up space on the 7th floor.  A Work Release (WER) relocation analysis is underway which could result in additional space on the 10th floor.  Changing Superior Court and District Court requirements and space use requests as well as other Courthouse space demands prompted Facilities Management Division (FMD) to initiate a series of user agency meetings to discuss overlapping agency space needs requests.

The efficient use of law justice functions in King County is critical.  Courtroom usage is particularly important in view of the current District Court Operational Master Plan, the recent courtroom space usage correspondence between the District and Superior Courts, and the recent push for a new Unified Courts Building by the Superior Court all set the stage for a review courtroom usage.  The Courthouse Seismic Project completion in August 2004 will also bring all permanent KCCH courtrooms back into service after a two-year hiatus.  A summary matrix of courtroom usage has been initiated as the first step in understanding how King County uses its courtrooms.  The matrix is only preliminary at this point but will summarize courtroom usage by building, floor, courtroom number, and current assigned judge.

- LEEDs Policy (Leadership in Energy and Environmental Design Program):  The Executive’s Green Building Initiative has been proposed for elevation from an Implementation Plan in the adopted 2002 Space Plan to a proposed policy in the proposed 2003 Space Plan.  For newly acquired or constructed office buildings, the proposed plan calls for the county to comply with the use of LEEDs methods and techniques including practices that conserve resources, use recycled content materials, maximize energy efficiency and consider other environmental benefits.  However, while the proposed Space Plan supports the use of LEEDs methods and techniques, it does not actually establish a LEEDs policy.  LEEDs is an area requiring further cost-benefit analysis and deliberation.  The cost benefits of the LEEDs program has not been vetted by the Council and there is no adopted county-wide LEEDs policy.  In 2003 Council adopted Motion 11712 which adopted a LEEDs policy for DNR and Parks capital projects.  In late 2003 Council staff requested that a LEEDs policy discussion be initiated.  Based on staff to staff discussions draft legislation has been prepared and is currently being in internal review.  Transmittal of proposed legislation is tentatively scheduled for May 2004.

Phase II of the NCOB project scope of work includes $30,000 for a green consultant to investigate environmental opportunities.  Despite the lack of a formal LEEDs policy work was initiated by the NCOB project team on March 15th and a report distributed to the team on March 29, 2004.  The report states on page 3:

“The goal is to achieve at least a LEED Silver rating.”

NCOB PHASE II

The Council’s review and approval process for the Phase II NCOB is organized into a series of policy choices and decision points based on the orderly progression of the work leading to the authorization to proceed into final design and construction.  Phase II components include:

- A motion to approve the Project Plan

The plan includes a summary of the scope, schedule, & budget and a follow up report on the Executive’s proposal to recover the land value as part of the project.

- A motion to approve the site selection.

Site selection is the Executive’s recommendation of a preferred site based on the site evaluations of the three proposed sites proposed in 2003 (Ordinance 14812).

- An ordinance to amend the proviso expenditure authority for early release of funds.

The proposal for an early release of expenditure restrictions ($350,000) is based on the Executive’s assessment that project approvals might lag behind the pace of expenditures projected by the cash flow.  The proposal is intended to maintain planned progress.

- A motion to approve the reevaluation of the proposed central steam plant.

The reevaluation of the proposed central steam plant was necessitated by a challenge by Seattle Steam on the Executive’s 2003 analysis.

- A motion to approve a report on alternative Work Release space usage.

The analysis of Work Release is based on a request by the Council to consider the merits of alternative locations of Work Release from its current location in the Courthouse.  This request is tied to the use of space in King County and is interrelated with the proposed NCOB, Integrated Security Project (KCCF), the Space Plan and other space use proposals.

- An ordinance to approve the NCOB lease and development documents.

Lease and development documents are the legal instruments associated with the proposed “63-20” Tax exempt lease project delivery methodology and is the final step in authorizing the Executive to proceed into final design and construction.

Additionally quarterly reports will be provided to keep everyone current on the progress of the NCOB.

Today’s briefing is the first review items #1, #2, and #3 listed above.

2. NCOB PHASE II PROJECT PLAN					Proposed Motion 2004-0073

On January 30, 2004 the Executive transmitted the proposed project plan for phase II of the NCOB.  The plan is in response to a proviso requirement in Ordinance 14812 and requires council approval of the plan by Motion (Motion 2004-0073) in order to release partial expenditure authority (Attachment #3).

Scope:

The scope of work for the NCOB is based on the development of a new 261,000 RSF office building at one of three proposed county owned sites.  Phase II is the next step in a multi phased process and consists of site selection, the development of schematic design and engineering necessary to submit for a Master Use Permit (MUP).  The three building sites under consideration for further site selection evaluation at the time Ordinance 14812 was adopted were:

Option A:	Goat Hill Site

Option B:	King County Automotive Center Site

Option C:	North Kingdome Parking Lot Site

A summary of the proposed agency tenants, projected space needs and full time equivalents (FTE’s) is summarized in Attachment #10.

Schedule:

Schedules were provided for each of the three development Options (Option A- Goat Hill Site, Option B-Automotive Center Site, & Option C-North Kingdome Site).  Copies of the proposed project schedules are included in the staff report in Attachment #11.  The report cited development uncertainties of the North Kingdome Site (Option C) as the reason this schedule was less developed than Options A & B.  The proposed occupancy schedule for both the Goat Hill Site (Option A) and the Automotive Center Site (Option B) is August 2007.  Committee staff requested an analysis of the existing proposed tenant leases to confirm if an optimum tenant move date emerged.  The Executive’s analysis of lease costs, term dates and holdover costs from January through December 2007 varied significantly from month by month but can be summarized as follows:

Schedule impact of existing leases:

Average monthly rent for NCOB candidate tenants					$422,043

Average monthly decrease of termination & holdover costs Jan 2007 - Dec 2007	($55,000)

Net average monthly cost								$367,000

The analysis indicates that from a lease basis it will be in the county’s best interest to move tenants earlier rather than later.  This analysis will be useful as a tool to optimize move dates on a tenant by tenant basis.  The financial model for the NCOB assumes debt service payments will not begin until March 2008.

Lease termination restrictions will require careful planning and commitment to the completion schedule as noted by the following:

| Lease | Lease Rate | Termination | Notification |
| --- | --- | --- | --- |
| Exchange Building | $25.72 - +0.50 annually $18.00 +0.35 annually $26.47 +$1.00 annually | 12/31/05, 6/30/06, 12/31/06, 6/30/07 | 12 months notice |
| Wells Fargo Building | $23.50 - +0.50 annually up to max $28.00 | Not earlier than 12/31/06 | 12 months notice |
| Key Tower | $24.00 – up to max $26.00 in 2008 | 3/31/07, 9/30/07, 3/31/08 | 24 months notice |
| Walthew Building | $23.00 | 12/31/06 |  |
| Bank of America Tower | $25.00 | Not earlier than 12/31/04 | 12 Months notice |

The following summarizes a review of the proposed project schedule:

- Inadequate Council Review Periods:  BFM Committee Chair transmitted a letter to the Executive dated February 17, 2004 noting that the scheduled council review periods shown on the proposed schedule were inadequate for the council to do its due diligence and needed to be revised.  The proposed schedule included five separate council review and approval periods which varied from 2 to 5 weeks but averaged 30 days (from transmittal to full council approval).  Committee staff provided guideline of a minimum of 60 days from introduction to full council action on legislation.  However, this guideline is not a commitment and is subject to overall committee workload.

- Design Schedule:  Committee staff noted that the project design schedule could be reduced by several months if the Master Use Permit and SEPA processes were done concurrently with the design development and contract documents phases.  Following a review and confirmation by the project team that any added development risks could be reasonably managed Committee staff requested that the proposed schedule be revised to reflect this approach.

- Construction Schedule:  Further refinement of construction schedule assumptions methods and techniques by executive staff and the developer subsequent to transmittal of the site selection recommendation report indicated that construction phasing could be reduced by several months.

Revised Schedule:  Based on the above Committee staff requested that revised project schedules for Options A and B be developed to reflect an orderly sequential review and approval process.  The revised schedules were not received in time to include in this staff report.  The revised schedules were to include the following key milestone council review and approval periods for each of the following:

|  | Original Proposed Schedule | Revised Proposed Schedule |
| --- | --- | --- |
| Description | Review Period | Scheduled Approval | Review Period | Scheduled Approval |
| Project Plan | 30 days | 3/1/04 | Not Received | Not Received |
| Site Selection | 26 days | 3/29/04 | Not Received | Not Received |
| Steam Plant | 19 days | 4/19/04 | Not Received | Not Received |
| Work Release | 21 days | 5/3/04 | Not Received | Not Received |
| Lease/Development Documents | 36 days | 9/13/04 | Not Received | Not Received |

Council Design and Planning Participation:  Recognizing the Council’s interest in the design and development of the NCOB, Executive staff have proposed that the council establish a committee to comment and advise on the design, finishes and relationship to the courthouse campus of the NCOB.  This committee could consist of interested council members and staff and would be provided briefings on a bi-weekly basis.  These briefings would continue until the MUP process is complete and would not replace the weekly council staff attendance at the NCOB development team meetings.

Budget:

Ordinance 14812 appropriated $1.2 million for the phase II scope of work pending approval of a series of proviso restrictions.  A summary of the phase II budget is as follows:

Table A

Approved Phase II Budget

Architect				297,000

Structural Engineer			  70,000

Civil Engineer				  22,000

Electrical Engineer			  10,000

Mechanical Engineer			  20,000

Minimum Signage for MUP		    2,000

Elevators				  10,000

Lighting (exterior for MUP		    2,000

Traffic Engineer			  30,000

Green Consultant			  30,000

Reimbursables				    7,000

Survey					  42,000

Soils Testing				  85,000

MUP Permit Estimate			  40,000

Subtotal			687,000

King County Staff/Advisors		225,000

Steam Plant Design			300,000

Total Proposed Budget	         1,212,000

King County Staff Costs:  The total King County staff costs for Phase II and Phase III (construction) are budgeted at $456,954 which represents less than 0.7% of the Guaranteed Maximum Price (GMP).  This compares to 0.6% staff cost for the Patricia Bracelin Steel Memorial Building GMP which utilized a similar 63-20 project delivery methodology.  Staff costs for traditional Design-Bid-Build projects generally run around 7% of the Maximum Allowable Construction Cost (MACC).

Steam Plant Design:  It is anticipated that only a portion of the steam plant design budget of $300,000 will be needed based on the current recommendation to utilize a simpler more straight forward central hot water boiler system design for the King County complex of buildings.

Land Liquidity Options:  The Executive report entitled An Approach to Reducing King County Office Space Costs provided information showing that if the county selected a county owned site for the proposed NCOB an opportunity existed for the county to liquidate the land value and achieve a one time cash revenue equivalent to the value of the land.  The example provided was based on an assumed $10 million value for the Goat Hill site.  The Council included a proviso restriction in Ordinance 14812 and asked the executive to evaluate the land liquidity proposal further and make a formal recommendation.

The proposed project delivery methodology for the NCOB is a “63-20” tax exempt lease-lease back financing strategy.  As a reminder, “63-20” tax exempt bond financing is a provision of the Internal Revenue Service (IRS) tax code that allows a non-profit corporation to issue tax exempt bonds to finance a project utilized by a government agency.  This project delivery methodology has been used by the county on the King Street Center and the Patricia Bracelin Steel Memorial Building projects.

Under the initial land liquidity proposal (12/2003), the land would be transferred to the non-profit entity.  The bonds issue would be sized to include the value of the land.  The county would then receive payment for the land from the bond proceeds in a lump sum.  Under this concept, the tenant lease payments would be used to retire the debt including the land value.  At the end of the lease term (+/- 25 years) land ownership would revert back to King County along with the building.

Subsequent discussions with the Prosecuting Attorney’s Office and the county’s bond council concluded that application of the land liquidity concept within a “63-20” tax code delivery methodology was an untested position and could result in unintended transaction risks for the county.  As a result in January 2004 the Executive recommended an alternative internal county process that will avoid any transaction risks yet still achieve the financial objectives of land liquidity.  The Executive’s current recommendation is to charge the NCOB tenants rent through the county’s central overhead and recover the value of the land in rent payments each year as a CX revenue.  Because the majority of proposed NCOB tenants are non-CX agencies (92%) it is estimated that rent revenues accruing to the CX fund would be in the range of $672,000 to $738,000 annually.  According to the report total liquidation of the land value could be accomplished at any time with the issuance of limited tax general obligation bonds (LTGO) backed by the rent revenue stream.

The report notes that the Executive’s recommended land liquidity concept will receive a full legal review prior to implementation.

Options for use of the Land Liquidation Funds:  Under the proposal, tenant rent payments should start accruing once occupancy of the NCOB occurs sometime in 2007.  The proposed financial model for the NCOB assumes debt service payments will start in March 2008.  The Council could designate use of these funds either through the annual budget process; or, by policy, designate use of these funds for a specific purpose.

CX Debt Service Policy:  The county’s CX debt service policy is defined in Motion 11196 (2001) and Motion 5888 (1984).  These policies are summarized as follows:

- Required annual debt service payments shall not exceed 5% of the general fund’s net revenue available for debt service.

- Anticipated year-end undesignated CX fund balance should be between 6% and 8% of estimated annual revenues.

The adopted 2004 budget indicates the percentage of CX debt service is projected to trend upward toward the 5% maximum to 4.61% in 2005 and 4.63% in 2006.  Executive staff noted that the proposed NCOB project will have only minimal impact on the CX debt service policy limit due to the low percentage of CX agencies proposed in the building (7.66%).  Based on this interpretation of the policy, beginning in 2008, the impact on the CX debt service capacity is estimated to be $478,000 annually (Option B) and $420,000 annually (Option A).  The projected debt capacity is based on a 2% revenue growth projection for 2008 is shown in the following table:

| CX Debt Service | Adopted 2004 Budget Projected 2006 CX Debt Service | Projected 2008 CX Debt Service | Increase / Decrease |
| --- | --- | --- | --- |
| Total Revenue | $450,296,826 | $468,488,818 | $18,191,992 |
| Budgeted Debt | $20,866,560 | $21,344,560 | $478,000 |
| Debt as % | 4.63% | 4.56% | -0.08% |

The PAO has been requested to provide an interpretation of the policy.  Committee staff will continue to monitor this issue.

3. NCOB PHASE II SITE RECOMMENDATION			Proposed Motion 2004-0126

The analysis report entitled An Approach to Reducing King County Office Space Costs included preliminary evaluation of three candidate building sites for further site evaluation and final site selection as part of a Phase II effort.  These three sites are:

- Option A:  Goat Hill Site

- Option B:  Automotive Center Site

- Option C:  North Kingdome Parking Lot Site

Council adopted Ordinance 14812 In December 2003 which provided a supplemental appropriation of $1.2 million to proceed with phase II.  The Executive transmitted his site selection recommendation on March 4, 2004.  Proposed Motion 2004-0126 would approve the executive’s recommended Option B:  The Automotive Center Site for the NCOB (Attachment #5).

Site Options Key Issues:  The site recommendation report noted the following key issues associated with each of the following three sites evaluated:

Option A  Goat Hill Site:

- 261,000 RSF Building

- 337 structured parking, 80 on-grade parking, 985 total parking

- Less than desirable soils conditions.

- Steep grade.

- Requires coordination with WSDOT (I-5).

- Requires $6.6 million in planned Automotive Center upgrade investment.

- Uses approximately one-half of future Goat Hill development potential.

- Preserves future Automotive Center development potential.

Option B  Automotive Center Site:  `

- 260,000 RSF Building

- 248 + 657 structured parking, 80 on-grade parking, 985 total parking

- Requires a two phase construction process – longer schedule.

- Better soils and grade conditions.

- Closer proximity and access to Administration Building & Courthouse.

- Views are less obstructed compared to Option A (i.e. higher property value).

- More efficient parking than Option A (i.e. compared to existing Automotive Center).

- Saves $6.6 million in planned Automotive Center upgrade investment.

- Preserves future Goat Hill development potential.

Option C  North Kingdome Parking Lot Site:

- 260,000 RSF Building

- 149 structured parking, 250 replacement parking

- Limited allowable zoning height.

- High water table limits below grade parking and revenues.

- Inability to acquire property from Public Stadium Authority (PSA).

- Requires extended schedule due to unknown development constraints.

- Requires “L” shaped “oversized” floor plates (49,500 SF/Floor).

- Higher development costs.

- Close proximity only to King Street Center.

- Unknown soils conditions.

- Possible conflicts with planned monorail extension.

Throughout the Site Recommendation report comparable data on Option C (North Kingdome Parking Lot Site) is less developed compared to Options A & B.  The report notes overriding development uncertainties and site encumbrances that led to the Executive’s decision to discard this option.  Option C would require acquisition of a portion of the Public Stadium Authority (PSA) north lot property in order to achieve the objective of a 260,000 RSF building.  Attachment C to the Site Selection Recommendation Report includes a letter from the Washington State Public Stadium Authority dated February 3, 2004 summarizing the PSA board’s objections to locating a portion of the NCOB on PSA property.  The PSA letter further notes the Stadium Act does not allow an office building that is not associated with the Stadium and Exhibition Center to be built on land owned by the PSA (Section 106(2) of the Stadium Act).  It is estimated that without the PSA parcel the NCOB size would be reduced by approximately 110,000 RSF (42%).  The report includes a series of rough order of magnitude premium costs associated with development of Option C totaling over $20 million (pages 10-12).  Based upon the above the report concludes in Section 2.3.1, page 10 that:

“Notwithstanding the highly speculative nature of the development assumptions, it is currently infeasible to site an office building on the North Kingdome Parking Lot that will meet the county’s requirements.”

Comparison of Option A and Option B:  A cost comparison between the original pro-forma, Option A and Option B is summarized in the following excerpts from Table 1 Economic Comparisons to Original Pro-forma; proviso response #2, page viii:

| Cost Element | Original 12/03 Pro-forma | Option A Goat Hill Site | Option B Garage Site |
| --- | --- | --- | --- |
| New County Office Building |  |  |  |
| Entitlements and Utilities | $865,000 | $865,000 | $983,000 |
| Shell and Core Architecture | $1,131,000 | $1,131,000 | $1,720,000 |
| Shell & Core Engineering | $898,000 | $898,000 | $1,197,000 |
| Shell & Core Construction | $43,446,500 | $39,457,000 | $46,423,540 |
| Tenant Improvements | $14,331,500 | $14,331,500 | $16,351,500 |
| Misc. Dev. Costs/Fees/Contingencies | $9,293,710 | $9,253,815 | $10,290,030 |
| Total Development | $70,165,710 | $66,136,315 | $76,965,070 |
| Financing | $2,500,000 | $2,900,000 | $2,900,000 |
| Net Capitalized Interest | $6,312,987 | $6,326,422 | $5,871,941 |
| Total Development w/financing(excl. land) | $78,978,697 | $75,362,737 | $85,737,011 |

| Existing Automotive Center Garage |  |  |  |
| --- | --- | --- | --- |
| Vehicle Restraint & Exterior Enhancement |  | $4,200,000 | - |
| MMRF & Seismic Upgrade |  | $2,400,000 | - |
| Subtotal Automotive Center |  | $6,600,000 | $0 |

| Total Combined Projects (excluding Land) |  | $81,962,737 | $85,737,011 |
| --- | --- | --- | --- |

Existing Automotive Center Garage Projects:  The series of planned infrastructure improvements to the existing Automotive Center noted in the table above will have a cost impact on whatever Option is ultimately selected.  These projects are summarized in the following table:

Costs Unique to Option A – costs included in cost summaries above

| Description | Justification | Estimate | Comments |
| --- | --- | --- | --- |
| Vehicle Restraint | Safety | $1.66 million | Seattle Building Code requirement (voluntary-non retroactive). Space Plan policy – To maintain safe and attractive buildings |
| Exterior Enhancement | Aesthetic | $2.5 million | Exterior facing to upgrade compatible with NCOB (voluntary) |
| Seismic Upgrade | Safety | $594 thousand | A total of $1,138,173 appropriated in 2000 through 2003. Remaining unencumbered (03/17/04) $720,000 |
| MMRF | Maintenance | $864 thousand | Various 6-year MMRF CIP projects |

Automotive Center costs unique to Option B are summarized in the following table:

Costs Unique to Option B – costs included in cost summaries above

| Demolish existing Automotive Center and Replace | Option B Requirement | $11.6 million | Premium construction cost (including soft costs) to demolish and rebuild a new parking garage for 568 vehicles. |
| --- | --- | --- | --- |
| Automotive Center Maintenance Shop Relocation | Option B Requirement | $2 million | Placeholder Estimate only. Final resolution of the maintenance shop relocation is unresolved at this time. |
| View Protection (i.e. property value) | Option B Requirement | No Allowance Established | Option B will require some form of view protection from a possible major development on the western half of the block. This might mean acquisition of property or air rights. |

Land Value:  The above summaries are exclusive of any county-owned land value assumptions.

Budget Summary:  The following table is based on figures provided by Executive staff.  Committee staff analysis continues.

| Description | Option A Goat Hill | Option B Automotive Center |
| --- | --- | --- |
| Total Development (incl. Financing, Excl. land) Minimum Bond Size Amounts | $75,362,737 | $85,737,011 |
| Costs |  |  |
| Annual Debt Service | ($5,481,935) | ($6,236,567) |
| Land Payment in lieu of debt | ($727,407) | $0 |
| MMRF | ($236,249) | ($236,249) |
| Remodel | ($87,289) | ($87,289) |
| Total Costs | ($6,532,879) | ($6,560,104) |
| Rent |  |  |
| Rent $/SF | $22.24 | $25.13 |
| Value of Land (based on $10 million) $/RSF | $2.79 | $0 |
| Total Rent | $25.03 | $25.13 |
| CX |  |  |
| CX Tenant Portion of Debt Service | ($420,000) | ($478,000) |
| Land Value Revenue to CX | $672,000 - $738,000 | $0 |
| Total Net CX | $252,000 - $318,000 | ($478,000) |
| Impact on Agency Overhead |  |  |
| Existing Rent Proposed Tenants (2007) | $5,064,521 | $5,064,521 |
| NCOB Rent Proposed Tenants | $6,532,879 | $6,560,104 |
| Difference | ($1,468,358) | ($1,495,583) |
| Existing Automotive Center |  |  |
| Safety & Enhancements | $4,200,000 | $0 |
| Existing (funded) Projects & MMRF | $2,400,000 | $0 |
| Total Automotive Center | $6,600,000 | $0 |

A copy of the Executive’s project costs summary for Option A and Option B, including land values, is included in the staff report in Attachment #12.  A cost summary for Option C was not transmitted in the report.

Other Proposals:  As with previous reports, the Executive’s site selection report reiterates a willingness to consider other competitive proposals (Executive Summary, page vii).  However, as with previous phases the willingness to consider alternatives is conditional and lacks the appearance of an active pursuit.

4. NCOB PROVISO MODIFICATION				Proposed Ordinance 2004-0103

Ordinance 14812 included a series of proviso expenditure restrictions.  The first proviso restricted expenditure authority on $400,000 until Council approved by motion a Project Plan (Proposed Motion 2004-0073).  Proposed Ordinance 2004-0103 was transmitted to provide early release of $350,000 of restricted expenditure authority prior to approval of the Project Plan in order to avoid a possible cash flow situation (Attachment #7).

It has come to the attention of committee staff that Schematic Design and MUP application materials were initiated on March 1, 2004 primarily on the executive’s recommended Option B.  Work on the schematic design commenced before approval of the Project Plan, Proposed Project Schedule, and even before transmittal of the Executive’s Site Selection Recommendation Report.

The executive’s cash flow analysis indicates that the consultant team will expend approximately $282,000 during March and April.  Clearly some of this work will be sunk costs should the Council approve a site other than the executive’s recommended site.

It is typically unacceptable King County policy to initiate design work prior to Council approvals.  Under extraordinary circumstances mitigating circumstances may warrant such activity but usually only after careful consideration of all factors.  In any event it is the Council that should make the policy call on whether or not proceeding with design is warranted at this time.

NCOB QUARTERLY REPORT:

The first NCOB quarterly report was due to be transmitted on March 31, 2004.  As of the date of this staff report BFM Committee staff had not received the transmittal.  It is intended that all council members are to receive copies of the quarterly reports.

CENTRAL STEAM PLANT REEVALUATION

The central steam plant reevaluation report was due to be transmitted on March 31, 2004.  As of the date of this staff report BFM Committee staff had not received the transmittal.

Next Steps:.

- Finalize Review of the Project Plan (Proposed Motion 2004-0073).  Approval of this report will allow the team to proceed with Phase II and will release $400,000 of expenditure restrictions.

- Finalize Review of the Site Selection Recommendation (Proposed Motion 2004-0126).  Resolution of site options will allow the project team to focus on development of a single direction.

- Finalize Review of the Steam Plant Report (Proposed Motion 2004-XXXX).  Resolution of the steam plant issue will allow the team to move forward with the energy design for the NCOB and the county’s downtown complex.

- Review of Proposed 2004 Space Plan.  Transmittal is anticipated in June 2004.

INVITED:

- Kathy Brown, DES Director, Facilities Management Division

- Dave Preugschat, DES Deputy Director, Facilities Management Division

- Jim Napolitano, DES Capital Projects Manager

ATTACHMENTS:

- Proposed Ordinance 2003-0100

- Transmittal Letter, dated March 3, 2003

- Proposed Motion 2004-0073

- Transmittal Letter, dated January 30, 2004

- Proposed Motion 2004-0126

- Transmittal Letter, dated March 4, 2004

- Proposed Ordinance 2004-0103

- Transmittal Letter, dated February 25, 2004

- Space Planning & NCOB Legislation & Policy Matrix

- Proposed NCOB Space & FTE Projections

- Proposed Schedules Options A, B, & C

- Executive Proposed Economic Comparisons, Options A & B

# Footnotes

The Facilities Management Division within the Department of Executive Services is responsible for performing these functions.

The LEEDs Green Building Rating System™ is a voluntary, consensus-based national standard for developing high-performance, sustainable buildings. Members of the U.S. Green Building Council representing all segments of the building industry developed LEED and continue to contribute to its evolution (see:www.usgbc.org)	.

Master Use Permit (MUP) is a Seattle permitting requirement that includes resolution of site and zoning, issues early in the design process.  It is a first step in the overall Seattle building permit process.

Holdover is staying beyond the termination date on a month to month tenancy. There is usually a penalty associated with holdover.