Attachment B.								12018

Annexation Initiative

Executive’s 2005 Work Program    9/22/04

Communication, Outreach, and Negotiation Activities

- Continue to engage regional leaders regarding the importance of the County’s Annexation Initiative.

- Expand citizen/community outreach efforts on community-by-community basis to increase awareness regarding the importance of annexation in addressing the sustainable and efficient provision of local services.

- Work with King County workforce and unions to identify ways to manage any staff/departmental transitions associated with annexation or incorporation..

- Establish a reporting mechanism to the King County Council on initiative activities.

- Consistent with the county’s adopted state legislative agenda, actively engage in state level activities regarding annexation methods, related policies, and additional funding:

- Testify in State Legislature

- Pursue State Legislation to increase options to address remaining small urban unincorporated islands if they are not being annexed in a timely fashion.

- Develop joint legislative agenda on annexation with cities in preparation for 2005 legislative session.

- Continue to seek additional sources of state funding to support city annexation/incorporation efforts.

- Participate in Boundary Review Board proceedings as appropriate to advance Annexation Initiative.

- Negotiate Interlocal Agreements for highest priority areas.

Fiscal Analysis, Budget and Transition Planning

- Continue to refine and improve financial model and database for unincorporated area revenue and expenditures to support both external outreach needs and internal budget and transition planning work: - Refine the identification of services by type (regional, local, urban, rural, contract). - Identify services, costs, and revenues for each of the ten largest urban unincorporated areas and by County fund or department. - Develop methodology to identify fiscal impacts of annexations on the county overhead allocation and internal service fund rate models. - Develop target reductions for each department/division prior to final negotiation of any specific agreements for annexation or incorporation.

- Establish a workgroup among affected executive departments and divisions as well as the sheriff’s office, prosecuting attorney’s office, and the district court, for development of department/division specific annexation transition plans for operations and budget. - Assess the impact of annexations on the County’s contract services and identify opportunities for contracting with cities for service delivery in newly annexed areas. - Review target reductions for each department/division prior to the finalization of any specific agreements for annexation or incorporation. - Assess the impact of annexations and incorporations on county employees and work with employees and unions to develop transition plans for impacted employee groups. - Integrate annexation effort and associated transition planning into all operational master plan efforts. - Develop framework for examining post-annexation changes in service delivery and budget savings scenarios for both direct and indirect costs.

- Prioritize the ten largest urban unincorporated areas for accelerated annexation efforts based on refined financial analysis and city/resident interest.

- Develop area-specific strategies based on outreach efforts and refined financial analysis.

- Develop and implement “island” strategy to address the 10% of remaining unincorporated urban areas (approximately sixty islands less than 100 acres in size).