## STAFF REPORT

| Agenda Item: | 10 | Name: | Erin Auzins |
| --- | --- | --- | --- |
| Proposed No.: | 2023-B0120 | Date: | November 28, 2023 |

Subject

An overview of the Council review process for the 2024 King County Comprehensive Plan.

Summary

The 2024 King County Comprehensive Plan (2024 KCCP) will be the first opportunity where the entire plan will be open for review and update since 2016.  The Executive expects to transmit the 2024 KCCP to the Council on December 7, 2023. It is also expected that the 2024 KCCP will be referred to the Local Services and Land Use (LSLU) Committee.

Review of the 2024 KCCP will be led by the LSLU Chair, consistent with past updates.  Review will include Committee briefings on the substance of the Executive's Recommended Plan (ERP), substantive analysis of each change by policy staff, public outreach, development of a LSLU Chair's striker, line amendments by LSLU Committee members, and a vote in LSLU in June 2024.

Full Council adoption is expected in December 2024, after a formal public hearing on November 19, 2024.

Anticipated key dates are shown in the table below.

| Date | Event |
| --- | --- |
| December 7, 2023 | Transmittal of 2024 KCCP to Council |
| March 29, 2024 | Striking amendment requests due to LSLU Chair/staff |
| May 14, 2024 | Striking amendment released |
| May 22, 2024 | Line amendment requests due to staff |
| June 5, 2024 | LSLU Committee vote |
| November 19, 2024 | Full Council Public Hearing |
| December 3, 2024 | Full Council vote |

All dates are subject to change.

Background

Review Cycle.  The KCCP is the guiding policy document for land use and development regulations in unincorporated King County.  The King County Code (K.C.C.) allows for amendments to the KCCP on an annual, midpoint, or ten-year update schedule.  The ten-year update is on the same timeline as the Growth Management Act (GMA) mandated review and update. The entire KCCP, and associated implementing regulations, is open for substantive revision, subject to limitations in the GMA, VISION 2050, the Countywide Planning Policies, KCCP policies, and the K.C.C.

Scoping Motion.  K.C.C. 20.18.060 requires the County to approve a scope of work for the ten-year KCCP update, known as the scoping motion.  The scoping motion establishes the baseline issues that the County proposes to consider in the development of the 2024 KCCP update; additional issues beyond what is in the scope of work may also be addressed in the ten-year update.  The Council approved the scoping motion, as well as the State Environmental Policy Act (SEPA) work program and public participation plan, as part of Motion 16142 in June 2022.  The scope of work included three focus areas: Pro-Equity, Housing, and Climate Change and the Environment.  It also adopted a General category to cover other required and priority items for the County.

Executive Recommended Plan.  The Executive is expected to transmit the Executive's Recommended Plan (ERP) on December 7, 2023.  This follows 18 months of work by the Executive, including, in part, public issuance of an early concepts document, an interbranch review by Council staff at two stages, a Public Review Draft with a public comment period, and an interdepartmental review of the plan by Executive staff.

The Executive is expected to transmit the following:

- A proposed ordinance, making changes to development and other implementing regulations

- The ERP and associated appendices (Housing, Transportation, Capital Facilities and Utilities, Regional Trails, Growth Targets)

- Changes to the Vashon-Maury Island Subarea Plan and associated zoning map conditions

- Land use designation and zoning map amendments

- I-207 matrices and Plain Language Summary

- Equity Analysis

- Other supporting materials (Public Participation Summary, area zoning and land use studies, code studies, best available science summary)

- The Snoqualmie Valley/Northeast King County Subarea Plan (transmitted as a separate ordinance with subarea-specific development regulations and map amendments, as well as a Fall City residential study)

- Updated Countywide Planning Policies (transmitted as a separate ordinance)

The Executive has engaged with an Equity Work Group for the 2024 KCCP that have focused on housing proposals, public engagement, and equity impact review.  The Equity Work Group will be invited to an early LSLU Committee meeting to talk through their work.

SEPA Environmental Impact Statement.  The SEPA review for the 2024 KCCP will include an environmental impact statement (EIS), which includes alternatives analysis based on the scope of work and other potential amendment concepts.  The Executive expects to issue a Draft EIS concurrent with transmittal of the 2024 KCCP to the Council on December 7, 2023.  A Final EIS will be developed based on the Committee-Recommended version of the plan and any new amendment concepts.  Amendment concepts raised after publication of the Draft EIS must be within the scope of the alternatives analyzed in the Draft EIS, otherwise a supplemental EIS would be required.

Committee Review.  The 2024 KCCP is expected to be referred to LSLU Committee.  LSLU is anticipated to meet on the 1st and 3rd Wednesdays of each month from January through June 2024, and to make a recommendation to full Council at the June 5, 2024 committee meeting.  Each committee meeting will be dedicated to specific chapters of the 2024 KCCP (see the attached schedule for anticipated chapter's to be covered in each meeting). This will include briefing proposed changes, discussion of the effect of the changes, and Councilmember questions and direction for resolution of any issues to staff. This approach allows for detailed review of each chapter, but will not provide time in Committee to revisit most issues discussed in earlier meetings.  The Snoqualmie Valley/NE King County (SVNE) Subarea Plan will be briefed at the beginning of the Committee review process, and then heard with the striker at the end of the Committee review process.

The schedule takes into account a number of factors including the EIS process; LSLU Committee meetings; public comments; lead time to analyze and produce amendments; minimum noticing timeframes; and the state deadline for adoption. The schedule assumes one meeting solely for briefing the striker and one meeting to vote on the underlying ordinance, the striker, and all line amendments.

Special LSLU Evening Meetings. The Committee should expect to hold 5 special evening LSLU meetings on the 2024 KCCP and Draft EIS. At this time, staff is anticipating that the Council Chambers is the only venue that can accommodate remote participation and testimony. If KCTV determines that remote participation and livestreaming capabilities are feasible at other locations, these options will be provided to the public.

| Meeting Date/Time | Location | Focus |
| --- | --- | --- |
| Thursday, January 18, 2024 Doors open: 6:00pm Meeting starts: 6:30pm | County Council Chambers 516 Third Ave, Room 1200 Seattle | Hearing on Draft EIS |
| Thursday, February 8, 2024 Doors open: 6:00pm Meeting starts: 6:30pm | Covington City Hall 16720 SE 271st Street, Suite 100 Covington | TBD |
| Thursday, March 7, 2024 Doors open: 6:00pm Meeting starts: 6:30pm | Riverview Educational Service Center 15510 1st Ave NE Duvall | Snoqualmie Valley / NE King County Subarea Plan |
| Thursday, April 4, 2024 Doors open: 5:00pm Meeting starts: 5:30pm | Vashon Center for the Arts 19600 Vashon Hwy SW Vashon | Map changes, Shoreline code changes |
| Thursday, May 16, 2024 Doors open: 6:00pm Meeting starts: 6:30pm | Skyway area | Committee Striking Amendment |

These locations were chosen based on the location of significant map amendments and issues of interest, and to provide geographic distribution of the meetings. The first meeting on January 18th will be primarily to hear verbal public comment on the Draft EIS (the written public comment period for the Draft EIS will start in early December and extend through the end of January). Comments on the KCCP will also be accepted. The final evening meeting on May 16th will be focused on the Committee striker.

Format.  Evening meetings are expected to include: a welcome/open house at the beginning, followed by Councilmember remarks, a staff presentation, and public comment. The majority of the meeting will be dedicated to receiving public comment. Materials to share information and obtain written comment will be prepared and provided at the meeting.

Public Outreach and Communication Plan.  The GMA requires "early and continuous public participation" for all Comprehensive Plan updates.  The K.C.C. also sets requirements for public participation during the Council's review of the KCCP. This includes:

- Establishment and dissemination of "a committee review schedule with dates for committee meetings and other opportunities for public testimony;"

- Broad dissemination of the proposal and alternatives to the proposal; and

- Information on the submittal and review procedures for written public comments.

Council Policy, Communications, and Equity and Social Justice (ESJ) staff have developed a Community Outreach Plan for the 2024 KCCP, included as an attachment to the staff report.  The Community Outreach Plan proposes the following approaches:

- Opportunities for verbal public comment at each committee meeting.

- A webpage with transmittal materials, Committee materials, the review schedule, public notices, and environmental review materials.  People may also submit public comments to the Council for the record through this website; Council policy staff will then batch comments received and distribute them to all Councilmembers.

- Regular electronic news (Enews), emailed to an established subscriber list, at key milestones.

- Evening meetings discussed above, focused on receiving public comment.

- A public hearing will be held at full Council prior to final action. This is proposed on November 19, 2024, two weeks before anticipated final adoption.  A public hearing notice is published in local newspapers and mailed where there are proposed land use map amendments.

- Digital advertising and social media to increase engagement. Used on the County’s social media accounts and distributed to Councilmembers for use on their accounts. Digital advertising on these platforms can be used to engage audiences and focus on specific geographic regions where evening meetings occur.

- Press Release and Traditional Media across print, broadcast, and online outlets. This would likely be timed with key milestones (such as committee vote or final passage) or evening events in local newspapers.  Councilmembers, such as the LSLU Chair, could provide op-ed pieces on the KCCP for publication near key milestones.

- Councilmember offices may choose to complete additional district-specific engagement during the 2024 KCCP to get information out on various networks. This may include District email lists, in person meetings, or other communications. Staff would prepare graphics, information, or other materials for use by the offices.

Chair Striker.  The Committee Chair is expected to sponsor and lead development of the Committee striking amendment.  Policy staff will prepare analysis and potential options that will be distributed to all Committee members' offices for their consideration, in advance of the deadline to request striker amendments.

Regular briefings for district staff will be provided, and Policy staff will be available to brief Councilmembers individually.

Amendment deadlines.  The draft review schedule attached to this staff report includes the proposed amendment deadlines.  This schedule will be formally published after transmittal.

Key Committee review dates include:

- Striking amendment requests due to LSLU Chair/staff: March 29, 2024

- Striking Amendment released: May 14, 2024

- Line Amendment requests due to staff: May 22, 2024

- LSLU Committee vote: June 5, 2024

ATTACHMENTS

- DRAFT Review Schedule for 2024 KCCP

- 2024 KCCP Community Outreach Plan

INVITED

- Lauren Smith, Director of Regional Planning Unit, Office of Performance, Strategy and Budget

- Chris Jensen, Comprehensive Planning Manager, Office of Performance, Strategy and Budget

LINKS

Council's 2024 Comprehensive Plan website:

https://kingcounty.gov/council/CompPlan/2024compplan.aspx

Executive’s 2024 Comprehensive Plan website: https://kingcounty.gov/depts/executive/performance-strategy-budget/regional-planning/king-county-comprehensive-plan.aspx

K.C.C. 20.18.030, including changes proposed with the 2024 KCCP update.

The required best available science and critical area update will be transmitted to the Council on March 1, 2024, for the Council to incorporate into the LSLU striking amendment.

There are additional requirements for the Executive to complete in the Code.

K.C.C. 20.18.140.B.5. and K.C.C. 20.18.160.