## Slide 1: Brightwater Project Progress
Regional Water Quality Committee
March 7, 2012
Gunars Sreibers, Brightwater Project Manager

## Slide 2: Brightwater Treatment Plant & Conveyance System

## Slide 3: Brightwater Treatment Plant – Dec. 2011

## Slide 4: Brightwater Accomplishments in 2011 Treatment Plant
  Spring – Start Up Planning and Staff Training
  May – Continuous 10-Day Clean Water Test
  September 6 – Wastewater Treatment Begins
  September 24 – Plant Grand Opening
  November 8 – First Biosolids Truck Loaded

## Slide 5: Brightwater Accomplishments Through 2011 - Conveyance System
  May 2009 – Marine Outfall completed
  April 2010 – West Tunnel (BT-4) mining completed
  July 2010 – East Tunnel (BT-1) completed
  August 2011 – Central Tunnel (BT-2) completed
  August 16, 2011 – Central Tunnel (BT-3C) mining completed
  September 6, 2011 – Influent Pump Station (IPS) begins pumping wastewater

## Slide 6: Tunnel Mining Completion – August 16, 2011

## Slide 7: Brightwater Tunnel from Treatment Plant to Point Wells

## Slide 8: Brightwater – Remaining Work
  Spring 2012 – Finish lining BT-3 and BT-4 tunnels
  Spring 2012 – Complete work on Influent Pump Station
  Summer 2012 – Complete tunnel/outfall connection, diffuser port opening and sampling facility at Point Wells
  September 2012 – Began conveying treated wastewater through conveyance tunnel and outfall
  2013 – Complete permanent odor control facilities at Ballinger and North Kenmore
  2013 – Restore Kenmore, Ballinger and Pt. Wells portal construction sites

## Slide 9: Brightwater Influent Pumping Station

## Slide 10: Questions?