# Facilities Management Division - Print Shop Operations

# Second Semi-Annual Operational Review

# December 31, 2008

# Background

On December 17, 2007 the Metropolitan King County Council passed Motion 12659. This motion acknowledged receipt of a revised King County Executive recommendation and a Transition Plan for county Printing and Graphics Arts operations (“Print Shop”), thus meeting the requirements of a budget proviso presented in the 2007 Budget Ordinance, Ordinance 15652 Section 106.

The Facilities Management Division (FMD) subsequently assumed control of Print Shop operations on January 2, 2008.  Upon taking on responsibility for the Print Shop, The FMD’s primary goal was to transition the Print Shop from what has frequently been a financially underperforming unit with chronic revenue problems into a viable in-house (in-plant) line of business.

# Transition Plan

FMD’s mandate from the County Council and the County Executive begins with the Transition Plan, originated by the Office of Information Resource Management (OIRM) in late 2007 as it prepared to hand off management responsibilities for the Print Shop to the FMD by year end. The Transition Plan had 6 key components:

- Reduce print shop expenditures

- Operate two downsized copy centers

- Decentralize graphics arts function

- Utilize brokers in the service ordering process

- Utilize a Transition Manager

- Perform Recurring Operational reviews

These components were to be implemented in a Print Shop reconfigured to comprise two downsized copy centers at King Street Center (KSC) and the new Chinook Building. Press printing at some reduced capacity was to be retained, but relocated from the Graybar building to the KSC site. Outside printing services would be used for larger and/or more complex printing jobs. As originally written, the Transition Plan provided for three full-time equivalent (FTE) positions. During the development of the budget, and as the plan was ultimately reviewed and approved by council, two additional press operator positions were added. This revised transition plan provided for a total of five full-time equivalent (FTE) positions to staff the two centers: two at each site, with one floating FTE to cover operations during employee breaks and time off, as well as to help meet peak production requirements. Two remaining graphics staff would transfer to the Department of Transportation (DOT), the largest consumer of such services in the county. Graphics users in other agencies could avail themselves of these DOT graphics staff on a fee-for-service basis.

The Plan provided for financing the two centers’ costs through a cost allocation methodology that assigned a share of center costs to each agency based on agency FTE/TLT counts rather than actual copy volume. The Department of Transportation and the Department of Natural Resources and Parks would share costs of the KSC site; other agencies in the Seattle downtown core would each pay a proportionate share of costs at the Chinook site.  Since the allocations were not dependent on copy volume, at any level below a certain number of copies, agencies would have an incentive to use Print Shop services rather than contracting directly with an outside commercial vendor.

The Plan envisioned an internal broker service within Finance and Business Operations Division (FBOD) Procurement. This service would distribute customer orders that are beyond the production capabilities of the Print Shop to outside vendors, based on needs, cost effectiveness, and resources.

The Plan provided for a Transition Manager, charged with the responsibility to oversee closure of the Graybar Building operations and transition to the new, two-center business model, make necessary leased equipment changes, and work with customer agencies during the transition period.  The manager would also be involved in periodic operational reviews of the Print Shop to be conducted by the Department of Executive Services (DES) every six months over a two-year period.

# Transition Plan Implementation

# Reduce Print Shop Expenditures by Downsizing Operations

The 2008 budget for the Print Shop was approximately $1.1 million and authorized 5 full time positions.  This budget eliminated three lines of business, photography services, multimedia services and graphic arts services as part of the Print Shop’s array of services.  This budget also assumed that operations would be discontinued at the Graybar Building.   As originally written, the Transition Plan assumed that there would be only three employees operating two copy centers.  Ultimately, and as reflected in the 2008 budget, the Transition Plan was effectively modified, through Council action, to provide for a continuation of press operations, utilizing two additional employees.

This budget, by design, did not provide for maintenance of the presses and peripheral equipment, did not provide staffing for production control, did not provide for future replacement of presses and related equipment, and did not provide for technology and business system investments.  It was assumed that these issues would be addressed as the budget for a transitioned print shop was formulated and proposed.

On a trial basis during development and testing of a new Print Shop business model, the 2009 Adopted Budget did provide sufficient funding resources to temporarily support two term limited positions.  One position supports customers requesting print jobs and serves as a broker for outsourced work.  The second position supports operations by providing pre-production graphics and working with customers on their graphic needs.  Both positions provide operating support by ordering paper products and supplies as requested by the digital and press operators.  The 2009 Adopted Budget also provides sufficient budget authority to pay sales and use taxes as required by state RCW’s.  Accordingly, the 2009 budget is slightly higher than 2008 at about $1.5 million.

Open a New, Downsized Copy Center in the Chinook Building and Continue the Copy Center at King Street Center

The rationale for this transition recommendation was sound.  The recommendation was based on the fact that a majority of current county copying needs are in the downtown core campus, that two locations would enable quicker turnaround and convenience on copy type jobs, particularly in the downtown core which carries highest demand for service.  Also related to this rational was that thought that such a move would enable the retention of some positions within similar classifications.

This recommendation, however, was based on an original assumption that the Print Shop would no longer provide offset printing services.  Continuing the press work does broaden the scope of services rendered by the Print Shop but increases the complexity of decisions about location.  Based on this and other significant factors, the Print Shop is now consolidated at the Graybar Building.

# Decentralize Graphic Arts Function

The Transition Plan calls for a decentralized graphic arts function by relocating graphics staff from centralized service model to departments who maintain high need/use of specialized graphic services.  Low use departments would use decentralized graphics staff on an as needed, charge back basis.

This provision of the Transition Plan has been fully implemented but not without a certain degree of uncertainty among customer agencies and labor issues surrounding the historic body of work that was performed by the Print Shop graphics staff.  An interim triage and referral function has been established at the Print Shop to assist customers receive graphic arts services and the Print Shop’s new pre-production graphics position will facilitate customer access to graphics services.

# Utilize Brokers in the Service Ordering Process

The Transition plan calls for establishing a broker function to handle customer orders for graphic design, printing, or copying services beyond the capability of the copy centers.  The brokers would determine the best way to fill orders based on service needs, cost effectiveness, and existing resources.  This was assumed to be a front end process where the brokers would:

- Receive customer orders.

- Determine best way to fulfill orders (copy center, vendor, or combination) based on service needs, cost effectiveness, and existing resources.

- Ensure fulfillment of orders and increased customer service.

- Accurately track service data and bill customers for services.

The assumption was that this brokerage function would be performed by FBOD Purchasing with no additional resources.

This transition element has proven problematic in that the scope of a necessary brokerage function as defined in the Transition Plan is beyond the capability and expertise of FBOD Purchasing and the Print Shop budget did not include any resources to perform this function.  A temporary funding remedy for this resource gap was provided for in the 2009 Adopted Budget.  The operations are being carried out in a “status quo” operating mode with temporary resources until a new business model can be formulated, tested and fully implemented.  Thus, Print Shop employees continue to perform a brokerage function for jobs that are not assigned in-house.  This portion of the Transition Plan is addressed through the proposed interlocal agreement with the State Printing Department.

# Charges for Services

The Transition Plan called for the transition manager to fully identify the procedures and guidelines related to operating the copy centers before opening the new copy center.  In addition, as part of implementing copy center services, communication with all existing or potential copy center customers will be performed, letting them know how to utilize the copy centers before the print shop has shut down and the new copy center is opened.

The FMD continues to work on customer relations and communications.  The FMD has also created a printing advisory committee designed to be a sounding board for upcoming policy decisions as the Print Shop is transitioned to a new business model and to inform customer agencies about various elements of the Print Shop’s lines of services.  The FMD has made a major update to the FMD intranet web site which discusses access to Print Shop services and other changes that have and will occur as we transition to a new way of doing business.

The Transition Plan further assumed that the transition manager would also finalize the “rate-card” to be utilized for all copy center services.

- A central services model will be utilized for funding.

- Fixed costs will be included as part of facilities costs to be spread across local tenants.

- Market rates will be utilized to determine the amount to charge for each service.

- Using the central services model with market rates is intended to encourage maximum usage of the copy centers by providing a competitive cost for each service provided and minimize work that is sent outside.

- Initial rates to be charged by the new copy center and used by the existing King Street copy center will be finalized by the transition manager.

- Brokers will be responsible for monitoring market rates and ensuring that internal rates are maintained at market rates.

- Recurring operational reviews will need to look at the full cost of service delivery in assessing financial viability of on-going operations.  The reviews will include all fixed as well as variable costs in assessing financial performance related to service delivery.

The implementation of the 2008 budget involved two features.  First, agencies were required to pay their allocated Print Shop costs regardless of the amount of work they send our way.  Agencies did receive a memorandum invoice (not a bill) showing a pricing of the work delivered by job up through the 3rd quarter.  Loss of one of the temporary support positions through the County’s layoff recall program made it difficult to price out the fourth quarter work and issue memorandum invoices.  This will be discussed later under barriers.

One of the basic assumptions in the Transition Plan was that, through cost cutting measures and strong management, the Print Shop can provide services whose price approximates market.  We have now visited a number of companies who provide printing and copying services.  Most were of the opinion that it will be a challenge to bring a small copy or print function’s pricing into alignment with private sector pricing, particularly one that is a union shop.  They reported that this industry is going through tremendous change which makes it more and more difficult to compete.

On the other hand, we visited with other companies that took a more positive view of the Print Shop’s opportunities.  They reported that through strategic decisions about equipment and business systems, an in-plant print shop such as the King County Print Shop can become successful, particularly if access to the services is made easy, status information is readily available, and quality products are provided.  It is true that in-plant facilities face significant challenges.  However, some industry analysts report that through online ordering/digital storefronts, digital color printing, shop management systems, and leveraging in domain expertise, these types of operations can prove successful.

The FMD intends to match State Printing Department pricing for its 2009 production.

# Transition Timeline

The original Transition Plan was quite aggressive as to timeline and was developed with two significant assumptions.  First, it was assumed that the revised business model would include a scope of services that did not include press work.  Secondly, it was assumed that the County Council would approve the Transition Plan by the end of September 2007.  Neither one of these assumptions held true.  There was a last minute decision to include presswork in the services provided and the Council did not approve the Transition Plan until late December.

Enclosed as Attachment A is a comparison of the original Transition Plan timeline compared to the projected timeline accompanying the first operational review (July 2008).  Attachment B is a current forecast timeline (March 2009) as compared to the projected timeline accompanying the first operational review.

The Transition to a new business model involving a strategic print partner has been delayed due to the length of time required to reach an interlocal agreement with the State Department of Printing.  As Council review and action on the interlocal is anticipated over the next month, we are currently estimating a delay of approximately six months as compared to our forecast timeline of July 2008.  Accordingly, once the interlocal is fully implemented, we will have a shortened period of time to propose a Print Shop budget for 2010 that reflects experience and expectations under the Print Shop’s new business model.

# Operational Results - The Second Half of 2008

There were a number work items necessary to effectively carry on operations after January 1st  2008, perform year-end close out procedures transitioning from OIRM to FMD, communicate to customers, deal with immediate equipment needs, and lay the framework for implementing a new business model.  These were successfully carried out and reported as part of the first operational review.

There have been a number of accomplishments as well for the second half of 2008:

# Finance and Business Operations:

- Refined interim procedures for budgeting, accounting, and billing.  Transitioned to a more centralized accounts payable and accounts receivable process.  Modified paper flow to increase efficiency and improved checks and balances.

- As part of the 2009 budget process, the FMD identified temporary staffing needs for 2009.  The delayed implementation of the desired business model and the strategic partnership with the State Printing Department has made it difficult to do a final assessment of long term staffing needs.    Staffing needs up until such time as the interlocal is in place have been established.  Pending implementation and testing of a new interlocal business model, there appears to be a need for additional staff resources to manage production, perform pre-production graphics, perform quality control, order paper and production supplies, process vendor payments, generate billings, generate production data, and provide production information as a source of billings.  Currently, two TLT positions are being funded on a temporary basis in the 2009 budget to cover these identified resource gaps and assist in converting to and testing a new business model.  It is assumed that the transition will occur by the end of 2009.  Currently, it appears that two permanent positions may be needed in a fully transitioned business model with one of those positions dedicated to production and one to customer relations and preservation of the interlocal agreement.

- Sustained significant backfill issues during extended vacations.  A single Print Shop location has facilitated backfilling and maintaining production.

- Formulated and implemented a process of paying bills related to outsourced work in a manner that is efficient and effective.

- Prepared to implement a job pricing and billing methodology so that customers will be billed only for printing and copying services.

- Tested various pricing methodologies and confirmed that, while the pricing will not match the most aggressive of the County’s outside vendors, it can be economically viable and match the pricing of the State Department of Printing.  The State Department of Printing pricing is designed to be near the mid point of market for each type of job.  The economic viability of this pricing strategy will be tested beginning January 1, 2009 as the Print Shop moves to a bill-by-job operation.

# Decentralized Graphic Arts Services:

- Worked with FBOD to initiate a series of graphic arts contracts available to all county agencies if those services could not be obtained through either the DOT or the DNRP.

- Hired a term limited pre-production graphics person to assist in coordinating the graphics needs of customers and facilitate production in both the press and digital areas.

Upgrade Print Shop Digital Printing Capacity and Reduce Production Costs:

- Placed new and upgraded digital equipment into production with a substantial savings in equipment leasing costs.

- Through minor investments and leasing, increased both the in-plant production capacity of the digital copiers and peripherals, presses, and bindery.

Maintained Production with Just a Slight Reduction in Production Levels:

- Maintained operations for both the copy centers and presses and, even with reduced authorized staffing levels, achieved production volumes at about 85 percent of historical production with some increase in outsourcing due to decreased production and bindery capacity.  During 2008 the Print Shop averaged nearly 1,000,000 impressions a month on its presses and over 700,000 impressions a month on its digital copiers.

- Began to aggressively use resources made available through the placement of “Light Duty” individuals who are recovering from surgery or injuries restricting their performance of normal job duties.  This has significantly enhanced bindery operations at no cost to the Print Shop.

- Continued to research the various barriers to providing quality cost effective print services.

Worked on Finalizing the Concept of a Strategic Partnership with the State Printing Department:

- Finalized negotiations with the State Printing Department and proposed an appropriate interlocal agreement for Council consideration.

- Met with the State Department of Printing to begin formulating steps necessary to implement the proposed interlocal agreement.

- Worked with the State Department of Printing and the Office of Information Resource Management to live test the possibility of the State Printing Department and the Print Shop handling the printing for the County’s computer center.

- Developed revised business plan and proposed a 2009 budget that assumes a strategic relationship with the State Printing Department.

# Positive Financial Results for 2008:

The financial results for 2008 were very encouraging.  Revenues were a few thousand dollars higher than budgeted because of outside revenue sources such as print work done for City of Seattle agencies.  Actual expenditures were $50,000 over budget caused by non-budgeted sales tax expenses of just over $73,000.  This condition was anticipated and reported in the first half operational review.  Discounting unbudgeted sales taxes, expenditures were below budget by about $23,000. The 2009 budget does account for the County’s sales tax obligations related to print production and the fact that the County is subject to sales tax for print work done on behalf of County agencies continues to be identified as a barrier to successful Print Shop operations.

The $50,000 operating deficit caused by unbudgeted sales taxes has been absorbed within the FMD internal service fund’s fund balance.

The current goal is to sustain an economically viable in-plant print shop even without a strategic print partner.  This is not the best of circumstances from the perspective of delivering effective print services because the Print Shop does not have the customer service network in place for larger operations like the State Printing Department has developed.  However, entering into a strategic print partnership will then be “icing on the cake” from the perspective of improved service delivery and increased cost effectiveness.

# Considerations Related to a New Business Model

The Print Shop has faced a number of barriers to operating an economically viable in-plant printing function.  Yet, we believe that if we achieve the volumes assumed in our 2009 budget, we will be very close to achieving self-sufficiency.  If given the ability to leverage a strategic print partnership with the State Printing Department, we will only become more cost effective and responsive to our current customers.  In addition, such a partnership will provide an enhanced ability to expand our customer base and attract new orders within the Seattle Metropolitan area.  Still, it will be necessary to aggressively pursue mitigating action to reduce the negative impact these barriers described below have on economic viability for the Print Shop.  Following is a list of those barriers and recommended mitigating action for those barriers under our control.

| Barrier | Mitigation Steps |
| --- | --- |
| The Print Shop does not run multiple shifts as do most high volume private sector companies. These companies run their machines to maximum capacity with a maximum number of running hours. | The Print Shop has new leased digital equipment that has sufficient capacity to cover increased production levels. The recent decision to, over the mid-term, locate all production activity at a single location makes it possible to go to 1½ shifts without increasing staff. The machinery could also support a two shift operation if production volumes warrant it. |
| The budget for the Print Shop is encumbered with central overhead and other internal service charges that are substantially higher than general administrative costs of a private sector company. | Unfortunately, this is a given for the County’s internal service funds. We will be on the lookout for ways to reduce internal service rates. However, the potential for a material change is small. |
| The Print Shop is not budgeted and staffed to perform manual folding and bindery tasks. | The new digital copiers recently installed at the Print Shop have increased bindery, merging, and folding capacity that significantly cuts down on manual bindery work. Recent use of “light duty” staff has enhanced bindery capacity. |
| The FBOD has, through competitive bidding, created external print contracts for individual County agencies that sometimes allow those agencies to directly outsource print products. This, in turn, makes it very difficult to manage print production and assist agencies with their print products. The higher the volume, the more competitive product pricing can become. | The proposed legislative package places the Department of Executive Services as the central focus of print products thereby empowering a more controlled environment for print products. |
| Many private sector companies are non-union. A union representative stated that union copy machine operators make 30 percent more than non-union employees and union press operators make 40 percent more than non-union employees. Furthermore, the county fringe benefit package provides substantially more benefits with higher costs than non-union shops. | The fact that the Print Shop is a union shop provides good family wage jobs for its staff and an opportunity to deal with the union on any performance issues. Fortunately, the five remaining production staff of the Print Shop are highly experienced and motivated to make this in-plant print service successful. FMD has established the goal of matching the print pricing structure of the State Printing Department, the proposed strategic partner and another union shop. |
| The budget for the Print Shop is encumbered with a sales tax requirement even though most of the services rendered are for other county agencies. | The County does not enjoy the same tax exemption as does the State Department of Printing when jobs are done for State agencies. This obligation costs the county up to $100,000 in sales tax a year. We have asked that the county’s upcoming legislative package include provision for sales tax exemptions for municipal print shops when they are functioning as an internal service fund. Unfortunately, this was not the year to seek initiatives reducing State revenues and the proposal did not get included in the County’s legislative agenda. |
| The Print Shop is hampered by outdated machinery, particularly pre-press machinery. This issue was highlighted by the Washington State Printing Department when they assessed the status of the King County Print Shop. | The digital copiers have been upgraded with an actual annual savings of over $100,000 when compared to the rental costs of the old outdated machinery. At the same time, the production systems and bindery capacity associated with the new equipment was also upgraded. Finally, the Print Shop is exploring new “green” plate making machinery which would replace outdated and uneconomical machinery. |
| The 2008 Budget did not provide any resources for production control or other fiscal duties. | While the FMD Director’s Office can provide fiscal and accounting support to the Print Shop, there are numerous support duties necessary to be successful as an in-plant printing service. It is necessary to have on-site support to deal with customer orders and pre-production graphics, job costing, pricing, billings, and customer relations. Pending successfully implementation and testing of an interlocal business model, the staff shortfall is estimated at 2.0 FTE’s. As an interim measure, the 2009 Adopted Budget did provide funding for two term limited staff to mitigate this shortfall. Another mitigating action for 2009 and beyond will be to leverage the production control capacity of a strategic print partner. This action is described below. |
| The Print Shop is hampered by a total lack of automated business systems commonly used in the print industry. | The new digital equipment recently leased by the Print Shop has software that controls digital print production and costs out jobs that are run on the machinery. Unfortunately, there have been insufficient resources available to implement these features. The ultimate solution will be to use the business systems in place at a strategic print partner. This is described below. |
| The current delay in implementing a new business model has resulted in term-limited support positions. | The Print Shop currently lost an experienced staff person occupying one of the term limited positions because he was placed in a permanent position through the Layoff Recall Program. This was disruptive to operations. The continuing uncertainty regarding continuing operations places undue pressure on the remaining staff to find positions elsewhere. Considering the limited number of staff, any loss of staff because of uncertainty is disruptive to operations already thinly staffed. |

# Thoughts About the Strategic Print Partnership

Generally speaking, we would look for a print operation with the following features:

- On-Line Ordering, Immediate Pricing, and Accessible Status Reporting

  - Training

  - Marketing Available Services

- Use of On-Line Templates for Business Cards, Awards, and Other Standard Print Jobs

- Cost Effective Print Production and Competitive Pricing

- Automated and Expanded Bindery Services

- Seamless Services In-House Versus Use of Outside Vendors

- Effective Quality Control and Delivery

- Timely Billing

Considering the lack of staff resources and business systems at the Print Shop, the primary option available to the county is to engage a strategic print partner.  This would enable the county to leverage that partner’s business systems, expertise, and resources to the advantage of the Print Shop’s customers and management.  That is why the FMD has proposed a strategic partnership with the State Printing Department.

This strategic partnership will provide the capacity to move to a more businesslike form of managing and billing print jobs as well as making provision for effective customer support.

.

The proposed partnership with the State Printing Department will allow FMD to leverage existing production and finance functions necessary for a successful print operation.  This business model relies on a strategic relationship with an entity that is a relatively large print provider.  This is not a true partnership in the legal sense.  Rather, this type of relationship features opportunities to:

- Use the print partner’s ordering system and production control systems.

- Use the print partner’s staff resources to carry out functions not currently provided for in the 2009 budget by augmenting customer services and expanding print services available to County agencies.

- Use of the print partner’s expertise in assisting agencies in selecting the most cost effective print products.

- Use of the print partner’s plant capacity to carry out printing, mailing, and fulfillment services that cannot be produced by the Print Shop.

- Use of the print partner’s strategic vendor relationships to produce print products currently beyond the capability of either the Print Shop or the print provider to produce.

- Use of the print partner’s expertise to appropriately price products, stage production, and improve production practices.

The State Department of Printing (PRT) has proposed a strategic relationship with the county that serves both governments well.  We now have an opportunity to forge a unique relationship with this State Agency that will be a “win-win” for both.  This relationship can be held out as a good example of how governments, through cooperation and collaboration, can function in an efficient and cost effective manner.  We have been advised by the Prosecuting Attorney’s Office that the appropriate legal vehicle to formalize such a relationship is through an interlocal agreement approved by the County Council and appropriate State officials.

With this in mind, the FMD has negotiated both the business points and general conditions of a proposed interlocal agreement (Agreement) which would provide the legal framework to proceed with this strategic relationship.  This agreement has the following features:

- Establishes the PRT as a preferred provider of print goods and services to county agencies except for those jobs to be completed by the FMD Print Shop or as so directed by FMD.

- Establishes the FMD Print Shop as a preferred provider of print goods and services for State and local agency job requests placed directly with the PRT that they would not normally fulfill themselves.

- Allows the FMD Print Shop to order materials and supplies through the PRT procurement network where volume leveraged purchases would result in costs lower than the Print Shops normal supply channels.

- Allows County agencies to use the PRT’s ordering systems currently in place and to use the PRT’s paperless all-inclusive ordering system currently under development.  Estimated delivery of the new system is the 1st Quarter of 2009.

- Calls for the PRT to provide customer training on their new system, their products and services, and to provide advisory services assisting customers make the most cost effective decisions about their needed print products and services.

We continue to await the County Council’s review and hopefully approval of this strategic relationship.  The goal would be to get approval and implement this partnership no later than June 30, 2009.