Potential Next Steps for Independent KCTD to Implement Roads Funding Measure

| Timeframe | Entity | Action |
| --- | --- | --- |
| Prior to April 17, 2026 | KCTD | Approve Resolution imposing 0.1% sales tax for Roads KCTD passes Resolution TD2026-01, which imposes a 0.1% councilmanic sales tax for roads funding needs |
| April 17, 2026 | KCTD | Inform WA Department of Revenue (DOR) For sales tax collections to begin July 1, 2026, KCTD must inform WA DOR by April 17, 2026 |
| April – June 2026 | KCTD | Approve Resolution requesting Executive to develop Implementation Plan KCTD passes second Resolution asking King County Executive to develop an Implementation Plan to use the revenues from Resolution TD2026-01, including: - Proposed Interlocal Agreement (ILA) between KCTD and King County for use of the revenues - Work plan with projects and proposed budget for 2026-2027 biennium - Proposed process to develop a work plan and budget for future biennia - Proposed accountability metrics - Proposal for regular review by King County Council and KCTD Board If KCTD intends for King County Roads to be able to expend revenues prior to the approval of an implementation plan and ILA, the Resolution would need to grant authority for KCTD to contract with King County to spend a specified amount during this time. |
| April – June 2026 | KCTD | Execute administrative agreements to receive revenues KCTD would need to sign a Cash Management and optionally an Investment Pool agreement with King County so Treasury can accept their tax revenues RCW 36.73.020 requires KCTD to use King County as ex officio Treasurer absent an interlocal agreement contracting with another government for this function NOTE: If collections begin July 1, KCTD would begin receiving revenues from DOR in late September (two months after end of first month of collections) |
| April – June 2026 | KC Executive KC Council KCTD | Create new King County fund(s) for KCTD revenues Executive transmits ordinance creating new RSD KCTD Fund for revenues (potentially a Subfund within the Roads Fund) KCTD would also need to create a special District Fund as part of the Cash Management agreement with Treasury for tax collections |
| April – June 2026 | KC Executive KC Council | Request additional appropriation authority for Roads Appropriate sales tax revenues in budget omnibus Executive requests and Council approves appropriation authority for the estimated revenues to be received due to Resolution TD-2026-01 through the end of the 2026-2027 biennium, with provisos or expenditure restrictions to: - Appropriate the revenues needed for administrative purposes (DOR, KC Treasury, PAO, Council staff, etc.) under existing KCTD-KC ILA (TD2014-04) - Appropriate revenues as desired for initial Roads work prior to adoption of Implementation Plan and ILA - Encumber remaining revenues until Implementation Plan and ILA are approved by Council and KCTD |
| June – September 2026 | KC Executive | Develop Implementation Plan and ILA King County Executive develops a proposed Implementation Plan and ILA, including a project proposal for 2026-2027 |
| July – December 2026 | KC Executive | Possibly begin work using sales tax revenues KC Roads begins work using the sales tax revenues under the conditions approved by the KCTD Resolution and budget ordinance |
| September 2026 | KC Executive | Transmit Implementation Plan to KCTD and Council The Executive transmits an Implementation Plan, including a proposed ILA between King County and the KCTD, to the Council and KCTD NOTE: Existing ILA (TD2014-04) authorizing County staff to do “startup” work expires upon the KCTD receiving any authorized revenues (DOR sales tax collections estimated to begin July 1, 2026, if Resolution TD2026-01 approved by April 17 deadline) |
| September – November 2026 | KC Council KCTD | Review and approve Implementation Plan and ILA KC Council and KCTD each review the proposed implementation plan and ILA - Council must pass the implementation plan and ILA by Ordinance - KCTD must pass the implementation plan and ILA by Resolution |
| January 2027 – June 2036 | KC Executive | Continue work using sales tax revenues, report as required KC Roads continues to use the sales tax revenues for projects as allowed by KCTD Resolution, implementation plan, and ILA, reports to Council and KCTD as required |

King County is authorized to assume the KCTD under RCW 36.74. The next steps shown on this timeline, however, are based on the KCTD remaining an independent entity

Procedures from Office of the Washington State Auditor, Transportation Benefit Districts, Accounting (link)