Metropolitan King County Council

Budget & Fiscal Management Committee

| Agenda Item No.: | 2 |  | Date: | August 20, 2003 |
| --- | --- | --- | --- | --- |
| Proposed No.: | 2003-0273 |  | Prepared By: | David Layton |

STAFF REPORT

SUBJECT:	This Proposed Ordinance will appropriate $12.5 million from a previous bond sale to support continuation of the Harborview Bond Program through December 2004.  Additionally this staff report includes discussion of a proposal for a $29 million increase in scope to the Harborview Bond Program Plan.

BACKGROUND:

The last BFM Committee briefing on the $263 million Harborview Bond Program occurred on July 16, 2003.  Additionally the briefing included a threshold briefing on a proposal by Harborview for a $20 million increase in scope to the Harborview Bond Program.  The BFM Committee provided direction to the King County Bond Oversight Committee representative.

SUPPLEMENTAL APPROPRIATION:

Transmittal of the proposed supplemental appropriation in June of this year is consistent with the funding schedule discussed at the BFM Committee briefing on April 2, 2003.  The supplemental appropriation amount of $12.5 million is intended to cover all Harborview Bond Program costs project through December 2004.  The current supplemental appropriation request in Proposed Ordinance 2003-0273 includes the following elements:

Independent Monitoring Consultant				$     150,000

Project No.1 – 9th & Jefferson Building (NJB)		$  4,676,000

Project No.2 – Inpatient Expansion Building (IEB)		$  7,265,000

Project No.3 – Demolition					$     454,000

Subtotal Current Supplemental Request		$12,545,000

Prior appropriations:						$12,598,576

Current Supplemental Appropriation Request:		$12,545,000

Subtotal All Appropriations				$25,143,576

Net 1st Bond Sale Proceeds:					$28,742,155

Total Appropriations (including proposed)			$25,143,576

Net Remaining 1st Sale Proceeds:			$  3,598,579

The current supplemental appropriation request totals for each of the subprojects are consistent with the monthly project cash flow projections as provided by the UW project manager and are within the approved project budgets.

A table summarizing the above including project cost categories, appropriations to date, current supplemental appropriation request, project savings reserves and total project budgets is included in Attachment #8.  Additionally the table summarizes the total 1st bond sale net proceeds total and remaining 1st bond sale proceeds and interest earnings.

Reasonableness:  								Ready for Action

Based upon this analysis, passage of Proposed Ordinance 2000-0273 is consistent with the approved program plan, cash flow projections and proposed funding schedule and constitutes a reasonable business decision.  This legislation is ready for action today.

Fiscal Note:  Per King County Code 4.04.075, a fiscal note outlining the fiscal impact of this legislation is required and is included in Attachment #6.

Proposed Striking Amendment:

A proposed Striking Amendment S1 (Attachment #1) and Title Amendment T1 (Attachment #3) are provided that includes a $240,000 increase to the proposed supplemental appropriation request to reflect final negotiations for the housing mitigation discussed at the July 16th briefing.  The change will revise internal budget line items in the approved program plan.  Funding to support the housing mitigation change is proposed to come from project reserve accounts and will not increase the overall approved budget.  A revised financial plan highlighting the allocations of the housing mitigation is shown in Attachment #9.

A revised Fiscal Note incorporating the housing mitigation change noted above is included in Attachment #7.

PROJECT STATUS & PROPOSED ADDITIONAL SCOPE:

A copy of the July 2003 Monthly report is included in the staff report as Attachment #10.

SCOPE:

The project scope has remained unchanged since approval of the Initial Program Plan in April 2003.  A proposal to add additional scope is discussed in a separate section of the staff report.

SCHEDULE:

The project is currently on schedule. The Schematic Design was completed on August 4, 2003 approximately one month early. The Schematic Design submittal review and A/E response resolution process is underway and is scheduled for completion on September 3, 2003.  A copy of the current project schedule is included within the July Monthly Report (Attachment #10).

BUDGET:

The project elements are currently within the approved project budgets.  A second and final bond sale is scheduled for March 2004.

PROPOSED ADDITIONAL SCOPE:

The Committee is being asked to consider the merits of the following proposed additional scope increases and consider a Motion to approve a revised Program Plan.

The proposed scope of work increase was first presented to the BFM Committee on July 16, 2003 and is summarized as follows:

- The addition of one floor of parking for 150 vehicles to be constructed below the lowest current designed parking levels of the Ninth & Jefferson Building (NJB)

Estimated cost $6 million.

- The addition of two “shelled” floors above the current approved program plan for the NJB

Estimated cost $14 million.

- Tenant Improvements to fit out the two “shelled” floors of the NJB noted above.

Estimated cost $9 million.  The Tenant Improvement component was not included in the proposed additional scope reviewed at the July 16, 2003 briefing. However, during the July 16, 2003 briefing the committee requested that analysis of the tenant improvement work be considered as part of the proposed additional scope in order to eliminate the need for additional legislation in the future.

A summary narrative of the proposed changes to the Ninth and Jefferson Building for the above additional scope is included in Attachment #11.  The narrative includes summary background information and cost recovery strategies.  Additionally, a Revised Bond Program Plan summary document dated August 2003 incorporating the proposed additional scope is provided in Attachment #12.  This document is similar to the April 2003 approved Initial Program Plan document except that it is revised to include the proposed additional scope.  If approved, this proposed addition will increase the Harborview Bond Program budget to $292,800,000.

Council Authorization Required:  The proposed additional scope increase represents a $29 million increase to the approved program budget.  Ordinance 14295 adopted the Bond Project Management Agreement and established the Bond Oversight Committee.  This Ordinance requires council authorization by Motion before the county’s BOC representative can vote to approve changes to scope, schedule or budget that exceed the following thresholds:

- Single change order exceeding one million dollars

- Overall increases in the approved project budget

Scope Changes: Section 4.5.3 of the Management Agreement states the following:

Scope changes to the Approved HMC Project Budget or Approved Project Budgets contained therein, may be recommended to the Oversight Committee to be funded by HMC upon approval of Board.  The Oversight Committee shall approve such Board requested scope changes, funded by HMC, provided the change facilitates the operation of the medical center and any cost, scope or schedule impacts to other aspects of the HMC Project or portions of same or on HMC’s long term capital project budget are adequately addressed by the HMC funding, or otherwise.  Such approval shall not be unreasonably withheld.

Revenues to support the proposed additional scope are to originate from newly identified revenue sources, and are not intended to increase King County’s risk beyond its current Bond Program obligations.  Further development of the proposal has continued following the July 16, 2003 BFM Committee meeting particularly with regard to revenue commitments and the facilities use and reimbursement agreement between the University of Washington and Harborview.

Parking Cost Recovery Strategy:  Cost recovery strategy for the proposed additional parking is intended to come from increased parking revenues.  According to HMC staff the additional parking spaces will help Harborview offset a Major Institution Master Plan (MIMP) requirement for 500 additional parking spaces by 2010 and allow Harborview to eliminate its current off-site leasing of parking spaces.  The demand for parking at Harborview is high and currently 400 Harborview staff are on a waiting list for a parking space.  The parking revenue analysis is based on increasing parking rates over time to align with market rates.

Shelled Floors and Tenant Improvement Cost Recovery Strategy:  Cost recovery for the proposed shelled floors is based on identification of a new revenue source associated with University of Washington research Facility Indirect Cost Recovery (ICRs).  Facility indirects generated by research at Harborview are estimated at $2.3 million per year and are expected to increase as space analysis continues to be refined and as research space is expanded.  The calculation of $2.3 million per year space utilization reimbursement to Harborview is based on existing research space utilized by the University at Harborview (approximately 57,000 sf) and does not include the proposed increase of research space proposed by this addition (approximately 50,000 sf).  The estimated $2.3 million reimbursement from the University appears adequate to cover both the debt service for the $14 million for the shelled floors as well as the $9 million Tenant Improvement (TI) project.

University of Washington Commitment:  As of the date of preparation of this staff report the University of Washington and Harborview have not executed a new Facilities Use and Reimbursement Agreement. However, negotiations have been very active over the last two weeks and aside from a few minor points agreement appears imminent.  This legally binding agreement replaces the existing University/Harborview occupancy Memorandum of Understanding (MOU) and will be used as the mechanism to ensure that space utilization reimbursements ($2.3 million per year) will continue to pass to Harborview through June 2015.  The term of the agreement corresponds to expiration of the current management agreement.  The University has agreed to ensure continuous occupancy of the space through the term of the agreement either directly by the University or through appropriate subtenants.  Additional space and reimbursement may be negotiated in the future as demand and supply increases.  A copy of the Facilities Use and Reimbursement Agreement is included in Attachment #13.

Harborview’s Debt Service Commitment:  David McDonald, President of the Board of Trustees, in a letter to Executive Sims and Councilmember Phillips, on July 14, 2003 emphasized the Board of Trustees commitment to the proposed additional scope and would direct management to begin to set-aside the $2.3 million in annual payments beginning in 2003 to service the debt for costs associated with the additional scope (Attachment #14).  It is anticipated that the Harborview Board of Trustees, Executive Committee will meet on Wednesday August 20th to affirm the board’s debt service commitment possibly via a resolution or other document.  The full Board of Trustees is not scheduled to meet until August 28th.  It is not clear if the Executive Committee has the legal authority to formally act on behalf of the board.

BFM Committee staff met with Harborview staff on August 12th to review Harborview’s financial status and to assess its ability to absorb this level of commitment without impacting its mission.  It appears that Harborview has more than enough resources to make this level of financial commitment.  A summary of Harborview’s current financial status, and prioritized strategy for servicing the debt for the proposed additional scope in the event the committed funds from the University were reduced or no longer available is provided in Attachment #15.  A copy of the 2003 Harborview audit has been requested and upon receipt additional copies will be made available to committee members upon request.

Bond Financing Strategy:

The current proposed financing strategy to service the debt for the proposed additional scope is to use the voter approved bonds for construction of NJB and the IEB while Harborview sets aside $2.3 million per year in a reserve account until permanent financing is needed in January 2008.  Under this scenario the reserve account will be allowed to build up to approximately $10.8 million which will reduce borrowing to $14 million.  Debt service on the remaining balance will continue to be financed by the $2.3 million annual set-aside until the balance is retired in mid-2008.  The mid-2008 debt retirement closely corresponds to the expiration of the current Harborview management agreement.

Bond Counsel Review:

The county’s bond counsel has been apprised of the proposed additional scope and reimbursement strategies.  Discussions between the Prosecuting Attorneys Office (PAO) and the county’s bond counsel identified no adverse impacts to the voter approved bonds.  Bond counsel representatives are present today and are available to respond to committee questions.

PROPOSED SCHEDULE:

The proposed additional scope will delay the start of construction for the Ninth & Jefferson Building (NJB) by 4 months.  Completion will be 11 months later than previously planned.  The start of construction of the Inpatient Expansion Building will be accelerated by 5 months.  Completion of the IEB will be 3 months earlier than previously planned.  The overall bond program schedule will be extended by one month.  A copy of the proposed schedule is shown in Attachment #16.

Independent Project Monitoring Consultant Review:  The project monitoring consultant (Vanir) reviewed the proposed scope increase including the costs and financing assumptions and provided a report as part of the July 16, 2003 committee briefing.  The Vanir report was amended on August 12, 2003 to include a review of the $9 million proposed Tenant Improvement Project requested by the BFM Committee.  A copy of Vanir’s report is included in Attachment #17.  Vanir’s Project Manager is available to provide a summary of the report and to respond to member questions.

Reasonableness 								Ready for Action

Approval of proposed Striking Amendment S2 (Attachment #1) will provide appropriation authority and direction for the county’s Bond Oversight Committee representative to begin design work on the $29 million proposed additional scope however, appropriation of additional funding is not required at this time.  Appropriation of the $29 million is anticipated concurrent with transmittal of the 2004 proposed budget.  The proposed additional scope appears to be a reasonable business decision based on the following:

- The University of Washington and Harborview have entered into a legally binding agreement for space utilization reimbursements sufficient to cover the debt service.

- Harborview Board of Trustees has formally made the financial commitments to ensure repayment of the bonds without the use of general county revenues.

- The UW/HMC agreement has received King County PAO and Council’s legal counsel review.

- The proposed scope has been favorably reviewed by the county’s independent monitoring consultant.

- Bond counsel review of the proposal has not identified any fatal flaws in the plan.  However, regardless of the commitment from Harborview and the legal agreement between Harborview and the University, it is the county’s full faith and credit that is on the line.

- Striking Amendment S2 will provide appropriation authority and direction for the county’s Bond Oversight Committee representative for the $29 million proposed additional scope but this amendment does not appropriate additional funding at this time.

Striking Amendment S2 is ready for action today subject to receipt of:

- Executed Facilities Use and Reimbursement Agreement and

- Harborview Board of Trustees financial commitment or,

- Delivery schedule of items #1 and #2 above as may be acceptable to the council

INVITED:

- Calvin Hoggard, King County Representative, Bond Oversight Committee

- Kathy Brown, DES, Director, Facilities Management Division

- Tom Kuffel, PAO Deputy Director

- Elise Chayet, Director Planning & Regulatory Affairs, Harborview Medical Center

- Troy Pyles, Vanir Construction Management Inc., Project Monitoring Consultant

- Jim Hattori, King County Financial Advisor

ATTACHMENTS:

- Striking Amendment S1

- Striking Amendment S2

- Title amendment T1

- Proposed Ordinance 2003-0273

- Transmittal Letter, dated June 6, 2003

- Fiscal Note

- Fiscal Note (revised to include housing amendment)

- Appropriations Table

- Revised Financial Plan

- Monthly Report July 2003

- Summary Narrative of Proposed Scope Increase dated August 20, 2003

- Harborview Bond Program Plan (Revised, August 2003)

- University of Washington/Harborview Facilities Use and Reimbursement Agreement (non-executed draft).

- Harborview Letter, dated July 14, 2003

- Harborview Financial Summary

- Project Schedule

- Oversight Monitoring Consultant Report Amendment August 12, 2003