ATTACHMENT A  July 22, 2004

| Work Plan Elements | Target Completion Dates (quarters) |
| --- | --- |
|  | 2004 | 2005 | 2006 |
| Leadership, Management, Organizational Structure | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Formalize crisis communications plan |  | X |  |  |  |  |  |  |  |  |
| Assess staff training needs, establish training matrix |  |  | X |  |  |  |  |  |  |  |
| Update procedure documentation |  |  | X | X | X | X |  |  |  |  |
| Establish performance benchmarking for voter registration & absentee ballot processing |  |  | X |  |  |  |  |  |  |  |
| Involve elections office in best management practices at regional, state & national level | O | O | O | O | O | O | O | O | O | O |
| Develop and adopt a Mission statement, Goals and Objectives | X |  |  |  |  |  |  |  |  |  |
| Develop performance measures emphasizing core business outcomes, efficiency, benchmarks and reporting to the public | X |  |  |  |  |  |  |  |  |  |
| For the new Election Management Voter Registration System: |  |  |  |  |  |  |  |  |  |  |
| Monitor each milestone contained in the vendor contract | X | X |  |  |  |  |  |  |  |  |
| Identify performance measures and establish performance benchmarks for each functional area of the system |  | X | X |  |  |  |  |  |  |  |
| Identify baseline information for each performance measure from the previous year |  | X |  |  |  |  |  |  |  |  |
| Develop and implement a plan to maximize available features of the system and that demonstrate measurable improvements in efficiency and streamlining of the business model |  |  | X |  |  |  |  |  |  |  |
| Public Confidence, Voter Outreach and Public Education |  |  |  |  |  |  |  |  |  |  |
| Demonstrate capacity to conduct elections entirely by mail |  |  |  | X |  |  |  |  |  |  |
| Expand use and development of the local Voters’ Pamphlet |  | X |  |  |  |  |  |  |  |  |
| Examine options for expanding public testing and auditing |  | X | X |  |  |  |  |  |  |  |
| Enhance and expand web-based information and services | O | O | O | O | O | O | O | O | O | O |
| Maintain active involvement in community outreach and voter registration | O | O | O | O | O | O | O | O | O | O |
| Facilities/Infrastructure and Security |  |  |  |  |  |  |  |  |  |  |
| Implement revised Information Technology support model |  |  | X |  |  |  |  |  |  |  |
| Consolidate Election Distribution Center and Mail Ballot Operations Satellite facilities |  |  |  |  |  |  |  |  |  | X |
| Update and formalize emergency preparedness procedures |  |  | X |  |  |  |  |  |  |  |
| Implement the federal Help America Vote Act disability requirements |  |  |  |  |  |  | X |  |  |  |
| Adopt and formalize security plans and protocols |  | X | X | O | O | O | O | O | O | O |
| Conduct an assessment and analysis on the impacts of reducing the number of precincts and polling places |  |  |  |  | X |  |  |  |  |  |

\

X indicates the target year and quarter completion date.  O indicates an ongoing or continuous activity.