Solid Waste Construction Capital Fund

Analyst: Terra Rose

|  |  | 2023-2024 Proposed |  | 2025-2026 Projected |  | 2027-2028 Projected |
| --- | --- | --- | --- | --- | --- | --- |
| Revenues |  | $176,013,913 |  | $50,416,994 |  | $123,753,074 |
| Expenditures |  | $176,013,913 |  | $50,416,994 |  | $123,753,074 |
| Major Revenue Sources: Bond proceeds, transfer from solid waste operating fund (disposal fees) |

Description

The Solid Waste Capital Improvement Program is comprised of three funds: the Solid Waste Construction fund, the Capital Equipment Recovery fund, and the Landfill Reserve fund. The Solid Waste Construction fund, which is the subject of this staff report, is used to finance the new construction and major maintenance of division transfer facilities and some closed landfill projects. Projects in this fund are financed through bond proceeds and transfers of disposal fee revenue from the Solid Waste Operating fund.

Summary of Proposed Budget and Changes

The proposed budget would appropriate approximately $176.0 million for projects related to recycling and transfer stations, projects at the closed landfills under the custodial care of the County, and new projects related to electrification and a co-digestion pre-processing facility. This is an increase of approximately $77.6 million relative to the 2021-2022 adopted budget.  Proposed expenditures worth note are described below.

South County Recycling and Transfer Station (SCRTS): $75.6M. This previously approved project will, when complete, replace the 1960s-era Algona Transfer Station with a new transfer station expected to offer new recycling services and waste compaction to reduce hauling trips, and to be enclosed to contain noise, odor, and dust. This project is consistent with the direction in the Comprehensive Solid Waste Management Plan.

According to budget materials, this appropriation would support the project through construction and project close-out, which is delayed by approximately two years and is now expected to open in 2026. The new estimate at completion has increased from $144.0 million estimated in the 2021-2022 budget materials to approximately $201.0 million. Executive staff attribute the increase in costs to several sources: COVID-19 impacts, higher salaries, and supply chain issues ($4M); inflation ($7M); additional project elements identified moving from 60 percent to 90 percent design ($25M); extended construction duration ($10M); higher contractor mark-ups ($10M); and increases in art and ESJ contributions ($2.5M).

Northeast Recycling and Transfer Station (NERTS): $7.7M This previously approved project would construct a new recycling and transfer station in Northeast King County at a site to be determined to replace the 1960s-era Houghton Transfer Station located in Kirkland, consistent with the direction in the adopted Comprehensive Solid Waste Management Plan. The new station is expected to offer additional recycling services, waste compaction, and be enclosed to contain noise, odor, and dust.

Budget materials indicate that this appropriation would support the planning and preliminary design phases of the project. SWD engaged in a siting review process with cities and community representatives and have narrowed the potential sites to two in Kirkland and one in Woodinville. Executive staff stated earlier this year that they expect to issue the final Environmental Impact Statement (EIS) and site selection by mid-2024. The station is anticipated to be complete and open in 2029. The estimated total cost at completion is approximately $178.9 million.

Cedar Hills Regional Landfill Facilities Relocation: $31.8M. This previously approved project would relocate existing administrative and maintenance facilities that are in the southeast portion of the Cedar Hills landfill to develop new disposal capacity. Budget materials indicate that some facilities will be moved to another location within the Cedar Hills boundary, such as in the buffer, and others will be moved offsite. The Final EIS for landfill development was issued in March 2022 with three facility relocation alternatives that are currently being evaluated.

This appropriation would support final design of the permanent facilities and the beginning of the implementation phase. Executive staff indicate that SWD is moving forward with designing a permanent facility in the southern buffer of the landfill. For this to occur, it is anticipated a Special Use Permit will be needed, with action by the Hearing Examiner and Council estimated in late 2023 and early 2024. Executive staff also note that staff are expected to be relocated to interim facilities during construction of the permanent facilities beginning in 2023, and budget materials indicate that they may be in these interim facilities for up to five years.

The estimated total cost at completion of the permanent facilities provided in the budget materials is approximately $96.7 million. However, Executive staff noted during deliberations on the solid waste fee ordinance earlier this year that the actual costs for this project will potentially be higher when more accurate estimates are available at 30 percent design.

On September 23, 2022, the King County Auditor issued a management letter that indicated that "Increased risk, cost, and potential for service disruptions are likely with King County Solid Waste Division's (SWD) permanent support facilities project at the Cedar Hills Regional Landfill." The letter goes on to note that SWD is unlikely to deliver the permanent support facilities on the current schedule, and delays may increase project costs and could cause disruptions to waste disposal. Among other issues, the letter cites staffing challenges and notes that as of July 2022, nearly half of the positions within SWD's Project Management Office, which is responsible for managing capital projects, are vacant. According to Executive staff, if permanent facilities are not constructed in time, lease extensions at the one rental interim facility may be needed and employees at other county-owned interim facilities may also need to stay at those locations longer. Executive staff indicate that plans for what to do if Area 9 is not complete by the time other areas are filled are ongoing.

The letter makes eight recommendations that the Auditor says are to address unresolved challenges and improve transparency of the project schedule and costs. SWD concurred with all eight recommendations in their agency response.

Electric Vehicle Infrastructure: $9.0M Executive staff indicate that this appropriation is for a new project that would do two things: (1) develop an electrification infrastructure plan that would cover the full transition to electrification for SWD in the coming biennia; and (2) design and construct the infrastructure necessary for electrification of the Division's transfer of waste from the transfer stations to the landfill by Class 8 tractors (e.g., capital improvements to increase electric power load). Budget materials indicate that vehicle electrification will help meet the goal in the Strategic Climate Action Plan for the Division to be carbon neutral by 2025 by eliminating approximately 11,000 MTCO2e.

According to Executive staff, the replacement of Class 8 vehicles is not included in this appropriation, nor is the design and construction of infrastructure to support fleet vehicle electrification. No additional appropriations for this scope of work are expected according to budget materials.

Maintenance and Monitoring Projects for Closed Landfills: $21.1M The proposed budget includes a series of project appropriations related to installing or modifying environmental control systems, landfill covers, and other maintenance and monitoring systems at closed landfills. Executive staff previously indicated that closed landfill projects are geared towards moving landfills out of post-closure care and that once this occurs, the routine activities funded by the Landfill Post-Closure Maintenance fund can be stopped and the properties can be considered for secondary beneficial use.

Key Issues

Issue 1 – Renton Transfer Station Redevelopment: $3.2M

The proposed budget would appropriate $3.2 million for a new capital project to identify, design, and implement new uses of the Renton Recycling and Transfer Station that are more aligned with County goals for waste diversion and recycling. Council staff has identified this project as a key issue due to the Council's historical interest in potential service changes at transfer stations.

The proposed appropriation would support the planning and preliminary design of modernizing the station or redevelopment into a different type of resource recovery facility. Executive staff note that preliminary possible options could include:

- modernizing the station for expanded recycling and compaction;

- redeveloping the site to host a food waste slurry preprocessing plant for anaerobic or co-digestion, salvaged lumber warehouse, mattress recycling facility, an EcoPark; or

- co-locating more than one of the recycling facilities listed in the previous bullet.

According to Executive staff, the Renton station was constructed in the 1960s and is a top load station without compaction and limited recycling services (e.g., facility does not accept yard/wood waste, scrap metal, etc.). Once NERTS and SCRTS are complete, the Renton station will be the oldest and only remaining transfer station from the 1960s not currently planned for replacement with a more modern facility. They further state that redeveloping this site for other reuse, recycling, and waste diversion purposes is consistent with a more circular economy, would reduce the number of truck trips to transport waste to Cedar Hills due to diverting garbage from the Renton station to stations with compactors, and improve safety by designing out current risks of a top load station. However, Executive staff also indicate that the costs associated with redevelopment would put upward pressure on fees during a time of already high growth in the capital program and would require self-haulers and commercial waste haulers to travel further to dispose of locally collected waste. This may, according to Executive staff, increase the curbside bills of residents living closest to the station.

The adopted 2019 Comprehensive Solid Waste Management Plan included recommended action 2-t, which stated: "Although approved for closure under the Solid Waste Transfer and Waste Management Plan, reserve the option to retain the Renton station until the new urban transfer facilities have been completed and the impact of closure has been fully evaluated." Executive staff cite the opening of the Bow Lake and the Factoria Recycling and Transfer Stations and note that the tons from the Renton station could be absorbed by these stations. Council staff have inquired about the analysis conducted by SWD supporting this statement and why SWD does not plan to wait until the SCRTS and NERTS projects are complete to evaluate the potential closure.

Executive staff expect to engage with the City of Renton, the King County Council, waste haulers that use the station, County staff, and other County agencies near the station in the next month or so. Executive staff also expect to engage community members and gather community input to inform the decision for the site. According to Executive staff, a decision for the use of the site would be expected to be made in 2024 and a capital budget request would be submitted to the Council to support the completion of the design and implementation. It is currently unclear what other Council action may or may not be necessary to close the Renton station, redevelop the site's purpose, or cease acceptance of certain types of waste like garbage.

Council staff analysis is ongoing.

Issue 2 – Co-digestion Pre-processing Facility: $11.1M

The proposed budget would appropriate approximately $11.1 million for a new capital project to site and build a structure that could house a pre-processing facility where commercial food waste is turned into a slurry. Executive staff indicate that this slurry can then be taken to an anaerobic digestor or co-digested with other organic material where methane is then captured and converted to a renewable energy product. Executive staff anticipate that they expect a third party would rent the space at this structure to operate a digester and the Division would receive rental income. Council staff has identified this project as a key issue due to potential unknowns surrounding the project, including third party interest, the potential challenges in siting an additional solid waste facility in King County, and unclear benefits to ratepayers.

According to Executive staff, HB 1799 passed by the Washington State Legislature this year mandated commercial food waste be collected as a separate stream beginning in 2024. Executive staff anticipate that approximately 50,000 tons of food waste in King County is currently disposed that could be diverted, which includes businesses that will be subject to the new state collection requirement. Executive staff indicate that in 2021, data showed that regional processing capacity for organic materials was close to 80 percent. They further state that while there is capacity now to compost the projected commercial food waste for the next few years, more capacity will be needed when the permitted capacity for composting will be reached by the early 2030s. Budget materials indicate that the proposed facility would help expand the regional organics management opportunities.

The proposed appropriation would support the planning and design phases of the project and potentially some implementation. Budget materials indicate that the appropriation request is scaled for the purpose of moving quickly on developing a structure to house a co-digestion pre-processing facility due to the new state law requiring organics diversion and the approaching County goal of zero waste of resources by 2030. The current estimated total cost at completion is approximately $19.6 million. The materials also state that a location for this facility has not been identified yet and so an additional appropriation may be necessary.

Council staff have requested additional information about the business case for this project, specifically on what has been done to gauge the existence of third-party interest in leasing this future space, why urgency is warranted when organics processing capacity is not expected to be reached until at least 2030, and what sort of siting process is expected given potential challenges in siting an additional solid waste facility. Additionally, Council staff have inquired how this capital project specifically benefits feepayers as it would be supported by revenues from garbage disposal fees and not fees paid for organics collection and disposal.

The Executive's proposed 2023-2024 budget also includes a related appropriation in the Wastewater Treatment Division capital budget of approximately $2.0 million to design and construct organics processing infrastructure for co-digestion of wastewater solids and food waste at the South Treatment Plant in Renton. Council staff has inquired about the relationship between the two projects.

Council staff analysis is ongoing.

Ordinance 18893

Ordinance 18893

https://kingcounty.gov/depts/auditor/auditor-reports/cpo/swd-cedar-hills.aspx

Executive staff indicate that EcoParks often co-locate a variety of waste reduction and recycling facilities that can be mutually beneficial to each other. For example, part of the site could be a recycling depot for bulky items and tools and another part of the site takes these materials and repairs/refurbishes them for use.

Ordinance 18893

Att A Page 123