King County Channel Migration Public Rule Update and Revisions

January 2023 Report per Ordinance 17485, Section 50.O

Introduction

Channel migration, a type of flood hazard from riverbank erosion and channel shifting, can threaten people and property. King County regulates land uses within mapped channel migration hazard areas to reduce these risks. Channel migration can be present outside of the mapped floodplain areas.

In 1999, King County adopted criteria for mapping channel migration hazard areas, and mapped four river areas (Raging, Tolt, Middle Green, and the area of the Three Forks of the Snoqualmie) that were most at risk of channel migration. Other major rivers were not mapped at that time. The County also adopted development regulations to control development within these mapped channel migration hazard areas.

This report includes a summary of work accomplished since June 2022 and lists upcoming milestones for the first and second quarters of 2023.

Ordinance Text

Ordinance 17485, Section 50.O included a King County Comprehensive Plan work program item directing that:

By June 1, 2013, the executive shall provide a report detailing the progress of the rule making process, as required by this ordinance, which will develop the criteria for the designation and mapping of the channel migration zone areas in unincorporated King County. Additional reports to provide updates on the progress on the rule making process and implementation of the designation and mapping of channel migration zones shall be provided each January 1 and June 1, until the mapping is completed. The reports required by this subsection shall be transmitted to the council in the form of a paper original and an electronic copy with the clerk of the council, who shall retain the original and provide an electronic copy to all councilmembers and to the lead staff for the transportation, economy and environment committee, or its successor.

Background

In 2012, the County updated its Shoreline Master Program and the King County Code with respect to channel migration zones (CMZ) as required by the Washington State Department of Ecology to comply with the Shoreline Management Act, RCW Chapter 90.58. With these code changes, the Department of Local Services (DLS), formerly the Department of Permitting and Environmental Review, and the Department of Natural Resources and Parks (DNRP) were required to adopt, by public rule, criteria for channel migration designation, classification and mapping, and also to adopt, by public rule, channel migration zone studies and maps (K.C.C. 21A.24.274A). Both functions were accomplished by updating the existing King County channel migration public rule in March 2014.

CMZ studies on the Cedar, South Fork Skykomish, Tolt, Raging, Middle White and Greenwater rivers were completed and adopted in 2015, 2017, 2018, 2020, and 2022 respectively.

Once adopted via the public rule process, the studies are deemed “effective” and used to review land-use proposals. Studies of the remaining rivers are proceeding using the new mapping criteria specified in the public rule. Studies of the Greenwater and Lower Snoqualmie rivers have been in progress since the second quarter of 2020.

This report constitutes the required progress report.

Summary

Accomplishments during the third and fourth quarters of 2022 include the following:

The public rule serves as the administrative mechanism for adopting completed channel migration studies and the resulting mapping. DNRP applied the mapping criteria in the public rule to prepare a CMZ study and maps for applicable King County stream segments along Issaquah Creek in 2022. After the study and mapping are prepared, DNRP and DLS will present information at a public meeting to engage the landowners and stakeholders in the areas covered by the CMZ study and maps. Completion of the Lower Snoqualmie River CMZ is delayed due to a staffing shortage.

Issaquah Creek CMZ

- Field work and data collection for the Issaquah Creek CMZ study began after the Outreach and Communications Plan was approved by the King County Flood Control District on May 23, 2022.

- Coordination with City of Issaquah staff also was initiated after the Outreach and Communications Plan was approved. City of Issaquah staff are providing historical information regarding flooding and channel migration and assisting with providing field work access within the City limits.

Lower Snoqualmie River CMZ

- Due to recent vacancies of technical staff and supervisor with expertise in CMZ mapping, completion of this study has been delayed until mid-2023. No additional work was accomplished on this study during the third and fourth quarters of 2022.

Next Steps

- WLRD staff will continue to conduct field work and technical analyses for the Issaquah Creek CMZ study in the first and second quarters of 2023.

- Once the field work and technical analyses are complete, draft maps and a report will be prepared.

- The Lower Snoqualmie River CMZ effort will be resumed when River and Floodplain Management Section staffing resources are restored. Recruitment to fill staff vacancies are underway.

- The next required status report, due to the King County Council on June 1, 2023, will include a schedule update of draft study reports and mapping conducted in the first half of 2023.

Information prepared in these CMZ studies is being used in conjunction with flood and landslide hazard mapping to improve information about flood-related hazards along river corridors. The studies also provide information about dynamic habitat-forming river processes and may be useful in planning efforts for regional habitat restoration.

Link to Ordinance 17485

Link to Public Rule LUD-17-1-3-PR