EXHIBIT E

List and Schedule of Deliverables

| Date | Deliverable |
| --- | --- |
| 2019 |  |
| June 15, 2019 | Compliance Monitoring and Institutional Controls Plan |
| July 1, 2019 | Phase 1A (Trail Capping) Engineering Plans and Specifications with Engineering Design Report |
| September 2019 – May 2020 | Phase 1A Construction |
| Within 90 days of project physical completion | Phase 1A Final Report |
| Start submitting annually 1 year after physical completion of Phase 1A (May 2021) | Annual Monitoring Report for work done to-date |
| October 1, 2020 | Phase 1B (Skeet Range Cleanup and Invasive Vegetation Removal Acres 4 - 6) Engineering Plans and Specifications with Engineering Design Report |
| April 2021 – August 2021 | Phase 1B Construction |
| Within 90 days of project physical completion | Phase 1B Final Report |
| December 2021 | Phase 2 Landscaping Plan and Specifications Complete |
| February 2022 – March 2022 | Phase 2 (Plant Acres 4-6) |
| Within 90 days of project physical completion | Phase 2 Final Report |
| June 1, 2023 | Phase 3 (Clear and Plant Acres 7 – 10, Wetland Remediation) Landscaping Plans and Specifications Complete |
| October 2023 – December 2023 | Phase 3 Construction |
| Within 90 days of project physical completion | Phase 3 Final Report |
| Start submitting 1 year after submission of first annual report (Est. Q2 2025) | Five Year Report |
| June 1, 2026 | Phase 4 (Clear and Plant Acres 11-13) Landscaping Plans and Specifications Complete |
| October 2026– December 2026 | Phase 4 Construction |
| Within 90 days of project physical completion | Phase 4 Final Report |
| June 1, 2029 | Phase 5 (Clear and Plant Acres 14-16) Landscaping Plans and Specifications Complete |
| October 2029– December 2029 | Phase 5 Construction |
| Within 90 days of project physical completion | Phase 5 Final Report |
| Within 10 days of Completion of the Remedial Action | Record the Ecology-approved Restrictive Covenant with the office of the King County Auditor |

Note:

The original CAP schedule concluded project work with Phase 4 in 2028.  King County has revised and extended this schedule and added a Phase 5 to finish project work in 2029.  Ecology hereby approves this extension of the original schedule as set out in the CAP and previously approved by Ecology.