Metro 2017-2018 Fares Work program

Overview

Metro is developing a fares work plan for 2017-2018 that will include both follow-up from the findings of the 2016 Regional Fare Forums as well as a comprehensive assessment of other fare issues.

### Key Objectives

| 1. Make fare easier to understand and pay | Simply fare options and fare payment across Metro services |  |
| --- | --- | --- |
| 2. Coordinate with regional partners | Coordinate fares across agencies, including planning for the next generation ORCA project |  |
| 3. Speed operations | Increase the use of faster fare payment methods such as ORCA and mobile ticketing, evaluate options for allowing fare payment off-board or at multiple doors |  |
| 4. Improve safety | Reduce the role of operators in fare transactions and sources of fare disputes |  |
| 5. Grow transit ridership and address affordability barriers | Identify opportunities for new and existing programs to make transit attractive and affordable. |  |

Assumptions: While these objectives are the primary drivers of potential changes, any proposed change to fare structure would be evaluated within the context of Metro's fund management and fare policies. The King County Council recently updated Transit's Fund Management Policies, including a fare revenue recovery minimum of 25% and target of 30% of operating cost. Current fare recovery is 31% of operating costs.

### Timeline and key decision points

| 2016 | 2017 |  | 2017-2018 |
| --- | --- | --- | --- |
| Q4 | Jan | Feb | March | April | May | June |  |
| Regional Fare Forums | Work Program planning | Stakeholder outreach | Initial public outreach phase Development and internal review of fare options to take to the public | Second public outreach phase (coordinated with Sound Transit) Develop and collect input on final proposal | Internal review of proposal | Transmit to Council | Development of long-term work program items |

### Fares Roadmap 2017-2018

|  | Work Program Areas |  |
| --- | --- | --- |
|  | Fare coordination/ simplification | Transit access and affordability | Speeding boarding and improving safety | Additional changes |
| Objective |  |  |  |  |
| 1. Make fares easier to understand and pay | Focus area | Benefit area | Benefit area | TBD |
| 2. Coordinate with regional partners | Focus area | Benefit area | Benefit area | TBD |
| 3. Improve safety | Focus area |  | Focus area | TBD |
| 4. Speed operations | Benefit area | Benefit area | Focus area | TBD |
| 5. Grow transit ridership and address affordability | Benefit area | Focus area | Benefit area | TBD |
| Planned Actions |  |  |  |  |
| Near Term (June) | Evaluate options and impacts of changes to zone/peak fares Potential fare change ordinance | Identify pilot/demonstration projects and research program for low-income, youth, and student fares | Conduct market research and analysis of strategies including increasing ORCA use, mobile payment, all-door or off-board payment | Collect input on needs |
| Long Term (2017-2018) | Additional coordination/ simplification if needed | Based on near-term findings, proposal for longer-term program changes | Implementation plan for recommended changes | Recommendations for additional changes |

Public Engagement Plan

### Engagement Goals

- Get input from stakeholders and the public on their preferences for simplifying Metro’s fares to inform an ordinance to simplify Metro’s fares; inform additional, longer-term fare work program areas of focus that would increase ORCA usage and access to transit

- Build an understanding among stakeholders and the public about the tradeoffs of various fare structures and key influencers (such as technology, agency policies and goals, regional coordination opportunities and constraints and customer data) that inform options under consideration

### Affected populations, communities, and stakeholders

- Riders of transit – including users of ORCA and cash payers, youth, older adults, students, users of LIFT and RRFP’s, Vanpool users, Access paratransit riders

- Transit advocacy groups

- Schools, colleges, and universities

- Employers

- Transit operators

- Community-based organizations and groups that serve people who use transit

- Partner agencies – including Sound Transit, City of Seattle

- Elected officials – including the King County Executive, King County Council and interested jurisdictions

### Engagement Timeline

| February | Stakeholder interviews and invitation to participate in workshops Brief Council staff (Interbranch) Brief TrEE Preparation for public outreach |
| --- | --- |
| March | Facilitate Stakeholder Workshop #1 Fare Forum follow-up meeting Website content Brief interested King County Councilmembers and staff on public options First round of general public and community-based outreach Facilitate Stakeholder Workshop #2 |
| Early April | Second round of public feedback – opportunity to attend online or in-person open house Update website content Media Invitation to participate - Social media, transit alerts, stakeholder email Facilitate three public open houses around the county |
| Late April | Facilitate Stakeholder Workshop #3 Public engagement summary |

### Methods of engagement

| Element | Description |
| --- | --- |
| Stakeholder Process |
|  | Stakeholder Interviews | Interview 15-20 stakeholders who have an interest in or serve people with an interest in the outcome of this work to build awareness and gather input on their desired outcomes for the fares work program. |
|  | Stakeholder Workshops | Convene a group of approximately 10-15 representatives from different organizations who reflect all types of users of transit including young people, older adults, people with disabilities, schools/colleges/universities, employers and people with low or no income. This group will serve in an advisory capacity and will not make any formal recommendations or decisions. Work is planned to include three workshop-style meetings. |
|  | Stakeholder Briefings | Brief a broader range of stakeholders at regularly scheduled meetings to update them on this work, invite participation, and help spreading the word about participating in the process via online engagement and public open houses. |
| Community-based outreach |
|  | Community Outreach Contracts | Public outreach facilitated by organizations who serve populations who are unlikely to otherwise engage in Metro’s public process. Metro will provide a set of questions to organizations and ideas for collecting feedback. In addition, Metro will be available to serve as a resource to conversations with these client populations. The organizations that facilitate input gathering can choose how best to gather input and will be expected to document and share their process and results with Metro. Suggested organizations to conduct this engagement must meet the following criteria: Primary work is provision of services to communities of color, communities with low English proficiency, low-income communities, and disabled communities Non-profit organization or public entity Organizations selected should represent a broad geographic and language distribution within King County Ability and willingness to conduct outreach on behalf of Metro |
|  | Smaller organizations | Smaller community organizations will be engaged in Metro’s public process even if they are not contracted for outreach. |
|  | ORCA LIFT organizations | Organizations that participate in the ORCA LIFT program will be leveraged throughout the outreach process. |
| General Public Outreach |
|  | Online Engagement | March: Gather feedback on rider priorities for fare payment and ways in which current fares and the fare payment system addresses these priorities. April: Share fare change options, solicit input on a preferred option, and additional work Metro needs to do to make transit and ORCA more accessible to people. |
|  | Public Open Houses | Facilitate three public open houses around the county at which the public can learn about fare change options and provide input on their preferred option. |