BEST STARTS FOR KIDS

IMPLEMENTATION UPDATE

By adopting Ordinance 18373, Council approved the Best Starts for Kids (BSK) Implementation Plan in September 2016.  During deliberations on this plan, Executive Staff noted BSK implementation would occur in stages, enabling broad stakeholder engagement, leveraging of partnerships and continuous consideration of community needs throughout King County to tailor funding strategies and calls for proposals to fit those needs.

The Budget and Fiscal Management Committee Chair requested a briefing to update this committee on the status of BSK implementation roll-out.  Executive Staff have provided information on a range of implementation-related items including: 1) the status of planning workgroups; 2) the status of planned or completed request for proposal (RFP) processes; 3) updates on signed contracts or contract amendments; and 4) staffing updates.  That information is summarized below by BSK allocation. Note that some BSK strategies and programs have been grouped together or separated to streamline planning and procurement. These groupings reflect the information provided by Executive Staff.

YOUTH AND FAMILY HOMELESSNESS PREVENTION INITIATIVE (YFHPI)

The Health, Housing and Human Services Committee was briefed on the status of this program on April 4, 2017.  Consistent with that briefing, 26 of the 27 contracts have been accepted as outlined in the chart below.  Additionally, all programs are currently receiving mid-contract site monitoring visits.  LGBTQ training, required of all recipients under the implementation plan for this initiative, has begun.  The first half-day training was held on February 14, 2017 and had 32 participants. Learning circles trainings have also begun and have included a range of topics.

| Agency | BSK Funded Amount |
| --- | --- |
| Africatown Center | $150,000 |
| API Chaya | 150,000 |
| Atlantic St Center | 150,000 |
| Auburn Youth Resources | 150,000 |
| Friends of Youth | 150,000 |
| Interim Community Development Ass. | 150,000 |
| Iraqi CC of WA | 150,000 |
| Kent YFS | 150,000 |
| LifeWire | 150,000 |
| Mother Africa | 150,000 |
| Mother Nation | 150,000 |
| MSC RAP Fed Way | 150,000 |
| Open Doors | 150,000 |
| Partners at Lowell | 150,000 |
| Partners in Employment | 150,000 |
| POCAAN | 150,000 |
| Refuge Womens Alliance | 150,000 |
| Riverton Park UMC | 150,000 |
| Seattle Education Access | 150,000 |
| Seattle Indian Health Board | 150,000 |
| The ARC King County | 150,000 |
| Therapeutic Health Services | 150,000 |
| United Indians of All Tribes | 150,000 |
| Wellspring | 150,000 |
| YES | 150,000 |
| YouthCare | 150,000 |

PRENATAL – 5 YEARS STRATEGIES

- Innovation Fund:  The prenatal to eight years committee of the Children and Youth Advisory Board and Executive Staff have been providing feedback and input to inform a supplemental appropriation that is on track to be transmitted before June 30, 2017, as required in the 2017-2018 budget; this supplemental appropriation ordinance will be transmitted along with clear written specifications and an investment process for this fund.

- Home-Based Services:

  - Work Group: A Home-Based Services work group has been created and has met to understand the current landscape and discuss priority populations. The work group intends to continue meeting.

  - RFP: Expected summer 2017

  - Partnerships: For the Parent-Child home program, one of the possible community-based programs and innovative approaches, United Way will be the intermediary, combining funds from private donors, King County and the City of Seattle.

- Community-Based Parenting Supports, Information for Parents/Caregivers on Healthy Development, Family Engagement (ex. Parent/Peer Supports):

  - Work Group:  Work group is considering alignment of secondary indicators across these strategies and reviewing data sources to inform strategies.

  - RFP: Expected July 2017

  - Partnerships: Staff meetings with Bezos Foundation and Child Care Resources to gather information for workgroup.

- Child Care Health Consultation: This workgroup began meeting during the first week in May and will be meeting weekly.

- Direct Services System Building to Assure Healthy Development and Workforce Development:

  - Work Group: Work Group is meeting regularly.

  - RFP:

    - Developmental Screening RFP is in the process of being developed for a landscape analysis of current developmental screenings, what training is happening and cultural competency. It is expected to be released spring 2017.

    - Workforce Development RFP is expected to launch in fall 2017.

    - Infant Mental Health RFP expected to launch summer 2017.

  - Contracts: Early intervention services contracts through the Developmental Disabilities Division have been extended through June 2017 with providers as shown below.

| Agency | BSK Funded Amount |
| --- | --- |
| Birth to Three Development Center | $ 94,655 |
| Boyer Children's Clinic | 161,075 |
| Children's Therapy Center | 327,600 |
| Childstrive | 3,675 |
| Encompass | 96,160 |
| Hearing Speech and Deafness Center | 7,770 |
| Kindering Center | 350,400 |
| Listen and Talk | 33,915 |
| Northwest Center | 103,235 |
| Seattle Children's Hospital | 5,770 |
| University of Washington | 15,760 |
| Wonderland Development Center | 68,290 |

- Help Me Grow: Staff is in the process of meeting with a range of entities and at a range of tables (national, state, and local) to obtain necessary information for system alignment and design.

- Investments in Public Health’s Maternal/Child Health Services: Best Starts for Kids funding is continuing to support these programs in the Department of Public Health.

5 – 24 YEARS STRATEGIES

- Trauma Informed and Restorative Practices: Building Resiliency of Youth and Reduce Risky Behavior [Trauma Informed Schools and Organizations & Restorative Justice Practices]

  - Work Group: Established and is meeting regularly. Staff has performed outreach to experienced school staff and has conducted a parent focus group organized with support of Team Child.

  - RFP: Two-tiered RFP planned.  First mini-RFP for either planning or programming (under $10,000) for the 2017-2018 school year will be released in early May 2017. Large RFP or RFPs will be released at the end of 2017/beginning 2018 for multi-year implementation starting in the 2018-2019 school year.

- Building Resiliency of Youth and Reduce Risky Behavior [Quality out of School Time]

  - RFP: Expected end of summer 2017.

  - Partnerships: BSK is partnering with Schools Out Washington to implement this strategy.  A planning contract has been signed to develop the implementation plan.  BSK will have staff representation on the development of the RFP and the review team but Schools Out Washington will be administering the contracts.

| Agency | BSK Funded Amount |
| --- | --- |
| Schools Out Washington Planning | $210,000 |

- Meet the Health and Behavioral Needs of Youth [Screening, Brief Intervention and Referral to Treatment & Early Detection and Intervention for the Prevention of Psychosis]

  - RFP: SBIRT is planning a two-part RFP process starting with small planning grants in May to middle schools (under $10,000) for planning and readiness assessment to start SBIRT in their schools. That RFP was released the second week in May and applications are due June 14. Larger RFP would take place at the end of 2017/beginning of 2018 in combination with MIDD funds to provide school-based behavioral health services of which SBIRT is a component.  The Early Detection and Intervention for the Prevention of Psychosis (EDIPP) pilot work has not begun.

  - Partners: Reclaiming Futures will consult to develop middle school model.

- Meet the Health and Behavioral Needs of Youth [School Based Health Centers]

  - RFP: There have been two bidders’ conferences in Kent and via webinar.  Applications were due in early April. Five were received for three available awards.  Notice of selection is expected mid-May.

- Youth Development: Building Resiliency of Youth and Reduce Risky Behavior [Healthy Relationships and Domestic Violence Prevention for Youth & Youth Leadership and Engagement Opportunities], Help Youth Stay Connected to Families and Communities [Mentoring], Meet the Health and Behavioral Needs of Youth [Positive Identity Development]

  - Work Group: This workgroup is established and has been meeting regularly.

  - RFP: Expected to be released in June 2017.  In response to community feedback, it is expected that there will be one RFP for all four strategies.

- Help Young Adults Who Have Had Challenges Successfully Transition Into Adulthood: Executive staff indicate that this strategy area will not have a work group. It is being developed by Executive staff in the Employment and Education Division of the Department of Community and Human Services and the Children and Youth Strategic Advisor.  Work includes integrating this funding opportunity with existing programming and funding in order to partner with the work that is already happening with workforce development in support of the region.

- Stop the School-to-Prison Pipeline

  - Contracts: The Theft 3 and Mall Safety Pilot Project was launched in April. It is still in the beginning phases of implementation. Contracted entities are outlined below.

| Agency | BSK Funded Amount |
| --- | --- |
| Safe Futures | $143,000 |
| Glover Empowering Program | 338,000 |
| Horn of Africa | 143,000 |

The Students Creating Optimal Performance Education (SCOPE) project has 35 young people participating in the program, which brings the current case manager’s caseload to capacity.  The program is in the process of hiring a second case manager and that position has been advertised.

COMMUNITIES OF OPPORTUNITY (COO)

Work Groups: The Communities of Opportunity Interim Governance Group is in the process of transitioning to the Communities of Opportunity-Best Starts for Kids Advisory Board.  Executive staff indicate that this group will create a Leadership and Learning Community Planning Committee that will function as the working group for the following programmatic approaches:

- Places: Awards to Community Partnerships

- Awards to other place-based sites

- Awards to cultural communities, including rural communities

- Institutional, System and Policy Change

- Learning Community

- Strategic investments to benefit COO partners broadly

- Forums

- Technical assistance

The work group will aim to ensure the implementation of investments are coordinated to increase collective, aggregate impact of the strategy investments. It is expected that Councilmembers and their district staff will be invited to participate in these work groups before the end of the month of May.

There are no workgroups anticipated for work involving investments in original place-based sites.

RFP:  COO anticipates releasing competitive requests for proposals for two strategy areas in 2017-2018.  The Institutional, Systems and Policy Change RFP is expected to be released in summer 2017. There is no date anticipated yet for other place-based sites or cultural communities, including rural communities within the Places: Awards to Community Partnerships program approach. Proposals will only be accepted from the three original place-based sites (Rainer Valley, SeaTac and Tukwila, and White Center/North Highline unincorporated area) selected by Communities of Opportunity in March 2015 through a competitive Letter of Intent process.  This Strategy Implementation Fund proposals process follows from a pre-application process in which Rainier Valley (HomeSight is the lead agency), White Center (White Center Community Development Association is the lead agency), and SeaTac/Tukwila (Global to Local is the lead agency) submitted pre-application materials in January 2017 - April 2017. Approximately $2.2 million in contract funding will be awarded in June 2017.

Contracts: Communities of Opportunity is making strategy implementation funds available through a proposal process for grant/contract funding with a term of up to 18 months, from July 2017 through December 31, 2018.

Partnerships: Since Communities of Opportunity inception, Seattle Foundation has made over $4,000,000 in grants to nonprofit organizations for COO place-based community partnerships and systems and policy change initiatives. In 2017-2018 COO BSK funding will leverage an additional $2,960,000 from the Seattle Foundation, its co-founding partner, and their philanthropic donors, including a multi-year commitment from Ballmer Giving dedicated to COO. Those amounts exclude additional in-kind operating and staff support provided by Seattle Foundation.

TECHNICAL ASSISTANCE AND CAPACITY BUILDING

The Best Starts for Kids Implementation Plan specifies that at least 1% of funds in the Prenatal – 5 Years, Approaches and Investments allocation and at least 1% of funds in the 5 – 24 Years, Approaches and Investments allocation will be used to contract with one or more independent organizations, as appropriate to the program area, to provide front-end and long-term community outreach, technical assistance and capacity building to reduce barriers for smaller and more isolated organizations, partnerships and groups to access BSK levy funds.

Executive staff note that they have differentiated between technical assistance and capacity building in their planning. With regard to technical assistance, they are considering specifically assisting organizations to apply for BSK levy funds – both in helping an organization determine “right fit” in funding as well as supporting the writing of applications process. Executive staff note that a request for qualifications (RFQ) will be released before the end of the month for technical Assistance. With regard to capacity building, this is being conceptualized as supporting organizations to become thriving, sustainable organizations once they have been funded.  There has been no more planning in this area yet but it is expected that a work group will be assembled to work on this issue in early summer 2017.

BSK STAFFING

Hiring of approved positions in the 2017-2018 budget has not yet been completed.  It is expected that staffing ramp-up will continue to parallel implementation ramp-up.  As of the writing of this document, of the 26 approved positions in the Department of Community and Human Services, 16 positions have been filled.  In the Department of Public Health, of the approved 39.45 positions, 20 have been filled.  Not all staff hired have begun employment yet.

Work Groups may include County staff, non-County stakeholders, members of the Children and Youth Advisory Board, and Councilmember district staff, who have been invited pursuant to requirements in the 2017-2018 budget.

The University of Washington was awarded a BSK-funded contract in the amount of $372,000 from the evaluation allocation for work on the 0-3 parent survey.