## STAFF REPORT

| Agenda Item: | 9 | Name: | Laura Hitchcock & Wendy Soohoo |
| --- | --- | --- | --- |
| Proposed No.: | 2017-0327 | Date: | January 24, 2018 |

SUBJECT

Proposed Motion 2017-0327 would approve the detailed Mental Illness and Drug Dependency (MIDD) 2 Implementation Plan. Proposed Motion 2017-0327 for Council approval of the plan has been referred first to the Regional Policy Committee, and then to the Health, Housing and Human Services Committee.

SUMMARY:

Proposed Motion 2017-0327 would approve the detailed Mental Illness and Drug Dependency (MIDD) 2 Implementation Plan. The MIDD 2 Implementation Plan was required by Ordinance 18407, which also established updated policy goals for the MIDD. Staff have not identified any major divergences between the transmitted MIDD 2 Implementation Plan and the policy direction in the council-approved MIDD 2 SIP, nor between the MIDD 2 Implementation Plan and the requirements set forth in Ordinance 18407 for the MIDD 2 Implementation Plan.

Twenty-two of MIDD 2’s initiatives are new, and nine existing strategies continued from MIDD 1 are being implemented with modifications (the remaining twenty-two are to be implemented with no change). There are various updates to the initiatives as approved in the MIDD 2 SIP, including a new approach to performance measurement and updated descriptions.  The Plan indicates that nine of the new initiatives and five of the existing initiatives are delayed from the estimated timeline approved by Council in the MIDD 2 SIP.  Nineteen initiatives have updated scopes or descriptions.  Four initiatives have revised allocations.  The Implementation Plan notes that MIDD 2 implementation is occurring amidst a dynamic and challenging external policy context that creates significant uncertainty, including for MIDD 2.

Council adoption of the motion would signify approval of the current implementation approaches to MIDD 2 and that the requirements for the implementation plan as established in Ordinance 18407 have been met.

Proposed Motion 2017-0327 was approved by the Regional Policy Committee on December 5, 2017.

BACKGROUND:

MIDD 1 History In 2007, the King County Council adopted Ordinance 15949 authorizing the levy and collection of an additional sales and use tax of one-tenth of one percent for the delivery of mental health and chemical dependency services and therapeutic courts. This tax is referred to as the Mental Illness and Drug Dependency sales tax (or MIDD 1).

MIDD 2 Assessment and Planning  In March 2015, in consideration of extending the expiration date of the sales tax, the King County Council passed Ordinance 17988 setting requirements for a comprehensive review and potential modification of the MIDD 1 initiatives, programs and strategies described in the council-adopted MIDD 1 Implementation Plan.   Ordinance 17988 required a comprehensive retrospective report on MIDD 1, along with a proposed Service Improvement Plan for MIDD 2, if the levy were continued.

MIDD Levy Extension  Ordinance 18333, passed by Council in August 2016, amended Ordinance 15949, and the King County Code Chapter 4A.500.300, as amended, to revise the expiration date of the levy from January 1, 2017 to January 1, 2026 (an extension of nine years) to allow the continued collection of the sales and use tax of one tenth of one percent for the delivery of mental health and chemical dependency services and therapeutic courts.  Known as MIDD 2, the levy is projected to generate $134 million for the 2017-2018 levy period, and increase by approximately $10 million per biennium for the levy remainder.

MIDD 1 Assessment Report The 2016 Comprehensive Historical Review and Assessment Report (Assessment Report) required by Ordinance 17988 was transmitted to Council and approved in September 2016 by Motion 14712.  The Assessment Report indicated that MIDD 1 achieved significant reductions in emergency department, psychiatric hospital, and jail utilization, a notable reduction in mental health symptom severity, and intentional linkages with other County initiatives, consistent with the adopted policy goals for MIDD 1.  Of the 32 MIDD 1 strategies that were funded, the Assessment Report notes that 19 met or exceeded long-term goals in at least one policy goal area.  The Assessment Report proposed changes to the MIDD 1 policy goals, and recommended revisions to MIDD evaluation, performance measure and data gathering processes, including an updated and revised evaluation framework, revised performance measures, targets and outcomes, updating the data collection and infrastructure, and enhanced and improved reporting processes. The Assessment Report also proposed a draft MIDD 2 Framework, in Appendix B to the Report, which outlines the relationship between the overarching MIDD 2 Result, policy goals, and theory of change, headline indicators, and sample performance measures for each of the 5 MIDD 2 strategy areas.  The proposed framework includes a new spectrum for categorizing programs and services, comprised of four strategies that are based on the continuum of care:  Prevention and Early Intervention; Crisis Diversion; Recovery and Reentry; and Systems Improvements.

MIDD 2 Service Improvement Plan  The proposed Service Improvement Plan (SIP) for MIDD 2 was then approved by Council by Ordinance 18406 in November 2016.  The adopted SIP made a variety of changes in MIDD 2, resulting from lessons learned as well as changes in the external environment (since the initial MIDD 1 levy was enacted) that were called out in the detailed Assessment Report. Also, as required by Ordinance 17988, the MIDD 2 SIP included a detailed description of each strategy, service and program, a schedule for implementation and a spending plan, and an initial list of performance measures, outcomes, and/or evaluation data for each proposed strategy.  In addition, the SIP, as required by Ordinance 17988, included process and administrative improvements to MIDD, addressing how initiatives would be added, deleted or revised, the role of and proposed changes to the MIDD Advisory Committee and a recommendation for MIDD fund balance reserve policies.  The MIDD 2 SIP also included a discussion of changed environmental conditions affecting the health and behavioral health systems subsequent to the initial levy of the tax, including behavioral health integration, the US Affordable Care Act, and the state Supreme Court ruling limiting psychiatric boarding.

The SIP included the following revised policy goals for MIDD 2:

- Divert individuals with behavioral health needs from costly interventions such as jail, emergency rooms and hospitals

- Reduce the number, length and frequency of behavioral health crisis events

- Increase culturally appropriate, trauma-informed behavioral health services

- Improve the health/ wellness of individuals living with behavioral health conditions

- Explicit linkage and furthering work of King County and community initiatives.

The MIDD 2 SIP also includes a revised MIDD 2 Framework in SIP Appendix F.

According to the MIDD 2 SIP Framework, MIDD’s desired result is:

People living with, or at risk of behavioral health conditions, are healthy, have satisfying social relationships, and avoid criminal justice involvement.

The MIDD 2 SIP as adopted added 20 new initiatives, for a total of 53 initiatives.

MIDD 2 Implementation and Evaluation Planning  The Council then addressed detailed implementation and evaluation planning for MIDD 2 in Ordinance 18407, also passed by Council in November 2016.  Ordinance 18407 amended King County Code Chapter 4A.500.300, codifying the revised MIDD 2 policy goals contained in the SIP, and amending requirements related to a MIDD oversight plan.  Ordinance 18407 outlines requirements for the oversight plan, renamed the “implementation and evaluation plan”; directs the Executive to develop the plan with the MIDD Advisory Committee and community stakeholders; and, notes that the plan is two parts:  Part One:  Implementation Plan, and Part Two:  Evaluation Plan. Ordinance 18407 Implementation Plan requirements are outlined in Table A, below.

Table A

MIDD 2 Implementation Plan Required Components of Ordinance 18407, as codified in KCC 4A.500.

| Summary | Implementation Plan Requirements (Part One) |
| --- | --- |
| Plan Content Requirements |
| What plan shall describe | Describe the implementation of the initiatives, programs and services outlined in the MIDD SIP, including: |
| Status and timing of work | A schedule of the implementation of initiatives, programs and services outlined in the MIDD SIP |
| Inputs (what is needed to do work) | A discussion of needed resources, including staff, information and provider contracts |
| Measures of impact | Outcome and performance measures |
| How will work be done/who will do work | Procurement and contracting information |
| Community engagement | Community engagement efforts |
| Alignment to long-term policy goals | How the initiative, program or service advances the county's mental health and chemical dependency policy goals |
| Fiscal Status | An updated 2017-2018 biennial spending plan and financial plan for the mental illness and drug dependency fund |
| Planning Process Requirements |
| Process to develop plan | Part One [Implementation Plan] is to be developed in collaboration with the MIDD Advisory Committee and community stakeholders |
| Timing of plan transmittal to Council | Part One [Implementation Plan] is to be submitted to Council by August 3, 2017 |

MIDD 2 Reporting to Council  Ordinance 18407 also amended the King County Code to require annual summary evaluation reports to be submitted to the Council by August 1st, starting in 2017.

ANALYSIS:

Overview This section of the staff report covers the following:

- Staff analysis of consistency of the MIDD 2 Implementation Plan with the Council-adopted Service Improvement Plan and Ordinance 18407, including both Plan content requirements and Plan process requirements for:

  - Updated schedule of implementation of initiatives, programs and services

  - Needed resources

  - Outcome and performance measures

  - Procurement and contracting information

  - Community engagement

  - Policy goals

  - Updated biennial spending plan and financial plan for the MIDD 2 Fund

- A summary of the Implementation Plan sections

- Highlights and Potential Issues, including:

  - MIDD 2 Implementation Plan changes, post SIP (delays, planned scope/design changes, and changed allocations)

  - Additional information on behavioral health system challenges and new incentive pool for providers

  - Discussion of the updated spending plan, as of Sept. 2017

The MIDD 2 Implementation Plan is required to ensure oversight, implementation and evaluation of the MIDD Service Improvement Plan are consistent with county’s policy goals and to fulfil the requirements of the state law that enables the levy’s sales tax.

The proposed MIDD 2 Implementation Plan, attached as Attachment A to Proposed

Motion 2017-0327, proposes an updated MIDD 2 framework, subsequent to its adoption in the MIDD 2 SIP (the framework includes the overarching result/goal for MIDD 2, 5 MIDD 2 policy goals, and the MIDD theory of change), as Appendix A.  The Implementation Plan notes that the SIP is the blueprint for MIDD 2 and that the Implementation Plan provides the initiative-specific, detailed working components of MIDD 2 and that together with the Evaluation Plan, the SIP and Implementation Plan provide a “full picture of MIDD 2 for policymakers, stakeholders and the public.”  The following sections provide an overview of the MIDD 2 Implementation Plan requirements and how they are addressed in the Implementation Plan, as well as additional information provided in the Implementation Plan, and additional information provided by the Executive regarding updates to the initiative timelines, and financial plan for MIDD 2.

MIDD 2 Implementation Plan Analysis  Staff have not identified any major divergences between the transmitted MIDD 2 Implementation Plan and the policy direction in the MIDD 2 SIP, as approved by Ordinance 18406, nor between the MIDD 2 Implementation Plan and the requirements set forth in Ordinance 18407 for the MIDD 2 Implementation Plan.  However, there are some changes to MIDD initiatives and implementation timelines in the transmitted plan that are reflective of the iterative work underway to redesign several initiatives, as well as the design work on new initiatives.  In addition, the plan indicates that some initiatives are delayed or changed due to behavioral health system external conditions.

Plan content requirements per Ordinance 18407 The Implementation Plan addresses each of the required elements of Ordinance 18407 and KCC 4A.500.309 and a table outlining where each of these elements is included in the plan can be found in the Executive Summary on page 5 of the Plan.  Staff concurs that each of the required plan elements is present.  A detailed cross-walk is provided with this staff report as Attachment 4: Cross-walk Between MIDD 2 Implementation Required Components and Proposed MIDD 2 Implementation Plan.

The MIDD 2 Implementation Plan describes implementation of the initiatives, programs and services outlined in the MIDD SIP, with Ordinance 18407 required elements underlined below, as follows.

- An updated schedule of the implementation of initiatives, programs and services is included in the proposed plan in Section 5, including technical corrections to service numbers or other errors contained in the MIDD SIP, updated narrative to reflect planning and changes to service delivery (such as whether to issue an RFP), and updated timelines.  In addition, updates to individual initiative language are provided within initiative descriptions (Section 6).  Subsequent to transmission of the proposed Implementation Plan, Executive staff provided further details on changes to initiative timelines, descriptions, and allocation changes.  A summary of these changes can be found in Attachment 6: MIDD 2 Initiative Changes Subsequent to SIP, to this staff report.

- A discussion of needed resources, including staff, information and provider contracts (Section 6 and Appendix D) is included.  Needed resources include estimated allocations for each initiative, whether King County will implement the initiative or whether it will be contracted, and indications that overall MIDD administration will be limited to six percent of the MIDD 2 budget.  These are included in the detailed initiative descriptions (Section 6), and in the MIDD biennial spending plan for 2017-2018.  No additional detailed information is provided in the Implementation Plan on staffing of King County-implemented initiatives or administration.  The plan indicates that management and administration will include DCHS staff support of contract and program functions, including supporting the MIDD 2 advisory committee.  Management and administration also includes:

- Budget management

- Behavioral health systems programmatic development

- Oversight of Requests for Proposals (RFP), memoranda of understanding (MOU) and contracting processes, and

- Evaluation of MIDD 2.

- Outcome and performance measures for each initiative where known (Section 6 and Appendix A) are provided.  Each detailed initiative description in Section 6 contains a section entitled “preliminary performance measures” based on the MIDD 2 framework.  All new, continuing and revised initiatives also contain revised performance measures subsequent to the MIDD 2 SIP, a substantive change to the way that initiatives will be measured. The proposed Implementation Plan notes in a footnote to each initiative description that “throughout 2017, review and refinement of Results-based Accountability (RBA) performance measures for MIDD 2 initiatives will be conducted whenever applicable, in consultation with providers.  Updates to performance measures that may result from this collaborative process will be reported in the next MIDD Annual Report in August 2018.”

The MIDD 2 Framework, in Appendix A to the plan, also demonstrates the outcome and performance measures, and includes “headline” indicators, a new set of indicators added to the Implementation Plan subsequent to Council approval of the MIDD 2 SIP, in alignment with the RBA approach.  Additional information on outcome and performance measures is found in the MIDD 2 Evaluation Plan, Proposed Motion 2017-0326, briefed separately.

- Procurement and contracting information (Section 6 and Appendix C).  Each detailed initiative description in Section 6 contains information about who will implement the particular initiative, and specifies whether it be a contractor or King County.  The implementation schedule contained within each initiative description also explains the procurement process and timeline, for initiatives competitively procured.  The Initiative Change Summary Table to the proposed Plan (Appendix C) notes where these implementation plans had changed as of June 2017.

Subsequent to transmission of the proposed Implementation Plan, Executive staff provided further details on changes to procurement processes, updated as of September, 2017, entitled:  MIDD 2 Initiative Procurement Approach Status.  This update can be found in Attachment 5 to this staff report.

- A section describing community engagement efforts for individual initiatives is included in the detailed initiative descriptions. (Section 6) Community engagement efforts are described as ongoing through formal stakeholder processes, design efforts for newer initiatives, or ad hoc.

- The proposed Implementation Plan contains the updated MIDD 2 policy goals linked by initiatives, linking initiatives to one specific policy goal, shown in Table B, below.

Table B:  MIDD 2 initiatives by policy goal

| Goal 1: Divert individuals with behavioral health needs from costly interventions such as jail, emergency rooms and hospitals (Diversion) |
| --- |
| PRI-01 | Screening, Brief Intervention and Referral to Treatment (SBIRT) |
| PRI-02 | Juvenile Justice Youth Behavioral Health Assessments |
| PRI-04 | Older Adult Crisis Intervention/Geriatric Regional Assessment Team (GRAT) |
| PRI-08 | Crisis Intervention Training – First Responders |
| CD-01 | Law Enforcement Assisted Diversion |
| CD-03 | Outreach and Inreach System of Care |
| CD-04 | South County Crisis Diversion Services/Center |
| CD-05 | High Utilizer Care Teams |
| CD-06 | Adult Crisis Diversion Center, Respite Beds, Mobile Behavioral Health Crisis Team |
| CD-07 | Multi-pronged Opioid Strategies |
| CD-10 | Next Day Crisis Appointments |
| CD-13 | Family Intervention Restorative Services |
| CD-14 | Involuntary Treatment Triage Pilot |
| CD-16 | Youth Behavioral Health Alternatives to Secure Detention |
| RR-01 | Housing Supportive Services |
| RR-02 | Behavioral Modification Classes at CCAP |
| RR-03 | Housing Capital and Rental |
| RR-05 | Housing – Adult Drug Court |
| RR-06 | Jail Reentry System of Care |
| RR-07 | Behavioral Health Risk Assessment Tool for Adult Detention |
| RR-08 | Hospital Reentry Respite Beds |
| RR-11 | Peer Bridgers and Peer Support Pilot |
| RR-12 | Jail-based SUD Treatment |
| RR-13 | Deputy Prosecuting Attorney for Familiar Faces |
| RR-14 | Shelter Navigation Services |
| TX-ADC | Adult Drug Court |
| TX-JDC | Juvenile Drug Court |
| TX-RMHC | Regional Mental Health Court |
| TX-SMC | Seattle Mental Health Municipal Court |
| TX-CPPL | Community Court Planning |

| Goal 2: Reduce the number, length and frequency of behavioral health crisis events (Reduce Crisis) |
| --- |
| PRI-06 | Zero Suicide |
| CD-09 | Behavioral Health Urgent Care-Walk In Clinic Pilot |
| CD-11 | Children’s Crisis Outreach and Response Team (CCORS) |
| CD-17 | Young Adult Crisis Facility |

| Goal 3: Improve the health and wellness of individuals living with behavioral health conditions (Health and Wellness) |
| --- |
| PRI-03 | Prevention and Early Intervention Behavioral Health for Adults over 50 |
| PRI-05 | Collaborative School Based Behavioral Health Services: Middle and High School students |
| PRI-07 | Mental Health First Aid |
| PRI-09 | Sexual Assault Behavioral Health Services |
| PRI-10 | Domestic Violence and Behavioral Health Services and System Coordination |
| PRI -11 | Community Behavioral Health Treatment |
| CD-08 | Children’s Domestic Violence Response Team |
| CD-12 | Parent Partners Family Assistance |
| CD-15 | Wrap Around Services for Youth |
| RR-09 | Recovery Cafe |
| RR-10 | BH Employment Services and Supported Employment |
| SI-02 | Behavioral Health Services in Rural King County |
| SI-03 | Quality Coordinated Outpatient Care |
| TX-FTC | Family Treatment Court |
| SP-01 | Special Allocation Consejo |

| Goal 4: Increase culturally-appropriate, trauma-informed behavioral health services (Culturally-Appropriate and Trauma-Informed) |
| --- |
| SI-01 | Community-driven behavioral health grants |
| SI-04 | Workforce Development |

| Goal 5 Explicit linkage with and further the work of, King County and community initiatives (Linkage) |
| --- |
| CD-02 | Youth and Young Adult Homelessness Services |
| RR -04 | Rapid Rehousing – Oxford House Model |

- An updated biennial spending plan for 2017-2018 (Appendix D); and financial plan for MIDD Fund (Appendix E) are included as appendices to the proposed Implementation Plan. Subsequent to transmission of the proposed Implementation Plan, the Executive provided further updates on the proposed financial plan for the MIDD 2 Fund.  This updated financial plan shows a decrease in projected revenue growth in 2019/2020 and 2021/2022 for the MIDD Fund and notes that the Executive anticipates reprogramming $5.7 million for initiatives being revised or new initiatives on hold.  The updated plan of August 2017 is Attachment 7 to this staff report.

Plan process requirements  The Executive has indicated that the proposed plan received community input and was developed in collaboration with the MIDD 2 Advisory Committee.  Ongoing stakeholder processes may inform initiative implementation, or one-time processes may be conducted.  In yet others, the MIDD 2 Implementation Plan notes that no community engagement will be undertaken for the initiative.  The Plan was submitted within the required timeframe under Ordinance 18407.

Summary of the Implementation Plan Sections  The MIDD 2 Implementation Plan is organized into seven sections and seven appendices.  These can be summarized at a high-level as follows:

Section 1:  Executive Summary:  Provides high-level summary of plan sections.

Section 2:  MIDD 2 Implementation Plan Overview covers:

Key changes from the MIDD 2 Council-adopted SIP found in the MIDD 2 Implementation Plan:

- Updates to the adopted policy goals to conform to Ordinance 18407

- Adding therapeutic treatment courts as a fifth strategy area.

- Revising “outcomes” to “headline” indicators.  New headline indicators listed are:

  - Improved emotional health

  - Increase in daily functioning

  - Reduced or eliminated alcohol and substance use

  - Reduced suicide attempts and death

  - Reduced drug and opioid overdose deaths

  - Reduced incarceration rates

Section 2 also describes:

- MIDD 1 Assessment Report’s findings on impact and value of MIDD 1 services

- Purpose of MIDD 2, stating that MIDD services provide enhancements to underlying federal or state-funded services or address gaps between such services.

- 5 new adopted MIDD 2 policy goals, per Ordinance 18407

- 2017-2018 budget for the MIDD fund ($135 million) for fifty three initiatives within five strategy areas covering behavioral health continuum of care (prevention, treatment and recovery), system improvements and therapeutic courts

- MIDD 2 service delivery by contracted providers and King County government

- MIDD Advisory Committee history and community engagement in MIDD 2 design

- The MIDD 2 Framework, noting the updated framework includes an overarching result/goal for MIDD 2, 5 MIDD 2 policy goals, and the MIDD 2 theory of change.

The MIDD 2 Strategy Areas are listed in Table C, below.

Table C

MIDD 2 Strategies

| Strategy Area Role | MIDD 2 Strategy Area | Description | Initiative Programmatic Elements (Range) |
| --- | --- | --- | --- |
| Continuum of Behavioral Health Care | Prevention and Early Intervention (PRI) | People get the help they need to stay healthy and keep problems from escalating | Trainings Early assessment Brief therapies Expanded access to outpatient care who lack access to Medicaid Services across lifespan |
|  | Crisis Diversion (CD) | People who are in crisis get the help they need to avoid unnecessary hospitalization or incarceration | Expedited access to outpatient care Multidisciplinary community-based outreach teams Crisis facilities Alternatives to incarceration |
|  | Recovery and Reentry (RR) | People become healthy and safely reintegrate to community after crisis | Housing capacity and services Supported employment Peer-driven recovery supports Criminal justice reentry services |
| Vital System Support | System Improvements (SI) | Strengthen the behavioral health system to become more accessible and deliver on outcomes | Strengthen workforce to improve quality and availability of core services Community-initiated projects |
| (New strategy area in MIDD 2 Implementation Plan: partially funded in MIDD 1; Full funding in MIDD 2) | Therapeutic Courts (TX) | People experiencing behavioral health conditions who are involved the justice system are supported to achieve stability and avoid further justice system involvement | Court operations |

Section 3:  MIDD Management and Operations addresses:

- King County Department of Community and Human Services’ (DCHS) role in management and implementation of MIDD 2

- Other county departments’ roles

- Equity and social justice principles foundational to MIDD 2 approaches, namely:

  - Culturally responsive and informed,

  - Evidence-based and equitable

  - Reduce harm

- Principles and approaches for RFPs and contracting:

  - Coordination with other related funding sources

  - Expanded access

  - Coordination with other county human services funding streams

  - Majority of services delivered by community agencies

- Transition to value-based purchasing, including:

  - Performance-based elements of initiatives

  - Emphasis on systems integration and health and human services transformation

- Administration Cap:

  - Under six percent of the total MIDD 2 biennial budget (including evaluation and IT) for administration.

Section 4.  MIDD 2 Implementation addresses:

- Implementation Plan purpose:

“The Implementation Plan is a point-in-time status report on the implementation of new MIDD 2 initiatives and planned changes to MIDD 1 initiatives.  It updates the initial MIDD Initiative Descriptions included in the adopted MIDD Service Improvement Plan (SIP).”

- Updated Initiative Descriptions and Timelines (from MIDD 2 SIP):

  - Reflecting adopted MIDD 2 policy goals

  - Current performance measures

  - Community engagement efforts

  - Updated timelines and notes

- Summarizes Implementation Status for New Initiatives

- Of 22 new initiatives, 14 to be directly allocated to providers

- Of the 14, nine initiatives contracted as of June 2017

- Remaining eight new initiatives planned to go through some type of procurement process (Request for Proposal, Request for Information or Request for Qualifications).

- Shift to Results-based Accountability (RBA) (Revised performance measures):

  - Section 4 describes shift to performance measures and results-based accountability, a major difference between initial initiatives’ descriptions contained in MIDD 2 SIP.

- Planning and Community Engagement:

  - Community engagement plans for new and re-tooled initiatives are listed in Section 4, and engagement of the MIDD Advisory Committee detailed.

  - Expected community stakeholder processes are called out for MIDD 2:

- Multipronged-opioid strategies

- Small grants initiatives focused on rural and cultural/ethnic communities (Community-driven Behavioral Health grants and Behavioral Health Services in Rural King County)

- Workforce related initiatives (Quality Coordinated Outpatient Care, formerly titled “Workload Reduction”, and Workforce Development)

- MIDD staffing

- Tables of new and modified MIDD 2 initiatives are included (with index to detailed descriptions in Section 5)

Section 5.  Implementation Schedule Tables:  This section provides three Implementation Schedule tables for the initiatives listed in Section 4:

- MIDD 2 New Initiatives Schedule Summary

- MIDD 2 Existing Initiatives to be Modified Schedule Summary

- MIDD 2 Existing Initiatives with No Programmatic Change

Each table includes MIDD 2 initiative number, cross-walk to MIDD 1 initiative number where applicable, MIDD 2 initiative summary, primary policy goal addressed by the initiative, and implementation schedule for new and modified initiatives (no implementation schedule is provided for existing initiatives with no change).

Section 6.  Initiative Descriptions: This section comprises the bulk of the Implementation Plan and provides a detailed description of each of fifty-three MIDD 2 initiatives, including:

- Whether the initiative is new, modified or existing (continuing with no change)

- How program  (initiative) advances adopted MIDD policy goals

- Program description including:

  - Service components / design

  - Goals

  - Preliminary performance measures

  - Spending plan for the initiative for the biennium

  - Implementation schedule (procurement and contracting and services date)

  - Community engagement efforts

Section 6 also references Appendix C to the plan, which summarizes high-level substantive changes made to initiative descriptions between adoption of the MIDD 2 SIP and proposed MIDD 2 Implementation Plan.

Section 7. Looking Ahead and Conclusion:  Section 7 reiterates MIDD 2’s approach of balancing new and continuing initiatives; making strategic investments to address service system gaps; building on successes of MIDD 1; and, addressing evolution of the behavioral health system. Section 7 acknowledges specific external context for MIDD 2, each of which could result in changes to MIDD 2, including if: specific services are no longer under the authority of the county, insufficient state or Federal revenue is available, or additional leveraged revenue is available.  These include:

- Physical and behavioral health integration by January 1, 2020 (or by January 1, 2019 if King County is an early adopter).

- State Medicaid waiver (1115) and demonstration project.  The state has a new contract with the federal Centers for Medicare and Medicaid Services (CMS) to test innovative models.

- Possible Affordable Care Act repeal.  At the time of the writing of the MIDD 2 Implementation Plan, repeal was actively being considered by Congress.

- State legislation and budget.  Section 7 notes that Medicaid rates were reset in July 2017, dramatically reducing rates for King County, which could affect specific MIDD initiatives and the behavioral health system generally.  The section also notes that proposed state legislation lifting MIDD supplantation restrictions may affect MIDD, and that the state budget could impact the overall system.

Section 7 notes that due to the environmental uncertainty outlined above, DCHS includes contingency language in each MIDD contract and has created a Medicaid Reconciliation reserve for MIDD initiatives that assumed a certain amount of Medicaid funding, to allow these initiatives to remain whole should Medicaid funding decline.  (See Appendix C to the Implementation Plan.)

Section 7 also that the Executive expects to transit legislation to Council in 2017 that would appoint the MIDD Advisory Board and change the name of the MIDD levy. Section 7 also outlines the expected and required process for communicating with policymakers and stakeholders about MIDD 2.

MIDD 2 Implementation Plan Appendices  There are seven appendices to the MIDD 2 Implementation Plan.  Key appendices are:

- Appendix A:  MIDD 2 Framework, revised as of 05.04.17

- Appendix C:  MIDD 2 Initiative Change Summary Table, brief overview of the substantive services changes to MIDD 2 post-MIDD 2 SIP.  Additional updates as of Sept. 2017 can be found in Attachment 6 to this staff report.

- Appendix D: MIDD 2 Biennial Spending Plan 2017-2018, with a summary of expected biennial funding for 2017-2018, by initiative.

- Appendix E:  MIDD 2 2017-2018 Financial Plan, including projected expenditures through 2022

HIGHLIGHTS AND POTENTIAL ISSUES

MIDD 2 Implementation Updates post-MIDD 2 SIP  Based on the MIDD 2 Implementation Plan, nine new and five existing initiatives are delayed by more than one quarter as compared to the MIDD 2 SIP as adopted by Council in 2016.  The Executive has indicated that these are due to ongoing planning for some MIDD initiatives, slower ramp-up than was expected at the time of the SIP and/or the Implementation Plan as transmitted, and in some cases due to intentional delay of new initiatives to address behavioral health system challenges, discussed further below.  Table D shows the new estimated implementation dates as indicated in the MIDD 2 Implementation Plan (as of June 2017).

Table D:  MIDD 2 Initiatives Delayed More than One Quarter as Indicated in Implementation Plan

|  | MIDD Initiative | Est. start date (as of June 2017) | Explanation |
| --- | --- | --- | --- |
| New Initiatives |  |
| PRI-06 | Zero Suicide Pilot | Q3 services | Change service launch date |
| CD-04 | South County Crisis Diversion Services/Center | TBD | Staged planning due to staffing availability |
| CD-09 | Behavioral Health Urgent Care Walk-in Clinic Pilot | Q4 RFP/Q1 2018 services | Ongoing planning |
| CD-14 | Involuntary Treatment Triage Pilot | Q2 | Change service launch date |
| CD-17 | Young Adult Crisis Facility | Q3 services expected |  |
| RR-12 | Jail-based SUD Treatment | Q3 RFP/Q4 contract expected/Q1 2018 services | Delay related to potential state budget impacts |
| S1-01 | Community-driven Behavioral Health Grants | Q4/Q1 2018 RFP expected/2018 services | Staged planning due to staffing availability |
| S1-02 | Behavioral Health Services in Rural King County | Q4/Q1 2018 RFP expected/2018 services | Staged planning due to staffing availability |
| TX-CPPL | Community Court Planning | Q3 RFP | 2018 launch may not be recommended or feasible |
| Existing Initiatives – Revised |  |
| PRI-01 | Screening, Brief Intervention and Referral to Treatment | Q4 update | Staff vacancy |
| PRI-03 | Prevention and Early Intervention Behavioral Health for Adults over 50 | 2018-2019/blended with VHSL funds | Procurement coordination with VSHSL |
| PRI-05 | Collaborative School-based Behavioral Health Services | Q1 2018 RFP expected w/BSK | Procurement coordination with BSK |
| CD-15 | Wraparound for Youth | Q2 expansion RFP/Q3 services | Timed to start of 2017 school year |
| RR-03 | Housing Capital and Rental | Q3 to align with housing funding RFP timelines | Procurement coordination with housing capital RFP |

MIDD 2 Initiative Scope Changes  Many MIDD 2 initiatives are undergoing design or re-design during the first year of MIDD 2.  Post-SIP changes are listed below in Table E. Additional detail is provided in Attachment 6:  MIDD 2 Initiative Changes Subsequent to SIP.

Table E:  MIDD 2 Initiatives with Planned Scope / Design Changes

|  | MIDD Initiative | Planned Change (as of June 2017) |
| --- | --- | --- |
| Scope/Program Changes |
| PRI-02 | Juvenile Justice Youth Behavioral Health Assessments | Possible program changes (in review, to strengthen program) |
| CD-01 | LEAD | Expand geographic scope (based on countywide interest) |
| CD-02 | Youth and Young Adult Homelessness Services | Increased system coordination; scope change (to youth under age 18) |
| CD-16 | Youth Behavioral Health Alternatives to Secure Detention | Increased system coordination; scope change (to youth prior to detention) |
| CD-17 | Young Adult Crisis Facility | Scope change (updated, based on provider input) |
| RR-05 | Housing – Adult Drug Court | Scope change: Removes funding for move-in costs (budget revision) |
| RR-07 | Behavioral Health Risk Assessment Tool for Adult Detention | Scope change: clarifies population target |
| RR-11 | Peer Bridgers and Peer Support Pilot | Scope change(removes expansion) |
| S1-01 | Community-driven Behavioral Health Grants | Clarifies description to conform to changed county procurement rules (3 year period only; removes matching $$ requirement) |
| S1-02 | Behavioral Health Services in Rural King County | Clarifies description to conform to changed county procurement rules (3 year period only; removes matching $$ requirement) |
| S1-03 | Quality Coordinated Outpatient Care [formerly: Caseload Reduction] | Scope change; reflects loss of Medicaid match (shift to “Incentive Pool” for value-based purchasing, behavioral health integration) |
| S1-04 | Workforce Development | Scope change based on planning (adds behavioral health providers, trainings, shift to framework, not plan) |
| Updated Descriptions* |
| CD-07 | Multipronged Opiate Strategies | Reflects Opiate Task Force Recommendations post-SIP |
| RR-09 | Recovery Café | Updates information on site-selection process |
| RR-14 | Shelter Navigation Services | Adds initiative description (not included in SIP) |
| TX-ADC | Adult Drug Court | Updates goals and focus |
| TX-RMHC | Regional Mental Health Court | Clarifies population targets |
| TX-SMC | Seattle Mental Health Municipal Court | Updated description |
| TX-CCPL | Community Court Planning | Reflects current project status; adds goals |
| SP-01 | Special Allocation - Consejo | Adds initiative description (not included in SIP) |

*Non-substantive technical changes to PRI-10: Domestic Violence Behavioral Health Services and System Coordination and RRL01:  Housing Supportive Services not shown above.

MIDD 2 Initiative Re-Allocations  Several initiatives have revised allocations subsequent to the indicated allocations included in the adopted SIP.  These are shown below in Table F. The staff report Attachment 6:  MIDD 2 Initiative Changes Subsequent to SIP provides additional detail.

Table F:  MIDD 2 Initiatives with Changed Allocations

|  | MIDD Initiative | Allocation change (June 2017) |
| --- | --- | --- |
| PRI-06 | Zero Suicide Pilot | Decreased expenditures (transfer to PRI-07) |
| PRI-07 | Mental Health First Aid | Increased expenditures (transfer from PRI-06) |
| PRI-09 | Sexual Assault Behavioral Health Services | Decreased expenditures (transfer to PRI-10 based on provider request) |
| PRI-10 | Domestic Violence Behavioral Health Services and System | Increased expenditures (transfer from PRI-09 based on provider request) |

Additional Information on External Behavioral Health System Challenges  Subsequent to the transmittal of the MIDD 2 Implementation Plan and the MIDD 2 Evaluation Plan, the Executive has noted several external behavioral health system challenges, and their potential impacts on the MIDD initiatives and biennial spending plan, including:

- Ongoing uncertainty about the Affordable Care Act, including potential repeal or revision

- OEFA projections of reduced MIDD revenue ($1 million for the 2017/2018 biennium)

- Challenges with provider recruitment/retention and impact of reduced Medicaid rates for behavioral health reimbursement

- Rapid behavioral and physical health integration for Medicaid service delivery providers in King County (King County as a region recently signed a MOU with the five insurance plans providing Medicaid payments to be a mid-adopter of behavioral-physical health integration, which will allow the region to draw down additional state funds to help incentivize provider compliance with integration requirements).

New Concept Subsequent to Implementation Plan Transmittal: Incentive Pool  Changes that Executive staff have indicated subsequent to transmittal of the Implementation Plan include intent to create an incentive pool for providers to support system transformation. Examples of incentive purposes listed by the Executive as under consideration include:

- Rapid access to treatment

- Service utilization increases

- New or expanded physical/behavioral health integration partnerships and/or commitment to a learning collaborative

- Functional assessment implementation, associated measurable client improvement

- Improving physical health screening and coordination.

Alongside some Medicaid dollars, the Executive indicates that MIDD 2 funding that could be redirected to this incentive pool, includes:

- Redesign and repurpose of the Quality Coordinated Outpatient Care initiative funds to support strategic initiatives

- One-time funds resulting from potential delay beyond the 2017-2018 biennium of the South County Crisis Diversion and Behavioral Health Urgent Care Walk-In initiatives

- One time funds resulting from intentional deferral of several initiatives to 2018.

Updated Spending Plan The updated MIDD 2 spending plan (as of September 2017) attached as Attachment 7 to this staff report shows a zero undesignated fund balance at the end of the biennium.  The Executive has noted projecting a total 2017-2018 underspend of approximately $5.5 million, reflecting a combination of the factors noted above:  New MIDD initiatives that have not yet begun, ongoing planning for some MIDD initiatives, slower ramp-up than was expected at the time of the SIP and/or the Implementation Plan as transmitted, and an estimate of typical underspend on existing initiatives already in operation. The Executive has indicated that it is working to develop contingency options that could necessitate commensurate changes to MIDD funding allocations and programming based on behavioral health system challenges.

Based on Council staff’s analysis, the MIDD 2 Implementation Plan complies with the requirements set forth in Ordinance 18407 and it is a policy choice for Council whether to approve the MIDD 2 Implementation Plan as transmitted or direct any changes.

INVITED:

- Jim Vollendroff, Behavioral Health and Recovery Division Director, Department of Community and Human Services

- Chris Verschuyl, Strategic Program Planner, Department of Community and Human Services

ATTACHMENTS:

- Proposed Motion 2017-0327 (and its attachments)

- MIDD 2 Implementation Plan Appendices in correct order

- Transmittal Letter

- Cross-walk Between MIDD 2 Implementation Plan Required Components per Ordinance 18407 and Proposed MIDD 2 Implementation Plan

- MIDD 2 Initiative Procurement Approach Status, Nov. 2017

- MIDD 2 Initiative Changes Subsequent to SIP

- MIDD Spending Plan, Sept. 2017

- MIDD RPC Briefing 12-5-17 PowerPoint Presentation

Proposed Motion 2017-0326, transmitted concurrently, would approve the MIDD 2 Evaluation Plan, and is briefed separately.  Both are required and collectively constitute a two-part plan for purposes of oversight, implementation and evaluation of the MIDD 2 Service Improvement Plan.

Ordinance 18406

In 2005, the Washington State legislature authorized counties to implement a one-tenth of one percent sales and use tax to support new or expanded chemical dependency or mental health treatment programs and services and for the operation of new or expanded therapeutic court programs and services.  RCW 82.14.460.

See 2017-2018 Financial Plan March 2017 Report:  MIDD Fund.  MIDD 2 Implementation Plan, Appendix E.  Out year projections assume revenue growth per March 2017 OEFA forecasts and King County Office of Performance, Strategy and Budget planning assumptions (note 5).

Strategies were required by Ordinance 17988 to be evidence and best or promising practice-based, incorporate goals and principles of recovery and resilience, integrate and expand the sequential intercept model that addresses the criminalization of mentally ill individuals, and reflect the county’s Equity and Social Justice Policy goals.

In re the Detention of D.W. et al.

SIP p 33

The SIP notes that the MIDD 2 Framework is intended to be iterative and flexible, to respond to new information.

See Reviser’s Note:  Ordinance 18406 (Proposed Ordinance 2016-0427) was apparently intended.

Ordinance 18407, codified at 4A.500.300.

The updated framework is also included as Appendix G to the proposed MIDD 2 Evaluation Plan.

MIDD 2 Implementation Plan, p. 4.

Staff report analysis omits minor internal discrepancies between dollar figures provided in the spending plan and the initiative descriptions.  The Executive indicates that all figures provided in the spending plan are correct.

The MIDD 2 Implementation Plan notes that of the 22 new initiatives, 14 are to be directly allocated to providers following the adopted MIDD 2 decision model on when to employ RFPs/competitive procurement (of these 14, 9 had been contracted as of the transmittal date of PM 2017-0327).  The remaining eight will go through some type of procurement.  MIDD 2 Implementation Plan, Section 5, p. 27

The following initiatives note that no formal community engagement is occurring at this time:  Sexual Assault Behavioral Health Services (PRI-09); Outreach and In Reach System of Care (CD-03); High Utilizer Care Teams (CD-05); Adult Crisis Diversion Center, Respite Beds, and Mobile Behavioral Health Crisis Team (CD-06); Children’s Domestic Violence Response Team (CD-08); Behavior Modification Classes at Community Center for Alternative Programs (CCAP) (CCAP) (RR-02); Adult Drug Court (ADC) (TX-ADC); Special Allocation Consejo (SP-01).

Section 2 states that the Framework has been revised subsequent to the adoption of the SIP, that it is intended to be a living document updated over MIDD 2 to reflect specific programmatic and services changes or other drivers.  MIDD Implementation Plan, p. 11 and p. 13.

Section 2 notes that MIDD 1 initially funded only the expansion of therapeutic courts, but due to a change in state law, MIDD 1 funds were later allowed to fund most of the base costs of therapeutic costs.

The Executive notes that some headline indicators were updated because population indicators were not available for the MIDD-specific population.  Headline indicators are addressed further in the MIDD 2 Evaluation Plan, transmitted concurrently with this plan, with Proposed Motion 2017-0326.

DCHS manages the budget; behavioral health systems programmatic development; oversight of the RFP, memorandum of agreement (MOA), and contracting processes; and evaluation of MIDD 2.

These are exemplified as Public Health, the Prosecuting Attorney’s Office and Judicial Administration.  Listed roles may include receiving direct allocations or procuring support for MIDD 2 initiatives that they manage.

The Implementation Plan notes that all initiatives subject to RFP process (Appendix F contains decision-making tool on competitive bidding).

Section 3 notes that coordination with funding streams from Best Starts for Kids and the Veterans and Human Services Levy can expand resources to bring programs to scale for new populations, and allow lessons learned across levies. Framework alignment with BSK and VHSL will allow for common results and indicators between the three initiatives, increasing the county’s ability to measure the combined effectiveness of the three local revenue sources for human services funding.  Executive staff across the three levies are working together to:  1) Analyze cross-system intersections in strategies and initiatives; 2) Identify collaboration and alignment opportunities; 3) conduct joint request for proposal processes; 4) utilize common language and definitions; 5) develop shared data, reporting and dashboards.  Implementation Plan, p. 17.

Value-based purchasing approaches are listed to include:

- Reducing fragmentation across systems,

- Increasing flexibility of services and coordination of care with strong emphasis on prevention, recovery

- Elimination of disparities for marginalized populations

- Evaluation of programs on meeting MIDD 2 policy goals

Section 4 further notes the distinction between performance measures and headline indicators.  Headline indicators are a “Results-based Accountability (RBA)”-informed approach that creates population accountability through population indicators (known as “headline indicators”) which assess well-being of individuals throughout King County overall. Performance measures are a RBA approach that establishes performance accountability through performance measures which assess well-being of the individuals and families directly served by MIDD-funded programs. The MIDD Evaluation Plan details further MIDD evaluation activities and performance measure information.

Section 4 notes that review of lessons learned and potential improvements, system gap analysis, and consultation with stakeholders and/or experts shaped MIDD 2.  New unmet needs, service access issues, or care continuum gaps that had been identified by community members, stakeholders or policymakers helped drive changes and new initiatives.

Section 4 notes that many of the design efforts for MIDD 2 will proceed next to a community input phase beginning later in 2017, to provide opportunities for groups and organizations to help shape, validate and/or adjust recommendations generated through initial planning work; staff will leverage opportunities for input, including other community outreach processes conducted under the auspices of BSK and/or VHSL.

The state will purchase all physical and behavioral health services through a single managed care contract with eligible Managed Care Organizations, and roles/responsibilities of Behavioral Health Organizations will then change (King County’s Behavioral Health and Recovery Division has been acting as the King County BHO since 2016).

This is a waiver from the standard state Medicaid approaches and as these projects are designed in King County, they could have impact on initiatives funded by MIDD and therefore lead to reevaluation of MIDD 2 investments so that funding is not duplicative and the region is maximizing both fund sources.

At the time of the writing of the Implementation Plan, Congress was actively considering repeal of the Affordable Care Act.  Section 7 notes that the ACA allows MIDD 2 funding to be directed towards services not covered by Medicaid, augmenting the behavioral health system, or to serve the remaining individuals who are uninsured.  Section 7 recognizes that changes at the federal level may necessitate adjustments to MIDD 2 Initiative implementation timelines and/or initiatives as a whole.

Executive staff indicates that because King County’s rate is now at the higher end of a lower rate band, King County will lose approximately $8 million in Medicaid matching funding over the biennium, significantly reducing support to MIDD 2’s SI-03 Quality Coordinated Outpatient Care (known under MIDD 1 as the Workload Reduction initiative), resulting in expected revisions to this initiative.

This process is also outlined in graphic format in the SIP, in Appendix I.

The framework modifies the MIDD 2 SIP framework, listing the overall MIDD 2 Result, adopted MIDD 2 Policy Goals to achieve the result, the MIDD 2 theory of change (how MIDD will get to the result), the six MIDD 2 headline indicators, the five MIDD 2 strategy areas, and sample service quantity and quality performance measures and impact performance measures for each strategy area, to be refined after specific programs/services are selected.

The Change Summary Table does not include:  Performance measure changes between the SIP and the Implementation Plan, information about community engagement that was added to the Implementation Plan, technical and wording changes that were not substantive initiatives delayed for only one quarter.

Delays of one quarter or less are not included in this analysis.

Additional information provided by the Executive subsequent to transmittal of the Implementation Plan indicate that this initiative will be deferred, with 2017-2018 funds included in the new provider Incentive Pool, described in the Highlights and Potential Issues section of this staff report.

Additional information provided by the Executive subsequent to transmittal of the Implementation Plan indicate that this initiative will be deferred, with 2017-2018 funds included in the new provider Incentive Pool, described in the Highlights and Potential Issues section of this staff report.

These topics have been included on recent MIDD Advisory Committee agendas.

Responses to Council Staff Questions Regarding the MIDD Implementation and Evaluation Plans, 9.27.17

Note that if the Council wishes to reallocate funds between strategies, this could also necessitate an amendment to the county budget.