| TASK | Responsibility CVI liaison Contact | ACTION ITEMS / STATUS |
| --- | --- | --- |
| REFERENCES & DATA |  |  |
| SPD Crime Report | Seattle Police CVI lead: Steve, Tony Contact: Steve, Tony | Monthly crime incidence report by block for East and west sides of 3rd Ave. |
| KC employee security incident report web portal | KC FMD CVI lead: Tony Contact: KC FMD, Collin Sanders, Facilities Security Manager | Security Incident Report Portal for KC employees to report security concerns; monthly incident reports summarized by FMD. Employees receive automated acknowledgement at Confirmation (“Thank you for submitting a report. You may be contacted by FMD Security for follow-up.”) Action (completed): Increased visibility of web resource with a) the addition of link on the KC.gov Employees web portal at two locations: Employees/My Workplace and Employees/My Tools, see Portal; and b) quarterly articles in King County Employee News highlighting reporting tool. Action (completed): Articles on CVI activities in King County Employee News (circulation 14,000), Oct. 27, 2016, Nov. 15, 2017 Action (completed): New employees -- include information on new employees portal and in KC New Employee Orientation (NEO) materials (Meghan McKnight, DES and Cameron) Action (ongoing): Periodic reminders to KC Employee News to use security incident reporting tool (Employee News in 2018: April 10 (All employee email), July TBD, Oct TBD - HRD Jason Argo) |
| Public security incident report web portal | CVI lead: TBD Contact: Malinda You, Cameron Satterfield, Paul Manolopoulos | Action: Develop portal for litigants, jurors and the public to report incidents – to be located on the Court's section of the website. Posters in juror orientation room (Malinda You and Greg Wheeler). Leads - Paul Manolopoulos and Cameron Satterfield (3/7/18) |
| CVI Annotated Map | DES CVI lead: Meg Contact: Meg | Action (completed): Map notes agency responsible for property, areas cleaned by contracted service providers, location of garbage cans, security responsibilities, etc. |
| SDOT policy | SDOT sidewalk policy | Property owner is responsible for maintenance of sidewalk, garbage and cleaning |
| Samis (Drexel Building) Information |  | http://samis.com/Frame_retail.html |
| One City Center | TBD | http://onecentercity.org/ |
| Lazarus Day Center relocation | City of Seattle CVI lead: TBD | Action (completed): Moving Dec. 2017, outreach to begin soon, plans on track (BG, 8/31/17) Action: Chief Seattle Club. Inquire as to how Lazarus space will be used once they move. (MG request to Robert Stowers 3/15/18) |
| CVI Committee Membership |  |  |
| GARBAGE REMOVAL |  | Metropolitan Improvement District - MID (for DESC properties) DESC (maintenance staff) Community Corrections work crew (for downtown campus), DAJD Metro transit (for tunnel and bus stops) KC Facilities Maintenance Division - FMD (for Courthouse side) Seattle Parks (for City Hall Park and Fountain) Sound Transit, effective 2018 |
| Bus stops and Pioneer Square transit station | KC Metro Transit CVI lead: Rob Contact: Dave Jager, Superintendent shelter cleaning group Sound Transit CVI lead: Steve | Location: See CVI annotated map (can at 3rd and Jefferson St. and at 3rd Ave. @ James St.) Frequency: Once/day, 7 days/week (graveyard shift) Action (completed): Increased trash collection beginning in May (community service workers) and will evaluate in September. TBD |
| East side of 3rd Ave (front of Courthouse) | King County FMD CVI lead: Tony Contact: FMD Customer Care hotline; 206-477-9400 CustomerCareServices.FMD@kingcounty.gov | Location: See CVI annotated map |
| West side 3rd Ave. | DESC & Samis DESC CVI liaison: Daniel Contact: Daniel Samis CVI liaison: TBD Contact: TBD | Location: See CVI annotated map; no cans on West side from Jefferson St. Alley to James St. Frequency: Daily, per MID (effective May 2017) Action (completed): DESC will continue to work with MID to remove daily trash before business activity picks up Action (completed): DESC will stay in contact with MID to insure that they continue the recent increased level of garbage collection and power washing services; may consider expansion of MID contract if resources are available. |
| City Hall Park (City Hall Park) Prefontaine Place Fountain (Prefontaine Place) | City of Seattle, Parks CVI lead: Robert Contact: Robert | Frequency: Garbage and grounds cleaned 2-3 x day 7 days a week (Mon, Tuesday cleaned 2 x/day; Wed-Sunday 3 x/day) |
| Downtown Campus | Community Corrections Work Crew - DAJD CVI lead: Tony Contact: Ameer Faquir, (FMD); Seth Oakes (DAJD) | Location: Downtown Campus (KCCH, Administration Building, Yesler Building, Jail, Chinook, etc.), all sidewalks, alleys, KCCH loading dock area SOW: Garbage pickup, sweeping, light washing (no power washing), raking leaves, emptying garbage cans, feces removal, etc. Frequency: Mon-Sat mornings; afternoons on Mon Action (completed): Increased use of community corrections work crew |
| SIDEWALK CLEANING |  | Metropolitan Improvement District - MID (for DESC properties) Community Corrections work crew (for downtown campus) Metro transit (for tunnel and bus stops) KC Facilities Maintenance Division - FMD (for Courthouse side) Seattle Parks (for City Hall Park and Fountain) Community corrections work crew (for downtown campus) |
| Courthouse sidewalk perimeter: FMD power washes 2-3 times/week and general cleaning daily | KC FMD CVI lead: Tony Contact: FMD Customer Care 206-477-9400 CustomerCareServices.FMD@kingcounty.gov | Action (completed): Increase frequency as of week of July 9, 2017 |
| Pioneer Square Tunnel entrance and bus shelters: | KC Metro Transit CVI lead: Rob Contact: Dave Jager, shelter; Don Brewer, tunnel Sound Transit CVI lead: Rob | Frequency: Tunnel: Power washing 7 days/week (graveyard shift), area - no specific footage Bus stop shelters: Power washing 7 days/week, area - 4’ surrounding shelter TBD |
| West side of 3rd Ave (and alley behind The Morrison) | DESC CVI lead: Daniel Contact: Daniel Samis Land Co. | Metropolitan Improvement District (MID) on contract to clean and provide outreach services on West side of 3rd Ave. (City Hall Park and Fountain for outreach only). Action (completed): MID increased services effective 7/10/17 Person washing: 3 passes/day every day with bucket, sweeping and trash Green machine: 3 passes/day every day (e.g. the push machine) Pressure wash: 5 days/week on weekdays in morning |
| Loading dock area (Jefferson St. alley) | KC FMD CVI lead: Tony Contact: Collin Sanders, KC FMD, Facilities Security Manager | Frequency: 2 times/week Action (completed): No formal agreement between City and County on Jefferson St. closure, City property FMD maintains. |
| JUROR ASSISTANCE |  |  |
| Route recommendations (map walking) | Superior Court CVI lead: Paul Contact: Paul | Action (completed): Added suggested walking directions to Admin. Building on Juror Information section of Superior Court web site at KC Juror Information Action (completed): Linked QR code on juror postcards with link to these directions Action (completed): Move “Transit Options” to the top of section on transportation option on KC Admin Bldg. web portal, per KC transportation/climate priorities |
| Signage improvements - Metro Tunnel | Metro Transit CVI lead: Rob Contact: Rob | Action (completed): Improved signage in Tunnel on mezzanine and exits directing people towards government facilities. |
| Wayfinding (escort from bus stop) | Metro Transit CVI lead: Rob Contact: Rob | Jurors arrive for orientation Mon and Weds at 8:00 am Action (completed): Not recommended at this time. |
| SECURITY |  |  |
| Metro Transit Police (KCSO) | Metro Transit CVI lead: Rob Contact: Major Dave Jutilla, Public Safety | Presence in front of Courthouse/3rd Ave; security coverage area 30’ at tunnel and at bus stops Action (completed): Schedule clarification – schedule varies but presence is consistent, with Bicycle Officers focusing on tunnel area |
| SPD Officers | SPD CVI lead: Steve Contact: Steve | Action (completed): Schedule clarification - presence in front of Courthouse/3rd Ave and in Park; schedule changes based on other city-wide priorities. Action (completed): All emergency calls from the Courthouse will be immediately flagged for SPD supervisor screening, per SPD 2.22.18 Action (completed): Communicate all concerns to SPD regarding encampment in front of Samis property in the Drexel building (3/22/18) |
| FMD Security | KC FMD CVI lead: Tony Contact: Collin Sanders, Facilities Security Manager | Action (completed): Effective July 2017, 2-3 Officers 6:30am - 8:00 am, 12:00pm-1:50pm Mon-Fri Security inside Courthouse for screening after-hours. 07.00hrs – FMD Security Officers are in attendance at the 3rd Ave. Courthouse entrance. Security team will maintain a presence at the 3rd Ave. Courthouse entrance with a stronger presence when staff and jurors arrive (06.00hrs – 08.30hrs), lunch breaks (12.00hrs – 13.30hrs), and close of business. Intermittent roving by FMD Security Officers. Security to accompany custodial teams while they clean the perimeter of the building (pressure washing – 06.00hrs – 07.00hrs - M, W, F). FMD Security contact SPD for any escalated incidents (hostile or non-responsive individuals). |
| KCSO Marshalls | KCSO CVI lead: Scott Contact: KCSO Marshalls | Inside Courthouse screening Court protection during business hours |
| Jurisdictional role clarification and coordination | KC FMD CVI lead: Tony Contact: Tony | Action (completed): Convene all security-related groups - SPD Officers, KCSO Marshalls, Metro Transit Police, FMD Security to clarify roles/issues and report findings Action: Annual review of coordination - include Sound Transit, DESC Safety Patrol and MID Outreach representatives at future security coordination meeting – schedule for Q3 2018 (convener TBD). |
| 4th Ave. Entrance | Superior Court CVI lead: Paul Point of Contact: Paul | Superior Court Ad hoc Safety committee request to open 4th Ave entrance (annual staff cost approx. $400K) Action (completed): Council approved funding to open entrance for 16 hours/week. 7:45am-9:45am; noon-2:00pm). Council requested measurement of impact and will be increasing signage. Will open in January 2018. Patti Cole-Tindall will be point of contact. Action: Evaluation of impact, deadline TBD |
| DESC Safety Patrol | DESC CVI lead: Daniel Contact: Daniel | One FT DESC staff position, cited on sidewalk during business hours. Focus is interaction with Morrison clients; some interaction with non-Morrison people. |
| Courthouse safety/security assessment | KC FMD CVI lead: Tony Contact: Collin Sanders, Facilities Security Manager | Action (completed): Briefed Judge Rogers at Dec. 1, 2017 (Caroline, Tony, Collin) Action (completed): FMD security assessment completed, per request from Superior Court Ad hoc security committee Action (completed) Omnibus request $200,000 for 4-5 bullet resistant windows in KCCH Action (completed): Omnibus request for sidewalk cleaning and improved lighting. Action: Increase outside lighting which is activated by motion in strategic locations such the Jefferson Street side of City Hall Park, loading dock, 3rd & 4th Ave. entrances. Deadline May 29, Approx. $30k-$40k Action: Install a gate at the entrance to the Courthouse loading dock to secure the loading dock.(King County FMD) Deadline: June 30, Approx. $40k Action: The 3rd Ave. rotunda, center door is currently non-operational. Until the door is repaired, barriers should be installed so that the alcove area is not accessible. Deadline: March 30 |
| TRANSIT FACILITIES |  |  |
|  | Metro Transit CVI lead: Rob Sound Transit CVI lead: Steve Tucker | Action (completed): Evaluation completed regarding relocation of 4th Ave bus stop in front of Admin building and removal of seating. It is not recommended at this time, but could be further explored as part of One City effort (11/15/17) Action: Research short-term improvements TBD and longer-term structural changes to Pioneer Transit station to increase safety and visibility (11/15/17 meeting) |
| JEFFERSON ST. ALLEY / LOADING DOCK |  |  |
|  | KC FMD CVI lead: Tony Contact: Collin Sanders, Facilities Security Manager | City right of way, there should be no cars or trucks in the area, per signage; loading dock is still active; bollards in place on the west end of Jefferson at 3rd Ave. Cleaning: Seattle Parks responsible for 1-2’ into alley, FMD responsible for the rest. Action (completed): Researched historic documentation on closure – seeking to clarify responsibilities of County and City (Tony, 8/17). No documentation found. Action (completed): Installation of new No parking / Tow signage on east side of alley; SPD parking enforcement will begin in March 2018 (per Peter Ahlstrom, PEU) Action: Feasibility study and permitting to install gate at East end of Jefferson at 4th Ave.; need for inclusion in 2019-20 budget for gate and capital project manager. Once budget is approved, a completion date can be determine (approximately Feb. 2019), per Collin 3/18. |
| FORSTON SQUARE |  |  |
|  | Contact: TBD | Parks property @ 2nd Ave & Yesler Way - southeast corner Action: Cherie to confirm City point of contact (2/15/18) |
| HYGIENE FACILITY |  |  |
|  | City of Seattle CVI lead: Robert Stowers, Parks Contact: Robert | Siting a bathroom facility in Pioneer Square or City Hall Park is not currently on the list of Parks priorities (2017). Bathrooms are currently available at Fire Stations, Precinct offices citywide, and KCCH during working hours. City has considered a bathroom at Occidental Square, in 2017 CM Bagshaw evaluated siting at Occidental Square, but costs were prohibitive. Seattle piloting Portland loo style bathroom in Rainier Beach currently and scheduled to located facilities in Ballard and U District in 2018. Could consider for Pioneer Square in 2018 http://theloo.biz/. Action (completed): Access map of public bathrooms in CVI (Gary Johnson (City of Seattle) (Oct. 2017) Action (completed): FMD prepared feasibility report to Council per request, March 2018. |
| CITY HALL PARK PREFONTAINE PLACE FOUNTAIN |  |  |
| City Hall Park Prefontaine Place | City of Seattle CVI lead: Robert Contact: Robert | Agreed upon goal to make City Hall Park and the Prefontaine Fountain area a safe, vibrant, destination location in the south downtown area and create the social changes needed to sustain physical improvements. Park and fountain are not currently on Parks’ priority list for improvements (2017). Fountain was a gift from the Prefontaine family to the City of Seattle. Actions: short-term Short term basic clean-up of Prefontaine Fountain and City Hall Park (Dec. 2017-May 2018) Change light lumens (LEDs are low cost) that could improve area while jurors and KC employees in the vicinity. Parks will research accessing energy conservation money), 2/22/2018, Robert Review and reset maintenance plan (Parks) Activation Plan: Improvement planning, inclusion in 2021-2026 plan/budget recommendations; programming options (evening activities, food trucks) Fountain: Research options for relocation (Parks) GIS Heat Map – evaluate number of residents living nearby (Parks) Dialogue on security collaboration - SPD, FMD, KCSO, MID, DCSA, etc. (CVI Committee) Actions: Long Term Prepare funding request for inclusion in Parks 2021-2026 six-year major capital improvement request, planning to begin Jan. 2018; Parks expects to revisit 2005 City Hall Park design – (funded at $4-5 million but not implemented) and include Prefontaine fountain redesign, Design and include Park and Fountain improvements in Park’s 2021-2026 six-year capital budget request. Park will bring updates on process, ideas, and deadlines to CVI Committee once confirmed, per Michael S. 2/22/18 Assess feasibility of creating “Friends of City Hall Park” Group, including businesses, 3rd and Washington workforce housing, KC, City, community based organizations, etc. |
| DSA 3rd Ave & One City Center http://onecentercity.org/ |  |  |
|  | CVI liaison: Maureen Thomas, FMD Others TBD: Metro & Sound Transit | Action (completed): Liaison to One Center City Reports; Downtown Seattle Association Third Ave. project Action: Research status, participants: City Hall Park and Prefontaine Fountain have been identified as a “Quick Fix” priority. Strategic vision is a revitalized 3rd Ave. |