| TASK | Responsibility Contacts | ACTION ITEMS / STATUS |
| --- | --- | --- |
| DOWNTOWN AREA PLANNING EFFORTS |  |  |
| Alliance for Pioneer Square Alliance | Contact: Lisa Howard, Executive Director | Parks and Gateways Project Concept Plan final report April 2016 (see City Hall Park pages 48-60) |
| Downtown Seattle Association (DSA) DSA | Contact: Jacqueline Gruber, Senior Economic Development Manager | Presentation to CVI Committee DSA presentation 6.28.18 Third Ave Design Vision ; DSA consultant |
| One Center City One Center City City of Seattle, Office of Planning and Community Development | Contact: Gary Johnson, Coordinator | Advisory Group members Action (completed): Invited to present at Sept. 2018 Committee meeting |
| Downtown Civic Campus Plan | Contact: Maureen Thomas, KC FMD | Status: Consultant (Northwest Studio) begins initial phase, June 2018. Action: Invite to future CVI Committee meeting |
| Commute Seattle Commute Seattle | Contact: Jonathan Hopkins, Executive Director | Quicks wins task force – 2018. CS supported by the Downtown Transportation Alliance (DTA) - executive leadership from Downtown Seattle Association, King County Metro, SDOT, Sound Transit as well as rotating private sector representation. Action (completed): Invited to present at Sept. 2018 Committee meeting |
| One Table – a community approach to homelessness and affordability One Table | Contact: TBD | One Table Work Group members |
| CITY HALL PARK & PREFONTAINE PLACE |  |  |
| City Hall Park Prefontaine Place | Seattle Parks Contacts: Robert Stowers (Operations) Michael Shiosaki (Planning) Marlan Teeters (Security) Victoria Schoenburg (Activation) Lisa Nielsen (Activation, “Friends of/Public Benefit Partnership) Andy Sheffer (lighting) Seattle Parks - Board of Park Commissioners Meets second and fourth Thurs/month Seattle Parks District Oversight Committee | Agreed upon goal to make City Hall Park and Prefontaine Place area a safe, vibrant, destination location in the south downtown area and create the social changes needed to sustain physical improvements. Park and fountain were not on Parks’ priority list for improvements in 2017 but has now been elevated to priority status. Fountain was a gift from the Prefontaine family to the City of Seattle. Action (completed) Clean-up: Prefontaine Fountain and City Hall Park (completed May 2018) Activation: August 6 – Sept. 30 (Victoria) Tree limbing Lighting: Standard globes have been cleaned inside and out; All luminaires have been replaced with LED; conductors are big enough for 100 amps; power available for limited festival lighting ACTIONS: SHORT-TERM Lighting improvements GIS Heat Map: Gather data to inform usage / needs assessment as part of planning for Park renovation (number of nearby residents current and projected) Sept. 2018 update (Robert) ACTIONS: LONG TERM Funding request 2021-2026 six-year major capital improvements Timeline: Planning Jan. 2018 - Dec. 2019 Design Resources: Alliance for Pioneer Square Parks and Gateways Project recommendations, 2005 City Hall Park design, UW School of Architecture recommendations (include activation plans in budget) Process: Update on process, design ideas, initial schematics, and input from CVI Committee and community (Michael Shiosaki) Board of Parks Commissioners and Seattle Parks District Oversight Committee: Letters supporting park improvements from stakeholders (e.g., CVI Committee, DSA, Alliance for Pioneer Square, Civic Campus Oversight Committee, Bar Association, other) (date TBD) |
| “FRIENDS OF” / “PUBLIC BENEFIT PARTNERSHIP” CITY HALL PARK & PREFONTAINE PLACE (Fortson Square) |  |  |
|  | Lead: TBD Contact: TBD | Action (completed): Researched best practices: Strong organizational structure (e.g., DSA/Alliance for Occidental); Clear mission and goals – developed in the context of the broader neighborhood dynamics and challenges; Clear roles/responsibilities among partners; Adequate resourcing (staffing and many associated costs); Comprehensive community-stakeholder engagement (e.g., businesses, residents, current park users, community based organizations, etc.); Implementation of low-hanging fruit - to build momentum (Future outreach per Seattle Parks: Freeway Park Association, Friends of Waterfront Seattle, Occidental Park (lead TBD) - input from Seattle Parks and King County Parks, June 2018 |
| FORTSON SQUARE |  |  |
| Right-of-way triangle area @ 2nd Ave & Yesler Way - southeast corner | SDOT Contact: Angela Steel | Action (completed): Discuss study Crime Prevention Through Environmental Design: Assessment of Fortson Square, prepared by Seattle Neighborhood Group for Alliance for Pioneer Square, 2017 (Lisa Howard, Sept. 2018 CVI meeting) Action (completed): Discuss maintenance, security, activation and plans for future (Angela Steel, Sept. 2018 CVI meeting) |
| REFERENCES & DATA |  |  |
| SPD Crime Report | Seattle Police Contact: Steve Tucker | Monthly crime incidence report by block for East and west sides of 3rd Ave. Action (ongoing): Report at CVI meetings |
| KC Employee Security Incident report | KC FMD CVI lead: Tony Wright Contact: KC FMD, Collin Sanders, Facilities Security Manager | Security Incident Report Portal for KC employees to report security concerns; monthly incident reports summarized by FMD. Employees receive automated acknowledgement at Confirmation (“Thank you for submitting a report. You may be contacted by FMD Security for follow-up.”) Action (completed): Increased visibility of web resource with a) the addition of link on the KC.gov Employees web portal at two locations: Employees/My Workplace and Employees/My Tools, see Portal; and b) quarterly articles in King County Employee News highlighting reporting tool. Action (completed): Articles on CVI activities in King County Employee News (circulation 14,000), Oct. 27, 2016, Nov. 15, 2017 Action (completed): New employees -- include information on new employees portal and in KC New Employee Orientation (NEO) materials (Meghan McKnight, DES and Cameron) Action (ongoing): Report at CVI meetings Action (ongoing): Periodic reminders to KC Employee News to use security incident reporting tool (Employee E-News in 2018: April 10, July, August, Jason Argo) |
| Juror Security Incident Report | CVI lead: Paul Sherfey Contact: Paul Manolopoulos | Juror Incident Report Portal Action (completed) Develop security incident report portal for jurors, litigants, and the public; Per GR36, incidents to be reported monthly to the Washington State Administrative Office of the Courts. Action (ongoing): Report at CVI meetings |
| Encampment Navigation Team | Seattle Finance and Administrative Services (FAS) Contact: August Drake-Ericson | Communicate concerns to August - key words: Bio-waste, needles, blocked sidewalk Action (ongoing): Report at CVI meetings |
| CVI Annotated Map | DES Contact: Meg Goldman | Action (completed): Map notes agency responsible for property, areas cleaned by contracted service providers, location of garbage cans, security responsibilities, etc. |
| SDOT sidewalk policy | SDOT sidewalk policy | Property owner is responsible for maintenance of sidewalk, garbage and cleaning |
| Samis (Drexel Building) | N/A | http://samis.com/Frame_retail.html Action: Requested contact from Lisa Howard (6/2018) |
| Lazarus Day Center | Catholic Community Services of King Count Contact: Flo Beaumon, Associate Director Chief Seattle Club Contact: Colleen Echohawk, Executive Director | Action (completed): Per Flo Beaumon, Lazarus Day Center expects to move into a new space on Rainier Ave. S. by July. CCS is selling the Leroy Helms building which houses the Lazarus Day Center to the Chief Seattle Club and expects to close that deal at the end of June. Chief Seattle Club will build affordable housing for Natives with other cultural supporting elements (5/22/18) |
| GARBAGE REMOVAL |  | Metropolitan Improvement District - MID (for DESC properties) DESC (maintenance staff) Community Corrections work crew (for downtown campus), DAJD Metro Transit (for tunnel and bus stops) Sound Transit (tunnel) KC Facilities Maintenance Division - FMD (for Courthouse side) Seattle Parks (for City Hall Park and Prefontaine Place) |
| Bus stops and Pioneer Square transit station | KC Metro Transit CVI lead: Rob Gannon Contact: Dave Jager Sound Transit CVI lead: Steve Tucker | Location: See CVI annotated map (can at 3rd and Jefferson St. and at 3rd Ave. @ James St.) Frequency: Once/day, 7 days/week (graveyard shift) Action (completed): Increased trash collection beginning in May (community service workers) and will evaluate in September. Transit station Sound Transit transition: Through 2019 |
| East side of 3rd Ave (front of Courthouse) | King County FMD CVI lead: Tony Wright Contact: FMD hotline; 206-477-9400 CustomerCareServices.FMD @kingcounty.gov | Location: See CVI annotated map |
| West side 3rd Ave. | DESC Contact: Daniel Malone Samis Land Co. Contact: TBD | Location: See CVI annotated map; no cans on West side from Jefferson St. Alley to James St. Frequency: Daily, per MID (effective May 2017) Action (completed): DESC will continue to work with MID to remove daily trash before business activity picks up Action (completed): DESC will stay in contact with MID to insure that they continue the recent increased level of garbage collection and power washing services; may consider expansion of MID contract if resources are available. |
| City Hall Park Prefontaine Place | City of Seattle, Parks Contact: Robert Stowers | Frequency: Garbage and grounds cleaned 2-3 x day 7 days a week (Mon, Tuesday cleaned 2 x/day; Wed-Sunday 3 x/day) |
| Downtown Campus | Community Corrections Work Crew - DAJD CVI lead: Tony Wright Contact: Ameer Faquir, (FMD); Seth Oakes (DAJD) | Location: Downtown Campus (KCCH, Administration Building, Yesler Building, Jail, Chinook, etc.), all sidewalks, alleys, KCCH loading dock area (garbage pickup, sweeping, light washing (no power washing), raking leaves, emptying garbage cans, feces removal( Frequency: Mon-Sat mornings; afternoons on Mon Action (completed): Increased use of community corrections work crew |
| SIDEWALK CLEANING |  | Metropolitan Improvement District - MID (for DESC properties) Community Corrections work crew (for downtown campus) Metro Transit (tunnel and bus stops) Sound Transit (tunnel) KC Facilities Maintenance Division - FMD (for Courthouse side) Seattle Parks (for City Hall Park and Prefontaine Place) |
| Courthouse sidewalk perimeter | KC FMD CVI lead: Tony Contact: FMD Customer Care 206-477-9400 CustomerCareServices.FMD@kingcounty.gov | Action (completed): Increased frequency as of July 2017; Power wash 2-3 times/week and general cleaning daily |
| Pioneer Square Tunnel entrance and bus shelters: | KC Metro Transit CVI lead: Rob Gannon Contact: Dave Jager, shelter; Don Brewer, tunnel Sound Transit CVI lead: Steve Tucker | Frequency: Tunnel: Power washing 7 days/week (graveyard shift), area - no specific footage Bus stop shelters: Power washing 7 days/week, area - 4’ surrounding shelter ST responsible for tunnel, effective March 31, 2019 |
| West side of 3rd Ave (and alley behind The Morrison) | DESC CVI lead: Daniel Malone Contact: Daniel Malone Samis Land Co. | DSA’s Metropolitan Improvement District services (MID) on contract to clean and provide outreach services on West side of 3rd Ave. (City Hall Park and Fountain for outreach only). Action (completed): MID increased services effective 7/10/17 Person washing: 3 passes/day every day with bucket, sweeping and trash Green machine: 3 passes/day every day (e.g. the push machine) Pressure wash: 5 days/week on weekdays in morning |
| Loading dock area (Jefferson St. alley) | KC FMD CVI lead: Tony Wright Contact: Collin Sanders, KC FMD | Frequency: 2 times/week Action (completed): No formal agreement between City and County on Jefferson St. closure, City property FMD maintains. |
| JUROR ASSISTANCE |  |  |
| Route recommendations (map walking) | Superior Court CVI lead: Paul Sherfey | Action (completed): Added walking directions to Admin. Building at KC Juror Information Action (completed): Linked QR code on juror postcards with link to these directions Action (completed): Move “Transit Options” on KC Admin Bldg. web portal |
| Signage improvements - Metro Tunnel | Metro Transit CVI lead: Rob Gannon | Action (completed): Improved signage in Tunnel on mezzanine and exits directing people towards government facilities |
| Wayfinding (escort from bus stop) | Metro Transit CVI lead: Rob Gannon | Jurors arrive for orientation Mon and Weds at 8:00 am Action (completed): Not recommended at this time. |
| SECURITY |  |  |
| Metro Transit Police (KCSO) | Metro Transit CVI lead: Rob Gannon Contact: Major Dave Jutilla | Presence in front of Courthouse/3rd Ave; security coverage area 30’ at tunnel and at bus stops Action (completed): Schedule clarification – schedule varies but presence is consistent, with Bicycle Officers focusing on tunnel area |
| SPD Officers | SPD CVI lead: Steve Winske Contact: Steve Winske | Action (completed): Schedule clarification - presence in front of Courthouse/3rd Ave and in Park; schedule changes based on other city-wide priorities. Action (completed): All emergency calls from the Courthouse will be immediately flagged for SPD supervisor screening, per SPD 2.22.18 Action (completed): Communicate all concerns to SPD regarding encampment in front of Samis property in the Drexel building (3/22/18) |
| FMD Security | KC FMD CVI lead: Tony Wright Contact: Collin Sanders, Facilities Security Manager | Action (completed): Effective July 2017, 2-3 Officers 6:30am - 8:00 am, 12:00pm-1:50pm Mon-Fri Security inside Courthouse for screening after-hours. 07.00hrs – FMD Security Officers are in attendance at the 3rd Ave. Courthouse entrance. Security team will maintain a presence at the 3rd Ave. Courthouse entrance with a stronger presence when staff and jurors arrive (06.00hrs – 08.30hrs), lunch breaks (12.00hrs – 13.30hrs), and close of business. Intermittent roving by FMD Security Officers. Security to accompany custodial teams while they clean the perimeter of the building (pressure washing – 06.00hrs – 07.00hrs - M, W, F). FMD Security contact SPD for any escalated incidents (hostile or non-responsive individuals). |
| KCSO Marshalls | KCSO CVI lead: Scott Somers Contact: Noel Fryberger | Inside Courthouse screening Court protection during business hours |
| Security - jurisdictional role clarification and coordination (subcommittee, as of July 2018) | KC FMD CVI liaison: Tony Wright Contact: Collin Sanders, Facilities Security Manager | Action (completed Q1 2017): Convene all security-related groups and report findings Action (ongoing): Initiation and on-going coordination of security subcommittee: SPD Officers (David Drain), KCSO Marshalls (Noel Fryberg), Metro Transit Police (Dave Jutilla), FMD Security (Collin Sanders), Sound Transit (Steve Tucker), DESC Safety Patrol (Daniel Malone), Seattle Parks (Marlan Teeters) and DSA/Metropolitan Service District (Dave Willard). First meeting July 2018, Collin. |
| 4th Ave. Entrance | Superior Court Contact: Paul Sherfey (KCSO Contact: Patti Cole-Tindall) | Superior Court Ad hoc Safety committee request to open 4th Ave entrance (annual staff cost approx. $400K) Action (completed): Effective Jan. 2018, Council approved funding to open entrance for 16 hours/week - Monday-Thursday 7:45am-9:45am; noon-2:00pm). Signage improved. Usage data gathered by KCSO Court Protection Unit. Action: Council requested measurement of impact; Patti Cole-Tindall, point of contact (deadline 2019 TBD) |
| DESC Safety Patrol | DESC Contact: Daniel Malone | One FT DESC staff position, cited on sidewalk during business hours. Focus is interaction with Morrison clients; some interaction with non-Morrison people. |
| Courthouse safety/security assessment | KC FMD CVI lead: Tony Wright Contact: Collin, Facilities Security Manager | Jefferson St Alley / Loading Dock: Alley is city right of way, there should be no cars or trucks in the area, per signage; loading dock is still active; bollards in place on the west end of Jefferson at 3rd Ave. Seattle Parks responsible for cleaning 1-2’ into alley, FMD responsible for the rest. Action (completed): FMD security assessment completed, per request from Superior Court Ad hoc security committee, briefed Judge Rogers at Dec. 1, 2017 (Caroline, Tony, Collin); Researched historic documentation on street closure – no documentation found (Tony, 8/2017) Action (completed) Omnibus request $200,000 for 4-5 bullet resistant windows in KCCH, sidewalk cleaning and improved lighting. Action (completed): Installation of new No parking / Tow signage on east side of alley; SPD parking enforcement will begin in March 2018 (per Peter Ahlstrom, PEU) Action (completed): Replacing door on 3rd Ave (near Rotunda (Summer 2018) Action: Install gate at East end of Jefferson at 4th Ave.; FMD requesting in 2019-20 budget for gate and capital project manager. If approved, FMD will begin permitting process with SDOT and an installation date can be determined by Feb. 2019, may be end of 2019, per Collin. |
| TRANSIT |  |  |
| Bus stops | Metro Transit CVI lead: Rob Gannon | Action (completed): Relocation of bus stops and removal of seating not recommended, but could be further explored as part of One City (11/15/17, per Rob) Action: Relocate bus stop at Southbound 3rd Avenue and James Street one block north, effective by March 2019 (6/7/18, per Rob) Action: Northbound stop may be moved in the future (6/7/18, per Rob) |
| PIONEER SQUARE STATION |  |  |
| Station infrastructure changes | Sound Transit (effective March 2019) CVI lead: Steve Tucker | Committee requesting ST evaluate possible major structural changes removal of current station structure to allow better sightlines and open space at ground level. Action: ST developed recommendations and soliciting input on proposed short-term improvements and longer-term structural changes to increase safety and visibility (Steve) |
| HYGIENE FACILITY CITY HALL PARK |  |  |
|  | City of Seattle Contact: Robert Stowers | Siting a bathroom facility in Pioneer Square or City Hall Park is not currently on the list of Parks priorities (2017). Bathrooms are currently available at Fire Stations, Precinct offices citywide, and KCCH during working hours. Action (completed): KC FMD completed hygiene facility feasibility report to Council, March 2018, Final Report; Council discussion May 9, 2018. |