## CX Debt Service Plan
|  | 820950 |  | Term of debt (yrs) | 20 | except FSRP and Tech Bond
|  | 2500000 |  | Interest Rate | 5%
9217059
|  |  |  | Borrowing | w Borrowing Costs | Date | Annual Debt Service | Comments on change
RCECC |  |  |  | 30025000 | 30330000 | 2003-07-01 | 2416000 | delay financing 6 months
NRF |  |  |  | 1750000 | 1770000 | 2004-01-01 | 141000 | Defer replacement; planning and demo only
CASP |  |  |  | 82500000 | 83330000 | 2004-07-01 | 6639000 | Reflects revised costs and schedule
Seismic Fixes |  |  |  | 2970000 | 3000000 | 2004-07-01 | 239000 | Previously $5.3 million in CASP above
ISP |  |  |  | 15920000 | 16080000 | 2005-07-01 | 1281000 | Reflects updated plan; still under review
[5 empty] | 12 | 4
[5 empty] | Monthly | Quarterly
Assumptions on future financing: |  | Original | 2001-02-13 | Current Model
20 year debt |  | 5.75% | 5% | 5% | 0.4074% | 1.227%
Interfund Borrowing rate |  | 6.5% | 6% | 6% | 0.4868% | 1.467%
Ban effective rate |  | 5% | 4.5% | 3.15% | 0.2588% | 0.7784%
| 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007
Original Package Provided:
Pre 1999 | 14501077 | 14096766 | 13811667 | 8156520 | 3958768 | 3961426 | 3980000
1999 Issues | 4497892 | 5435593 | 5429787 | 5302588 | 5267099.6967 | 2270708.1314 | 1847027.2469
Total | 18998969 | 19532359 | 19241454 | 13459108 | 9225867.6967 | 6232134.1314 | 5827027.2469
Revised Current CX Debt Service (Corrected):
Pre 1999 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1999 Issues | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Difference-Pre-1999 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Current CX Debt | #REF! | 19532359 | #REF! | #REF! | #REF! | #REF! | #REF!
Pre 1999 |  | 13489056 | 13442564 | 7881780 | 7834360 | 7105924 | 7129259 | 7130500 | 7130500
1999 Issues |  | 5745110 | 5738770 | 5611602 | 5579033 | 3079217 | 2660123 | 2653870 | 2653870
|  | 19234166 | 19181334 | 13493382 | 13413393 | 10185141 | 9789382 | 9784370 | 9784370
|  | -298193 | #REF! | #REF! | #REF! | #REF! | #REF!
Additional Principal Assumptions
Addition to Debt: | [9 empty] | Baseline Scenario |  |  | Alternative Scenario
[10 empty] | Principal | Years | Percent | Principal | Prin. +/-
(In Millions of $'s)
Courthouse Seismic | [5 empty] | 6609000 | 6609000 | 6609000 | 6609000 | 82950000 | 20 | 5% | 90.45 | 7.5 | Base Seismic w/o South Entrance |  | 5073846 | 5073846 | 5073846 | 5073846
RCECC |  |  |  |  | 2406000 | 2406000 | 2406000 | 2406000 | 2406000 | 30450000 | 20 | 5% | 28.2 | -2.25 |  | 937980 | 937980 | 937980 | 937980 | 937980
FSRP Placeholder |  |  |  |  | 799000 | 799000 | 799000 |  |  | 28310000 | 3 | 5% | 28.3 | -0.01 | $10 MM, 22%, 3 years | 1196696 | 1196696 | 1196696 | 1196696 | 1196696
Tech Bond Place Holder | [6 empty] | 488286.2401 | 488286.2401 | 488286.2401 | 3770000 | 10 | 5% | 3.8 | 0.03 | 1999 bond plus inflation |  |  |  |  | 1026883
Barclay Dean Purchase $3.0 million |  |  | 262000 | 262000 | 262000 | 262000 | 262000 |  |  |  |  | 5% |  | 0 |  | 262000 | 262000 | 262000 | 262000 | 262000
Barclay Dean Purchase Financing from Sheriff's current budget |  |  | -262000 | -262000 | -262000 | -262000 | -262000 |  |  |  |  | 5% |  | 0 | Funded from existing sheriff's lease $'s
North Rehabilitation Facility (NRF) | [5 empty] | 1724000 | 1724000 | 1724000 | 1724000 | 21640000 | 20 | 5% | 2.64 | -19 | $19.53 Jan 2000 escalated to time of construction
ISP Project | [6 empty] | 810500 | 1621000 | 1621000 | 20350000 | 20 | 5% | 16.35 | -4 | Per Current estimates; under review for reduction
Unallocated Debt Capacity | [5 empty] | 0 | 0 | 0 | 0 |  | 20 | 5%
Total Additions |  |  | 0 | 0 | 3205000 | 11538000 | 12836786.2401 | 12848286.2401 | 12848286.2401
Grand Total | #REF! | 19234166 | 19181334 | 13493382 | 16618393 | 21723141 | 22626168.2401 | 22632656.2401 | 22632656.2401
Revenue Increase % |  |  | 3.136% |  | -0.4317% | 2% | 2% | 2% | 2%
Estimated CX Revenues subject to 6% fund balance requirement |  | 391758418 | 404042563 | 411959273 | 410181027 | 418384647.54 | 426752340.4908 | 435287387.3006 | 443993135.0466
Debt as % of CX Revenues: Baseline Scenario |  | 4.91% | 4.747% | 3.275% | 4.051% | 5.192% | 5.302% | 5.199% | 5.098%
Debt as % of CX Revenues: Current Scenario |  |  |  | 3.275% | 3.565% | 4.068% | 4.966% | 5.015% | 4.727%
Debt Service Additions:
Courthouse Seismic and Seismic Fixes | [5 empty] | 3439000 | 6878000 | 6878000 | 6878000
RCECC |  |  |  |  | 1208000 | 2416000 | 2416000 | 2416000 | 2416000
FSRP Placeholder | [5 empty] | 840000 | 840000 | 840000
Tech Bond Place Holder | [6 empty] | 488286.2401 | 488286.2401 | 488286.2401
North Rehabilitation Facility (NRF) | [5 empty] | 141000 | 141000 | 141000 | 141000
ISP Project | [6 empty] | 640500 | 1281000 | 1281000
Total Additions |  |  |  |  | 1208000 | 6836000 | 11403786.2401 | 12044286.2401 | 11204286.2401
Prior Debt |  |  |  |  | 13413393 | 10185141 | 9789382 | 9784370 | 9784370
Total Debt |  |  |  |  | 14621393 | 17021141 | 21193168.2401 | 21828656.2401 | 20988656.2401
Debt as % of CX Revenues: Current Scenario |  |  |  |  | 3.565% | 4.068% | 4.966% | 5.015% | 4.727%
Previous Service Additions:
|  |  |  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007
Courthouse Seismic and Seismic Fixes | [5 empty] | 6609000 | 6609000 | 6609000 | 6609000
RCECC |  |  |  |  | 2406000 | 2406000 | 2406000 | 2406000 | 2406000
FSRP Placeholder |  |  |  | 2003: 799000; 2004: 799000; 2005: 799000
Tech Bond Place Holder |  |  |  | 2005: 488286.2401; 2006: 488286.2401; 2007: 488286.2401
North Rehabilitation Facility (NRF) | [5 empty] | 1724000 | 1724000 | 1724000 | 1724000
ISP Project |  |  |  | 2005: 810500; 2006: 1621000; 2007: 1621000
Total Additions |  |  |  |  | 3205000 | 11538000 | 12836786.2401 | 12848286.2401 | 12848286.2401
Prior Debt |  |  |  |  | 13413393 | 10185141 | 9789382 | 9784370 | 9317720
Total Debt |  |  |  |  | 16618393 | 21723141 | 22626168.2401 | 22632656.2401 | 22166006.2401
Estimated CX Revenues subject to 6% fund balance requirement |  |  |  |  | 427700222 | 435544055 | 449280111.4741 | 463449371.5365 | 478065497.4307
Debt as % of CX Revenues: Previous Scenario-2002 Budget |  |  |  |  | 3.886% | 4.988% | 5.036% | 4.884% | 4.637%
|  |  |  | Borrowing | w Borrowing Costs | Date | Annual Debt Service
RCECC |  |  |  | 29900000 | 30200000 | 2003-01-01 | 2406000
NRF |  |  |  | 21420000 | 21640000 | 2004-01-01 | 1724000
CASP |  |  |  | 82120000 | 82950000 | 2004-01-01 | 6609000
Seismic Fixes |  |  |  | above CASP | above CASP | 2004-01-01 | above CASP
ISP |  |  |  | 20150000 | 20350000 | 2005-07-01 | 1621000
Note on C18: Bob Williams: currently as of 8/28/2000 from Nigel is 5.5% but use 5.75 to provide cushion plus issuancce.
Note on C19: Bob Williams: current rate per Nigel on 8/28/2000
Note on G64: Bob Williams: Use last year increases from JR numbers to project final 2 years in the plan 9.28.2000
Note on D66: Robert Williams: These numbers for 2000 thru 2003 from Jim record on 9.28.2000 These numbers revised per Helene on 4.2.2001

## CASP Appropriation Summmary
Mo | Year | Accum Expenditures | Appropriations | Notes
| 1997 | 40542
Jan | 1998 |  | 3500000 | Appropriation in 1997 | Permanent financing
Feb | 1998
Mar | 1998
Apr | 1998
May | 1998
June | 1998
July | 1998
Aug | 1998
Sept | 1998
Oct | 1998
Nov | 1998
Dec | 1998 | #REF!
Jan | 1999
Feb | 1999
Mar | 1999
Apr | 1999
May | 1999
June | 1999
July | 1999
Aug | 1999
Sept | 1999
Oct | 1999
Nov | 1999
Dec | 1999 | #REF!
Jan | 2000
Feb | 2000
Mar | 2000
Apr | 2000
May | 2000 |  | 160000 | Ord# 13859 | interim financing
Jun | 2000 |  |  |  | interim financing
July | 2000 |  |  |  | interim financing
Aug | 2000 |  |  |  | interim financing
Sept | 2000 |  | 5383823 | Ord# 13945 | interim financing
Oct | 2000 |  |  |  | interim financing
Nov | 2000 |  |  |  | interim financing
Dec | 2000 | #REF! |  |  | interim financing
Jan | 2001 |  |  |  | interim financing
Feb | 2001 |  |  |  | interim financing
Mar | 2001 |  |  |  | interim financing
Apr | 2001 |  |  | Ord# 14088 | interim financing
May | 2001 |  | 59308884 | Core CH Seismic | interim financing
June | 2001 |  | 1227000 | CH Security | interim financing
July | 2001
Aug | 2001
Sept | 2001
Oct | 2001
Nov | 2001 | #REF! |  | $ 9,043,823 PreConst. Authorization
Dec | 2001 | #REF! | Red Line Indicates Transition to Construction Funds
Jan | 2002 |  |  | $60,535,884 Constr.Phase Authorization
Feb | 2002 | #REF!
Mar | 2002
Apr | 2002
May | 2002
June | 2002
July | 2002
Aug | 2002
Sept | 2002
Oct | 2002
Nov | 2002
Dec | 2002
Jan | 2003
Feb | 2003
Mar | 2003
Apr | 2003
May | 2003
June | 2003
July | 2003
Aug | 2003
Sept | 2003
Oct | 2003
Nov | 2003
Dec | 2003
Jan | 2004
Feb | 2004
Mar | 2004
Apr | 2004
Legend:
69579707
|  | Pre-1998 | 40542
|  | Total Current Est | 83244884.3643
|  | total spent +bud est | 83285426.3643 | Note $33,000 rev reimbursement from AFIS project
|  | Balance to App | 13705719.3643 | July 2002 Appropriation Request

## CASP cashflow
RCECC Cash Flow
May 2002
[12 empty] | Accumulated Interest | Accumulated Balance | Period Interest | Accumulated Int | Accumulated
[5 empty] | Earnings Rate |  |  |  |  | 1999, 2000 and 2001 | 3991226 | 0 | -3991226
[5 empty] | 4.5% |  |  |  |  | Previous Appn |  |  | -2791226 |  |  | 1200000
[5 empty] | BAN rate |  |  |  |  | January 2002 | 703630 |  | #REF! | #REF! | #REF! |  | #REF!
[5 empty] | 3.15% | rate+1% BAN setup |  |  |  | February 2002 | 55294 |  | #REF! | #REF! | #REF!
[10 empty] | March 2002 | 126237 |  | #REF! | #REF! | #REF!
[10 empty] | April 2002 | 102778 |  | #REF! | #REF! | #REF!
|  |  | Original Appn with bonds funded |  |  | 3500000 |  |  |  | May 2002 | 363605 |  | #REF! | #REF! | #REF!
[10 empty] | June 2002 | 441137 |  | #REF! | #REF! | #REF!
[7 empty] | Accumulated Balance | Period Interest | Accumulated Int | July 2002 | 822731 |  | #REF! | #REF! | #REF!
|  |  |  | Pre 1998 |  | 40542 | 3459458 |  | 0 | August 2002 | 1527528 |  | #REF! | #REF! | #REF!
|  |  |  | Jan | 1998 | 3559.15 | 3455898.85 |  | 0 | September 2002 | 1617046 |  | #REF! | #REF! | #REF!
|  |  |  | Feb | 1998 | 15556.57 | 3440342.28 |  | 0 | October 2002 | 1678752 |  | #REF! | #REF! | #REF!
|  |  |  | Mar | 1998 | 36224.56 | 3404117.72 |  | 0 | November 2002 | 1902537 |  | #REF! | #REF! | #REF!
|  |  |  | Apr | 1998 | 45994.05 | 3358123.67 |  | 0 | December 2002 | 2894178 |  | #REF! | #REF! | #REF!
|  |  |  | May | 1998 | 23298.68 | 3334824.99 |  | 0 | January 2003 | 2570666 |  | #REF! | #REF! | #REF! |  | Bond Issuance
|  |  |  | June | 1998 | 20570 | 3314254.99 |  | 0 | February 2003 | 2011257 |  | #REF! | #REF! | #REF!
|  |  |  | July | 1998 | 56304 | 3257950.99 |  | 0 | March 2003 | 2322402 |  | #REF! | #REF! | #REF!
|  |  |  | Aug | 1998 | 52194.2 | 3205756.79 |  | 0 | April 2003 | 2635600 |  | #REF! | #REF! | #REF!
|  |  |  | Sept | 1998 | 44569.85 | 3161186.94 |  | 0 | May 2003 | 3016391 |  | #REF! | #REF! | #REF!
|  |  |  | Oct | 1998 | 11367.63 | 3149819.31 |  | 0 | June 2003 | 1752702 |  | #REF! | #REF! | #REF!
|  |  |  | Nov | 1998 | 55594.88 | 3094224.43 |  | 0 | July 2003 | 65224 |  | #REF! | #REF! | #REF! | 30025000
|  |  |  | Dec | 1998 | 315114.38 | 2779110.05 |  | 0 | TOTAL | 30600921 |  |  | #REF!
|  |  |  | Jan | 1999 | 43082.28 | 2736027.77 |  | 0 |  |  |  |  | #REF! |  | 30025000
|  |  |  | Feb | 1999 | 303987.95 | 2432039.82 |  | 0 | Total Costs
|  |  |  | Mar | 1999 | 89554.73 | 2342485.09 |  | 0
|  |  |  | Apr | 1999 | 126012.08 | 2216473.01 |  | 0
|  |  |  | May | 1999 | 37868.06 | 2178604.95 |  | 0
|  |  |  | June | 1999 | 20191.52 | 2158413.43 |  | 0
|  |  |  | July | 1999 | 99259.4 | 2059154.03 |  | 0
|  |  |  | Aug | 1999 | 125328.63 | 1933825.4 |  | 0
|  |  |  | Sept | 1999 | 34236.98 | 1899588.42 |  | 0
|  |  |  | Oct | 1999 | 17327.55 | 1882260.87 |  | 0
|  |  |  | Nov | 1999 | 3205.31 | 1879055.56 |  | 0
|  |  |  | Dec | 1999 | 278664.88 | 1600390.68 |  | 0
|  |  |  | Jan | 2000 | 10798.05 | 1589592.63 |  | 0
|  |  |  | Feb | 2000 | 202975.97 | 1386616.66 |  | 0
|  |  |  | Mar | 2000 | 387469.25 | 999147.41 |  | 0
|  |  |  | Apr | 2000 | 3084.74 | 996062.67 |  | 0 | [7 empty] | Previous
|  |  |  | May | 2000 | 396807.5 | 599255.17 |  | 0 |  |  |  | Expenditures | 30600921 |  | Expenditures | 30600921
|  |  |  | Jun | 2000 | 225462.52 | 373792.65 |  | 0
|  |  |  | July | 2000 | 188125.96 | 185666.69 |  | 0 |  |  |  | Appropriation previous | 1200000 |  | Appropriation previous | 1200000
|  |  |  | Aug | 2000 | 186271.58 | -604.89 |  | 0 |  |  |  | RCECC Bond | 30025000 |  | RCECC Bond | 29900000
|  |  |  | Sept | 2000 | 160836.24 | -161653.8154 | -212.6854 | -212.6854
|  |  |  | Oct | 2000 | 63444.76 | -225606.1879 | -507.6125 | -720.2979 |  |  |  | Interest Earnings Net | #REF! |  | Interest Earnings Net | -495264.0716
|  |  |  | Nov | 2000 | 12594.77 | -238809.7048 | -608.7469 | -1329.0448 |  |  |  | Subtotal | #REF! |  | Subtotal | 30604735.9284
|  |  |  | Dec | 2000 | 623403.06 | -863657.8568 | -1445.092 | -2774.1368
|  |  |  | Jan | 2001 | 19436.05 | -885386.5185 | -2292.6117 | -5066.7485 |  |  |  | Net Balance of Rev: | #REF! |  | Net Balance of Rev: | 3814.9284
|  |  |  | Feb | 2001 | 22998.03 | -910738.873 | -2354.3245 | -7421.073
|  |  |  | Mar | 2001 | 629610.21 | -1543566.1359 | -3217.0529 | -10638.1259
|  |  |  | Apr | 2001 | 119850.73 | -1667626.0311 | -4209.1652 | -14847.2911
|  |  |  | May | 2001 | 494805.77 | -2167458.752 | -5026.9509 | -19874.242
|  |  |  | June | 2001 | 529166.1 | -2703008.9618 | -6384.1097 | -26258.3518
|  |  |  | July | 2001 | 812196.52 | -3523366.8882 | -8161.4065 | -34419.7582
|  |  |  | Aug | 2001 | 558675.04 | -4092024.0273 | -9982.0991 | -44401.8573
|  |  |  | Sept | 2001 | 331099.96 | -4434300.1191 | -11176.1318 | -55577.9891
|  |  |  | Oct | 2001 | 487306.7 | -4933886.4469 | -12279.6279 | -67857.6169
|  |  |  | Nov | 2001 | 142521.13 | -5089546.0878 | -13138.5109 | -80996.1278
|  |  |  | Dec | 2001 | 638349.99 | -5742093.9707 | -14197.8928 | -95194.0207
|  |  |  | Jan | 2002 | 73839.51 | -5831103.3917 | -15169.911 | -110363.9317
|  |  |  | Feb | 2002 | 158342.48 | -6004960.3426 | -15514.4709 | -125878.4026
|  |  | Est | Mar | 2002 | 32711.8327 | -6053478.1305 | -15805.9552 | -141684.3578
|  |  | Est | April | 2002 | 32711.8327 | -6102123.2777 | -15933.3144 | -157617.6722
|  |  | Est | May | 2002 | 32711.8327 | -6150896.1183 | -16061.0079 | -173678.68
9338539.94
[5 empty] | Act 1998 thru 2/2002 | 9338539.94 |  | -173678.68
9436675.4382
| Expenditures | Accumulated Balance | Period Interest | Accumulated Int
Paid thru 5/31/02 | 9436675.4382 | -6150896.1183 | -173678.68 | -173678.68
2002-06-02 | 417486.41 | -6585076.5815 | -16694.0532 | -190372.7333
2002-07-02 | 800903.2 | -7404316.793 | -18337.0115 | -208709.7447
2002-08-02 | 1266693.2 | -8692108.8594 | -21098.8664 | -229808.6112
2002-09-02 | 808787.95 | -9524775.1293 | -23878.3199 | -253686.9311
2002-10-02 | 748686.8894 | -10299447.205 | -25985.1863 | -279672.1173
2002-11-02 | 3743821.9439 | -14075218.9641 | -31949.8152 | -311621.9326
2002-12-02 | 4008892.2079 | -18126320.2929 | -42209.1208 | -353831.0534
2003-01-02 | 3969442.2079 | -22148553.9845 | -52791.4837 | -406622.537
2003-02-02 | 3600074.6646 | -25811493.7013 | -62865.0522 | -469487.5892
2003-03-02 | 3471910.1606 | -29355715.915 | -72312.0531 | -541799.6423
2003-04-02 | 3471910.1606 | -32909241.7119 | -81615.6364 | -623415.2787
2003-05-02 | 3855025.4246 | -36855713.6169 | -91446.4804 | -714861.759
2003-06-02 | 3307717.9046 | -40264519.1495 | -101087.628 | -815949.387
2003-07-02 | 3307717.9046 | -43682272.7966 | -110035.7425 | -925985.1295
2003-08-02 | 3179317.9046 | -46980429.5221 | -118838.8208 | -1044823.9504
2003-09-02 | 3507702.4166 | -50616059.4256 | -127927.4869 | -1172751.4373
2003-10-02 | 3562433.1686 | -54316035.4437 | -137542.8495 | -1310294.2868
2003-11-02 | 3562433.1686 | -58025723.8989 | -147255.2866 | -1457549.5734
2003-12-02 | 3398240.9126 | -61580742.5279 | -156777.7164 | -1614327.2898
2004-01-02 | 3386640.9126 | -65133477.8559 | -166094.4153 | -1780421.7052
2004-02-02 | 3120178.2776 | -68428726.7468 | -175070.6134 | -1955492.3185
2004-03-02 | 3065055.0256 | -71677430.0649 | -183648.2924 | -2139140.6109
2004-04-02 | 2955593.5216 | -74825056.0569 | -192032.4704 | -2331173.0814
2004-05-02 | 2627209.0096 | -77652129.0505 | -199863.984 | -2531037.0653
2004-06-02 | 1587324.7216 | -79445373.9745 | -205920.2025 | -2736957.2678
2004-07-02 | 1495822.3029 | 1597945.4741 | 6141.7515 | -2730815.5162 | 82533000
2004-08-04 | 1389708.3635 | 210607.7252 | 2370.6146 | -2728444.9016
2004-09-04 | 80215.7083 | 130839.579 | 447.5622 | -2727997.3394
2004-10-04 | 55653.3333 | 75456.6545 | 270.4089 | -2727726.9305
2004-11-04 | 55653.3333 | 19928.3499 | 125.0287 | -2727601.9018
Project Total | 83244927.7482 |  | -2727601.9018 |  | 85972529.6501
|  | Bond-CASP | 82500000 |  | June to end exp | 73808252.31
[5 empty] | June to end int | -2553923.2218
|  | Expenditures | 83244927.7482 |  |  | -3.46%
|  | Pre 1998 Expenditures | 40542
|  | Appropriation previous | 3500000
|  | CASP Bond | 82500000
|  | Reimbursement from AFIS | 33000
|  | Interest Earnings Net | -2727601.9018
|  | Subtotal | 83305398.0982
|  | Net Balance of Rev: | 19928.3499
5.9226e-09
Seismic Fix Additions
|  | Direct Estimated Costs | 2867132.375
|  | Estimated Financing | 99208.9058
|  | Seismic w Financing | 2966341.2808
|  | Total CASP/Repairs | 85466341.2808
|  | Total w/ Transaction Costs | 86330000