##### Metropolitan King County Council

Capital Budget Committee

| AGENDA ITEM No.: | 5 |  | DATE: | October 4, 2006 |
| --- | --- | --- | --- | --- |
| PROPOSED No.: | 2006-0437 |  | PREPARED BY: | Mark Melroy |

STAFF REPORT

SUBJECT:	AN ORDINANCE that would approve a build-to-suit, lease-lease back transaction for development of a medical building at 9th Avenue and Jefferson Street.

SUMMARY:

This ordinance proposes a lease-lease back arrangement to effect the construction of a medical services and office building on the Harborview Hospital campus.  The building, which would be located at the southeast corner of 9th Avenue and Jefferson Street, would house services such as the King County Medical Examiner (KCME), research laboratories, dry labs, clinical services, Involuntary Treatment Act (ITA) Courtroom, retail, lobby and five floors of underground parking.  This building would be constructed by the development team of Wright-Runstad and Turner Construction.  The land, which is owned by King County, would be leased to a non-profit named “NJB Properties” who would issue tax-exempt bonds to finance the building project.  NJB Properties would then lease the completed building back to the County and other building tenants including Harborview Medical Center.  NJB Properties would then use the tenant lease payments as revenue to pay off the bond debt over a period of 26.5 years.  When the bonds are paid off NJB Properties conveys full legal and unencumbered title for the project to King County for no additional consideration.  The construction contract is held between NJB Properties and the building contractor.

The proposed legislation would authorize the executive to execute the legal documents related to this series of transactions including the ground lease and project lease.  Adopting the legislation as proposed would also signal Council approval of the related development agreement and financing plan.

A different version of this building proposal was part of the overall Harborview Bond Project approved by voters in September of 2000.  The bond project also included construction of an Inpatient Expansion Building (IEB), which is currently progressing. The University of Washington manages Harborview and, under an agreement between King County, Harborview Medical Center and the University, the UW is managing the Bond Program.  This alternative proposal for the Ninth & Jefferson building is necessary due to significant cost overruns on the overall bond project, which will be detailed later in this report.

This is the Committee’s first chance to review this project proposal, which is currently estimated to cost nearly $180 million.

BACKGROUND:

Harborview Medical Center (HMC) is a comprehensive health care facility owned by King County, governed by an appointed Board of Trustees and managed by the University of Washington.  Its primary mission is to provide high quality health care to the residents of this region, in particular to the indigent and underserved residents of King County.  Serving a four-state region, Harborview is home to the nationally renowned level-one trauma center and Medic One Emergency Response Unit.

Scope:  In September, 2000, King County voters approved $191 million in bond funding to support facility improvements at Harborview.  The project proposed to the voters included:

- Seismic stabilization of the east wing inpatient facility.

- Elimination of two older buildings due to seismic risk.

- Construction of new facilities to house the displaced functions.

- Expanded critical care capacity.

The voter approved bond funds combined with interest earnings and contributions from Harborview reserves brought the total project budget estimate to $263 million.

On March 3, 2002 the Council adopted Ordinance 14295 which approved a management agreement between King County, Harborview Medical Center, and the University of Washington for management of the Bond Program.  On April 7, 2003 the Initial Program Plan (scope, schedule, and budget) was approved by the Council (Motion 11684).  On August 25, 2003 the Council adopted Ordinance 14744 approving $29.6 million of revenue backed scope increases that added additional parking and tenant space.  The revised scope increased the total Bond Program to a total of $292.8 million.

The project scope, as of 2003, could be summarized as follows:

- Project #1	Ninth & Jefferson Building (NJB):  $104M

New construction of a multi-purpose facility to house specialized services such as the King County Medical Examiner (KCME), research laboratories, dry labs, clinical services, Involuntary Treatment Act (ITA) Courtroom, retail, lobby and five floors of underground parking.

- Project #2	Inpatient Expansion Building (IEB) & Seismic Upgrade: $164M

Seismic Improvements to the North Wing trauma center tower and construction of a new inpatient wing connected to the existing facility by a bridge building.

- Project #3	Proposed Demolitions of Harborview Hall & East Clinic (South Wing): $11M

Demolition to seismically unsound East Clinic, and potential demolition of Harborview Hall.

The entire bond project was proposed to be accomplished using the General Contractor/Construction Manager (GC/CM) method.  Under this method, a contractor is selected and then acts as both the General Contractor and the Construction Manager for the project.  Turner Construction was selected as the GC/CM in December 2002.

When the major bids for construction of the NJB and IEB were opened beginning in late fall 2005, bids for various phases of the project were significantly higher than the engineering estimates.  Under the GC/CM method, Turner provided a maximum allowable construction cost (MACC) for the two buildings.  Normally, under the GC/CM method, the GC/CM would be held to the cost as proposed by the MACC that they developed.  In this case, however, Turner claimed that there were extenuating circumstances and design ambiguities that could not have been foreseen at the time that they developed the MACC.  Therefore, Turner argued, they should be allowed to revise the MACC.

The University of Washington, acting as the County’s agent, negotiated with Turner Construction and eventually reached the conclusion that the project budget for the IEB project should be adjusted by $15 million.  This negotiated amount was included in a settlement agreement signed by the involved parties.  The UW believed that a $15 million adjustment to the IEB project budget would be sufficient to complete the IEB project.  This decision was endorsed by the bond oversight committee.

With subcontractor bid guarantees set to expire on April 7, 2006, the King County Council passed Ordinance 15401 on April 3, 2006, which shifted $15 million from the NJB project to the IEB project.

Estimates for the NJB project at this time were also approximately $15 million above available budget.  Taken together, these two issues resulted in a net $30 million shortfall in the project budget for the Ninth and Jefferson building project.

Following the budget overrun, representatives of the UW Capital Projects Office, the Harborview Medical Center planning staff and executive staff began searching for options to somehow complete the overall bond project scope as promised to voters given the $30 million budget shortfall.  One strong interest, held by all parties, was to avoid going back to voters to request additional project revenues.  The legislative proposal before the committee today, is the Executive’s suggested solution to this situation.  The solution involves separating the NJB building project from the rest of the Harborview bond project and engaging a 63-20 type development agreement – as described previously in this report - to complete the NJB building project.

The following actions are integral to the consideration of the revised development proposal:

- Separate the Ninth and Jefferson building (NJB) project from the rest of the Harborview bond project.

This includes terminating the NJB portion of the bond program construction contract with the GC/CM contractor.  This also requires separating the financing revenues of the new NJB project from the rest of the bond program.

- Make adjustments to the three party agreement between UW, King County and Harborview Medical Center.

The current proposal involves King County managing the revised NJB project with UW no longer acting as the County’s agent for project management.  This also entails modifications to the current project oversight structure that allocates authority for project changes to a “Harborview Bond Oversight Committee”.  Changes to the three party agreement have not been made.

- Advertise for and select a development team to redesign and possibly manage the construction of a new building at the Ninth and Jefferson site.

The development team of Wright-Runstad/Turner Construction has been selected to serve the role described above.

- Select a non-profit entity to lease the county-owned land.  This non-profit entity would issue long-term bond debt to finance a new building and ensure construction of the building possibly using the developer as its agent for management of the project.  Finally, the selected non-profit would lease the completed building back to King County.

The non-profit entity “NJB Properties” has been selected to serve the role described above.

- Ensure the remainder of the Harborview bond projects, including the IEB and demolition projects, are unaffected by the current proposal for changes to the NJB project.

Completion of the IEB remains the critical task in the overall bond program schedule – the current deadline for that work is November 2007.

- Ensure King County is not exposed to an unreasonable amount of risk as a result of the proposed changes to the project.

This involves an analysis of complex project financing to ensure King County’s security in moving forward with the revised project.

ANALYSIS

A copy of the current Harborview Bond Project Monthly Report for September 2006 is included in the staff report as Attachment #4.  This report outlines the scope, schedule and budget status for the entire bond program.  For expediency, the following discussion pertains mainly to the NJB project.

NJB Scope:  The Harborview bond project, as proposed to voters in September, 2000 originally envisioned the construction of a multi-services building at the Southeast corner of Ninth Avenue and Jefferson Street.  This facility was planned to house the functions described here:

specialized services such as the King County Medical Examiner (KCME), research laboratories, dry labs, clinical services, Involuntary Treatment Act (ITA) Courtroom, retail, lobby and five floors of underground parking.

The NJB building was originally envisioned to be approximately 150,000 square feet and was planned to occupy the west half of the block bounded by 9th Avenue and Terry Avenue between Jefferson and James Streets – please see graphic provided in Attachment #4.

Future construction of an additional building on the east half of this block and has been approved in Harborview’s Major Institution Master Plan (MIMP).  The additional building however, was not included in the Harborview bond project approved by voters in 2000.   The additional building was planned to allow for expansion of Harborview’s facilities and likely would have required a new voter-approved bond to generate capital revenues to support construction.

The scope of the NJB in the currently proposed legislation includes construction of a 450,000 square foot, 14 story building that would occupy the entire block bounded by 9th and Terry Avenues on the east and west and Jefferson and James Avenues on the north and south.  This structure would approximately triple the size of the formerly planned NJB.

The size of the NJB project has grown for two major reasons:

The 63/20 financing method essentially uses the project’s land value as leverage to finance the project - more land means a bigger project which yields more lease revenue to pay for the initial bond debt.  By building out the entire block at this time, the project is more able to absorb the current shortfall by spreading it out across what would have been two projects as opposed to one.

Harborview Medical Center has been updating its facility requirements.  Harborview has indicated its willingness to make use of the additional space by relocating Harborview agencies that are currently engaged in off-campus leases to the new facility.

The larger building also allows for additional revenue-generating parking spaces.

The King County Medical Examiner’s Office facilities as planned within the expanded building do not differ substantially from what was outlined in the original NJB proposal.

NJB Schedule:  A copy of the project schedule for the NJB – as proposed in the current legislation - is included in Attachment #5.  Selected key milestone dates for the entire bond program are summarized below:

Planned	Current

12/4/07	2/27/08	Inpatient Expansion Building Substantial Completion

8/1/08		10/27/08	North Wing Seismic Upgrade Completion

3/28/08	4/22/09	Ninth & Jefferson Building Complete

There are several schedule constraints on the NJB project, not the least of which directly relates to the Inpatient Expansion Building.  In the original design of the bond program, substantial mechanical systems serving the IEB were to be housed within the underground parking structure of the NJB.  These systems would connect to the IEB via an underground tunnel beneath Jefferson Street just east of 9th Avenue.  Under the original program, the NJB parking garage would have been constructed and the mechanical systems would be in place by the time the IEB was complete.  Although the NJB project has been suspended, the mechanical systems and related structure must still be completed in order to meet the completion deadline for the IEB.  Two options are currently available in order to meet the current completion date for the IEB:

- Approve the 63/20 development agreement proposal for the NJB in the near future, allowing the development team to complete design and begin construction of a structure to house the mechanical systems for the IEB.

- Contract with the current GC/CM, Turner construction, to complete the necessary structure, which would house the mechanical systems for the IEB.

UW CPO staff estimate that they would need to engage the latter scenario no later than November of 2006 in order to meet the current schedule for opening the IEB.

Seismic improvements to the North Wing also cannot be completed until the IEB is operational - patients must be transferred to the new IEB facility before that work can begin.

Representatives of the selected developer for this project, Wright-Runstad, have stated their assumption that if a council decision is not made in October, 2006, they expect delays to extend for more than a month and as a result, it would be necessary to adjust their final guaranteed maximum price (GMP) for construction.

NJB Budget:

The total estimated cost of the revised NJB project is currently $178,236,400

A breakdown of this total estimated cost is provided in the project proforma, which is included as Attachment #6 to this report.  The construction cost numbers used to generate the total cost estimate will be market tested when Wright Runstad receives bids from its contractors on or around October 16th, 2006.  The following table shows a calculation of the required additional financing to build the expanded NJB project.

| Harborview NJB proposal - financing analysis |
| --- |
| Original project budget | $121,200,000.00 |
| Total projected expenditures for NJB project under GC/CM agmt | ($32,700,000.00) |
| Previous transfer to IEB project budget | ($15,000,000.00) |
| Original budget amount remaining for revised NJB project | $73,500,000.00 |
| Estimated construction cost of revised building | $178,236,400.00 |
| Less remaining budget amount from original project | $73,500,000.00 |
| Unfunded project amount requiring financing | $104,736,400.00 |
| Estimated transaction costs including period interest (13%) | $13,615,732.00 |
| Total amount required to finance revised NJB project | $118,352,132.00 |

The current proforma for the NJB project (Attachment #6) details how $118M would be spread over a period of 26.5 years.  Using an assumed interest rate of 4.6% the required annual payment amounts to $7,818,206.  Spreading this total annual payment over the additional space created by the new project (approximately 300,000sf) yields a lease rate of $26.50/square foot for that space.

HMC staff estimate that $73.5 million of NJB project funds remain from the original bond program budget.  An equivalent amount of Harborview revenues will be allocated to the new NJB project budget and the bond funds will be used on other bond program projects – this allows for separation of the new project’s financing from the overall bond program.  This $73.5 million would be used to finance the building space planned in the original project (approximately 144,790sf) by making an annual payment $5,485,000.

Adding the two annual payments together yields a required total annual payment amount of $13,300,000.  Executive staff have transmitted information about Harborview’s ability to cover this financial commitment that includes assumptions about revenues from interest earnings, parking, grants and other sources.  This information requires further clarification.  At the time of drafting this report, staff do not have access to HMC financial reports to fully review the assumptions included in these numbers.

On September 28th, 2006, the Harborview Medical Center Board of Trustees voted unanimously to approve the motion included as Attachment #7 to this report.  This motion resolved that the Board “supports the development of the newly designed Ninth and Jefferson Building.  This includes the Board agreeing to annually commit in its budget sufficient HMC funds to pay the monthly rent under the lease agreement, any additional rent due under the lease, and all costs (including costs of maintenance and operation), fees, taxes, assessments and liabilities associated with the County’s leasehold.”

It is staff’s understanding that, while this motion clearly states the intent of the HMC Board, it does not constitute a legal, binding agreement for HMC to fully cover the lease payments.  Per the agreements attached to the proposed legislation lease payments remain the responsibility of King County.

Further assurance, although binding in no way at this time, is an offer by the project’s developer, Wright Runstad to “condo”, or purchase, approximately 100,000 sf of space in the building.  Harborview Medical Center has, to date, expressed little interest in pursuing this option given their intention to otherwise occupy the entire facility.

Independent Project Monitoring Consultant Review:

The current three-party agreement included a description of responsibilities for an independent project monitoring consultant.  This consultant’s work is limited to “bond program” projects and would not technically apply to the revised NJB project since the revised project is not funded by the original voter-approved bonds.  The County does not have prior experience using independent project monitoring on projects funded with the 63-20 financing mechanism.

Per King County Code 4.04.075, a fiscal note outlining the fiscal impact of this legislation is required and is included in Attachment #3.  Although the fiscal note shows zero net fiscal impact to King County as a result of this agreement – risks outlined in this report may have the potential to impact King County’s financial health.

The following table describes the status of critical work activities mentioned earlier in this report:

| Issue | Comments |
| --- | --- |
| PAO & Council Legal Counsel review and approve legal documents | Development agreement and related legal documents not yet finalized |
| Separate NJB from HBV bond program | Financial plan not yet finalized |
| Adjust 3-party agmt (UW, HBV, KC) to reflect changes | 3-party agreement not yet modified to reflect proposed project changes |
| Select Developer | Developer selected |
| Select Non-Profit | Non-profit formed, selected |
| Ensure remainder of bond program unaffected by current proposal | Executive staff review of assumptions in financial plan not yet complete |
| Ensure effective independent project oversight | Role of independent oversight consultant on proposed project as yet undefined |
| Ensure KC not exposed to unreasonable risk | Financial review not yet finalized |

Reasonableness:  						NOT READY FOR ACTION

The legal documents and agreements that relate to the proposed legislation have not been finalized.  Several components of this proposal require final review and approval by the Prosecuting Attorneys Office.  Although many people have invested considerable effort in this project proposal it is not reasonable for the Capital Budget Committee to consider approving the legislation in its current form.

Staff will continue to work with all involved parties to resolve outstanding issues in the most expedient manner possible.  This work will allow the Committee to proceed in their review of this legislation.

INVITED:

Troy Pyles, P.E., Oversight Monitoring Consultant, Vanir Construction Management

Bob Cowan, Director, Office of Management and Budget

Kathy Brown, Director, Facilities Management Division

Jim Napolitano, Manager, Major Projects, Facilities Management Division

Leslie Harper-Miles, Senior Executive Project Manager, Executive Office

Elise Chayet, Director Planning & Regulatory Affairs, Harborview Medical Center

Eric Smith, Director, University of Washington, Capital Projects Office

Tom Kuffel, Senior Deputy Prosecuting Attorney, Prosecuting Attorneys Office

Pete Ramels, Senior Deputy Prosecuting Attorney, Prosecuting Attorneys Office

Karin Nyrop, Assistant Attorney General, State Attorney General’s Office

Jim Brewer, Legal Counsel, King County Council

Cindy Edens, Director of Development, Wright Runstad

Tom Gerlach, Senior Vice President, Turner Construction

Craig Holt, Project Manager, Turner Construction

ATTACHMENTS:

- Proposed Ordinance 2005-0437

- Transmittal Letter, dated September 18, 2006

- Fiscal Note

- Harborview Bond Project, Monthly Report, August 2006

- NJB Project Schedule

- NJB Project Proforma, Current Cost Estimate

- HMC Board Motion in Support of NJB – passed September 28, 2006