Reduced Fare ORCA Card Procurement Locations Implementation Plan

March 2020

Table of Contents

I.	Proviso Text	5

II.	Executive Summary	6

III.	Background	7

A.	Metro Transit Department Overview	7

B.	ORCA System Overview	7

C.	Reduced Fare ORCA Products (RRFP & Youth)	9

D.	Factors to Consider when Expanding Locations	9

Documentation Verification and Fraud	9

Technology Required for Current ORCA Card Sales	10

Staffing and Security Needs for ORCA Card Sales	10

Regional Agreements (ORCA and RRFP)	10

E.	Ongoing King County Metro Programs	11

Online Portal	11

The Metro Neighborhood Pop-Up Program	11

The Next Generation of ORCA	11

IV.	Research and Strategy Development Methodology	13

A.	Constraints and Opportunities	13

B.	Potential Opportunities	14

C.	Evaluation Criteria	14

Feasibility	14

High Impact/Ability to Distribute Many Cards	15

Easier Customer Experience	15

Alignment with Equity and Social Justice Strategic Plan	15

D.	Alignment with Results of Stakeholder Outreach	16

Description of Outreach/Engagement	16

E.	Recommended Strategies	17

V.	Report Requirements	21

A.	Locations Considered	21

B.	Estimated Costs, FTE and Contracting Needs, and Proposed Funding Sources	21

C.	Potential Policy Changes	22

D.	Engagement Activities	23

Major Themes/Takeaways	23

Outreach/Engagement by Group	23

The section below summarizes findings for each audience identified in the proviso.	23

E.	Expansion Marketing	26

F.	Potential Partners/Partnerships	27

G.	Populations Anticipated To Be Served at Each Location	28

H.	Map of the Potential Locations	28

I.	Schedule for Opening the New Reduced Fare ORCA Card Procurement locations	28

VI.	Implementation Plan for Recommended Potential Strategies	29

A.	Create a Network of ORCA Verifying Agencies	29

Description	29

Estimated Program Costs and Revenues	29

Potential Policy Changes	31

Engagement	31

Marketing	31

Partnerships	31

Individuals Served by the Program	32

Map of New Locations	33

Schedule	33

B.	Develop a Program to Expand Distribution through Schools	34

Description	34

Estimated Program Costs and Revenues	35

Potential Policy Changes	36

Engagement	36

Marketing	36

Partnerships	36

Individuals Served	36

Map	36

Schedule	37

C.	Expand Metro’s Neighborhood Pop-Up Program	37

Description	38

Estimated Program Costs and Revenues	39

Potential Policy Changes	40

Marketing	40

Partnerships	40

Individuals Served	40

Map of New Locations	40

D.	Improve communications to customers about fare products and their use.	41

VII.	Conclusion/Next Steps	42

VIII.	Appendices	43

A.	ORCA and RRFP Agencies	43

B.	Equity Analysis: Utilization Gaps in King County	44

C.	EMC Research Report on Focus Groups	45

D.	Verifying Agencies: Phase 1 Locations - Addresses	72

E.	Schools Distribution: Contracts for ORCA Cards and Metro Services – 2019-2020 School Year	73

F.	Schools Distribution:  School Districts in King County – Demographic Data	74

G.	Metro Neighborhood Pop-Up: Current Locations – Addresses and Facility Types	75

H.	Metro Neighborhood Pop-Up: A Sample of Customer Feedback	76

# Proviso Text

P7 PROVIDED FURTHER THAT:

Of this appropriation, $1,000,000 shall not be expended or encumbered until the executive transmits an implementation plan for expanding the number of locations where individuals who qualify for regional reduced fare permit ORCA cards and youth ORCA cards ('reduced fare ORCA cards') can apply for and receive those cards and a motion approving the implementation plan, and a motion approving the implementation plan is passed by the council. The motion should reference the subject matter, the proviso's ordinance, ordinance section and proviso number in both the title and body of the motion.

A.  The implementation plan shall be informed by:

1.  Engagement with: (1) populations that would be eligible for a reduced fare ORCA card, such as youths ages six to eighteen, seniors ages sixty-five and over, and individuals with disabilities; and (2) parents of youth, schools, other stakeholders, and members of the public. The engagement process should solicit input on what are the barriers to immediately accessing the existing reduced fare ORCA cards and suggestions for more accessible and convenient procurement locations and enrollment processes for these ORCA cards. This engagement may be carried out in conjunction with other Metro fares outreach and engagement efforts; and

2.  King County's Equity and Social Justice Strategic Plan.

B.  The reduced fare ORCA card procurement location implementation plan shall include, but not be limited to:

1.  A description of the types of reduced fare ORCA card procurement locations considered including but not limited to libraries, schools, retail locations and buildings where government services are provided such as city halls, evaluation criteria used to assess them, and how flexible delivery through ORCA to Go integrates with this plan;

2.   Estimated new and existing costs, FTE and contracting needs, and proposed funding sources, including fare revenue impacts, to implement the plan;

3.  Potential policy changes that would be needed to implement an expansion of Regional Reduced Fare Permit and youth reduced fare ORCA card procurement locations, including policy changes that provide for expanded locations for immediate issuance both of ORCA cards that require photographs and those that do not;

4.  A summary of engagement efforts and stakeholder input required by subsection A.1 of this proviso;

5.  How the expansion of reduced fare ORCA card procurement locations would be marketed to eligible populations;

6.  How the Metro transit department would partner or seek partners to serve as reduced fare ORCA card procurement locations;

7.  A description of populations anticipated to be served at each reduced fare ORCA card procurement location;

8.  A map of the potential and proposed reduced fare ORCA card procurement locations; and

9.  A schedule for opening the new reduced fare ORCA card procurement locations as early as 2020.

The executive should file the reduced fare ORCA card procurement location implementation plan and a motion required by this proviso by March 31, 2020 in the form of a paper original and an electronic copy with the clerk of the council, who shall retain the original and provide an electronic copy to all councilmembers, the council chief of staff and the lead staff for the mobility and environment committee, or its successor.

Ordinance 18930, Section 75, Proviso P7 -- Transit, p. 112-114.

# Executive Summary

Transit riders in the Puget Sound region can pay for their trips using cash, paper tickets, the TransitGo mobile ticketing application, or with One Regional Card for All (ORCA) electronic fare payment cards. There are three types of ORCA cards – Regional Reduced Fare Permit (RRFP) cards for senior citizens, RRFP cards for people with disabilities and ORCA Youth cards  –  that allow transit customers to ride for reduced fares throughout the Puget Sound region, once they prove they qualify for the cards by having certain medical conditions or being above or below a certain age.

In response to Ordinance 18930, Section 75, Proviso 7, this report presents an implementation plan that would increase the number of locations where customers can apply for and receive these three types of reduced fare ORCA cards.

Building on existing innovations in this area, Metro details four potential strategies in this implementation plan:

- Build a network of verifying agencies to assist with applications and to approve the documentation for these card types;

- Evaluate opportunities to create a more comprehensive schools program to distribute Youth cards and educate students and staff about how to access and use transit;

- Expand Metro’s Neighborhood Pop-Up program to offer additional mobile outreach and distribution; and

- Improve customer communications about these fare products, how to apply for them, and how to use them.

Metro currently does not have designated funding for these potential strategies. Funding for these strategies wil be evaluated as part of future supplemental appropriation requests or in the 2021-2022 budget deliberations.

# Background

This section provides background information on historic and current conditions related to the limited procurement locations for reduced fare ORCA products and the proviso’s requirements.

## Metro Transit Department Overview

Founded in 1973, King County Metro Transit (Metro) is one of the nation’s 10 largest transit agencies. Metro provides more than 125 million passenger rides annually on a wide range of services, including approximately 200 bus routes, Dial-a-Ride Transit (DART), the Seattle Streetcars, paratransit service for people with disabilities (Access), a commuter vanpool program, and the King County Water Taxi. The American Public Transportation Association named Metro the Outstanding Public Transportation System of the Year in 2018, recognizing its innovative leadership in mobility services, green practices, and programs for customers with low incomes. Metro has provided a reduced fare for seniors since its first year of operation, and since then has developed an array of discounted-fare programs with the goal of enabling everyone in King County to use public transportation. Metro participates in the One Regional Card for All (ORCA) program which standardizes electronic fare payments throughout the region.

## ORCA System Overview

One Regional Card for All (ORCA) was launched in 2009 through an agreement between seven transit agencies to standardize electronic fare payments and to facilitate a coordinated system of interagency transfers across the region – thus providing a better customer experience. ORCA allows passengers to board quickly, reducing time at stops.It reduces fare disputes, and it allows Metro to track regional transit activity for effective service planning. Please see Appendix A for the seven agencies in the ORCA system.

There are 17 full-time equivalencies in Metro’s Mobility Division’s Customer Communications and Services section dedicated to produce regular and reduced fare ORCA cards at the Pass Sales Office and Mail Room at 201 South Jackson Street in downtown Seattle. By interlocal agreement, this team also is regionally funded to handle the mail-in card sales and service requests for the entire region, including Sound Transit, Everett Transit, Community Transit, Pierce Transit, Kitsap Transit and the Washington State Ferries.

Today, about 70% of Metro riders use one of the five types of ORCA cards listed below. There are varying costs, eligibility, and application processes related to each card.

Table 1: Overview of Five Types of ORCA cards

|  | RRFP for People with Disabilities | RRFP for Seniors | ORCA Youth | ORCA LIFT | Adult ORCA |
| --- | --- | --- | --- | --- | --- |
| Eligibility | Proof of temporary or permanent disability status | Proof of 65 years or older | Proof of 6 through 18 years of age | Proof of incomes at or below 200% FPL | N/A |
| Where card can be obtained |
| King Street Center Customer Service Office | ✓ | ✓ | ✓ | ✓ | ✓ |
| Metro Neighborhood Pop Up | ✓ | ✓ | ✓ | 🛇 | ✓ |
| Ticket Vending Machines | 🛇 | 🛇 | 🛇 | 🛇 | ✓ |
| Retail locations | 🛇 | 🛇 | 🛇 | 🛇 | ✓ |
| By phone | 🛇 | 🛇 | 🛇 | 🛇 | ✓ |
| By mail | 🛇 | ✓ | ✓ | 🛇 | ✓ |
| Online | 🛇 | 🛇 | 🛇 | ✓ | ✓ |
| First card fee | No fee | No fee | $5 | No fee | $5 |
| Replacement fee | $3 | $3 | $5 | $3 | $5 |
| Metro bus fare | $1 | $1 | $1.50 | $1.50 | $2.75 |
| Picture required | Yes | No | No | No | No |
| Registration required | Yes | Yes | No | Yes | No |

With current ORCA technology, the first difference between all cards is their Passenger Type. As read by a card reader, the chip on each physical card contains information about the card, in this order:

  - What is the passenger type of this card? (Four options: Adult, LIFT, RRFP, or Youth);

  - Is there a pass product on this card? (Monthly pass, Passport, etc.); and if not

  - How much stored value is in this card’s e-purse?

The passenger type is coded onto the card when it is issued by proprietary ORCA hardware called a Customer Service Terminal (CST), and cannot be changed.  All ORCA cards default to an Adult Passenger Type unless they are coded as a different type. The three reduced fare Passenger Types require ORCA agency staff to confirm the passenger’s eligibility to assign the new Passenger Type at issuance.

Once an ORCA card with a Passenger Type is issued to a customer, that customer manages the account and adds value to pay for fares.  Generally, this means adding value as stored value in an "e-purse" or as a product such as a monthly pass.  Managing an account can be done in-person at an ORCA agency storefront such as Metro’s Customer Service Office, at a Metro Neighborhood Pop Up event in the community, at an ORCA Ticket Vending Machine, by phone with an agency call center, online, or at one of the 130+ retail locations.

## Reduced Fare ORCA Products (RRFP & Youth)

Reduced fare ORCA products provide eligible customers with less expensive access to the transit services of the seven ORCA agencies. These cards require verification of eligibility to acquire, which can result in a more complex process than what customers experience when purchasing a regular adult ORCA card.

To acquire a RRFP or a Youth card, a customer must present a completed application, required payment, and all necessary documentation to Metro staff for review, approval and submission. There are three ways to do this:

- In person at the Pass Sales Office (in King Street Center, 201 South Jackson Street in downtown Seattle);

- In person at Metro Neighborhood Pop-Up mobile outreach events; and

- By mail. In this method, the customer provides copies of any necessary documents along with the application and any required payment. Senior and Youth cards may be purchased by mail, but RRFP Disabilities cards may only be acquired in person because of the photo required by a 16-agency agreement (see below for more information).

Recognizing that mobile outreach was an effective way to expand its sales network, Metro rebranded its ORCA To-Go program as Metro Neighborhood Pop-Up program and expanded the program in 2019 by nearly 50%. Neighborhood Pop-up sales events have successfully reached the eligible populations for these products. In 2019, 87% of the cards sold at these events were RRFP or Youth cards.

## Factors to Consider when Expanding Locations

Metro acknowledges there currently are limited options to purchase reduced fare ORCA products. This section explains various factors that must be considered when seeking to provide more locations for these products. This includes the need to appropriately verify eligibility, the technology and staffing challenges related to the ORCA cards’ production equipment, and the policy restrictions that result from the two overlapping regional interlocal agreements for ORCA and RRFP.

### Documentation Verification and Fraud

Cardholders with reduced fare ORCA cards receive lower transit fares than other riders, so there is an inherent risk of fraud and abuse. Accordingly, staff members at ORCA partner agencies must verify all customers’ eligibility for these cards to ensure that no ineligible riders receive these cards. This duty of consulting appropriate documentation and following specific procedures has not been delegated to any entities outside the ORCA network.

This arrangement contrasts with that of the LIFT partnerships in which partners have the authority to verify eligibility and distribute cards. There are two primary reasons why this is possible. First, the eligibility for LIFT is often confirmed by verifying eligibility through online registries for other government benefits (such as the Supplemental Assistance Nutrition Program). No such central database exists to confirm eligibility for RRFP or Youth cards. The partners then use a common LIFT registry to connect cardholders to the ORCA system. Second, Metro cannot provide and distribute RRFP cards in bulk to partners because the RRFP cards require personal identification information, such as name, photo or expiration date, to be printed on them. This requires a special Customer Service Terminal (CST) specific to the ORCA network. Challenges associated with these CSTs are detailed below.

### Technology Required for Current ORCA Card Sales

The current equipment and software used to produce ORCA cards has significant operational challenges as it is now ten years old. Creating new ORCA cards or loading value into the cards requires a Customer Service Terminal (CST). A CST is comprised of a computer with software, a card reader, and a card printer. These units can be stationary, such as those as the Pass Sales Office windows, or they can become mobile units which are transported on carts, such as those used by Neighborhood Pop-Up program. The card readers are no longer made for this version of ORCA software, so they are only bought at great expense or reconstructed from parts. Because of its age, the current hardware can be difficult to use, and staff report that connections to the Internet can be unreliable when the equipment is used in remote locations.

The equipment and software is proprietary and exclusively serviced by Vix Technology, the creator of ORCA. New replacement parts are often difficult to find and sometimes are no longer in production. VIx’s support contract ends after 2022 as the region moves to a next generation system.

### Staffing and Security Needs for ORCA Card Sales

The sale of ORCA cards involves volumes of cash transactions. This requires adequate security measures as well as senior accounting representatives who must review all transactions and confirm financial activity daily. For instance, when card sales were offered at Westlake Station, an armored car service had to pick up the resulting cash daily. The Pass Sales Office also has bullet-resistant glass and features regular visits from security personnel to maintain a safe environment for staff members and customers. Any additional locations would need to be carefully planned to ensure security.

### Regional Agreements (ORCA and RRFP)

Two regional agreements – ORCA and RRFP – also impact this response. Metro is a party to both agreements, but in each case, the relevant decisions are made through consensus among all parties. Seven agencies in the Puget Sound area are party to the ORCA agreement, and 16 agencies throughout western Washington are party to the RRFP agreement. Senior citizens and customers with disabilities may use their RRFP cards as proof of their eligibility for reduced fares across all 16 of the RRFP transit systems. The ORCA and RRFP agencies are listed in Appendix A.

King County would need to work regionally with other agency partners to change either agreement (such as changing the requirement for a photo for the RRFP card for those with disabilities).

## Ongoing King County Metro Programs

In recognition of the challenges associated with purchasing reduced fare ORCA cards, Metro has three current efforts to improve the customer experience: 1) the development of an online portal to allow electronic card applications; 2) the expansion of the Metro Neighborhood Pop-Up (formerly ORCA To-Go) program in which mobile teams provide ORCA sales, reloading and customer services throughout King County; and 3) participation in the complex, regionally collaborative development of ORCA Next Generation, which will replace the current ORCA system in 2022.

### Online Portal

In 2019, Metro began development on a software program that will enable individuals to apply for reduced fare cards online. This program will allow individuals to apply for these cards from any place where they have Internet access. Users will have the capability to upload electronic documentation regarding their eligibility instead of mailing the documentation to King Street Center or presenting it in person.

Per the program’s current design specifications, it will also allow users to upload pictures, so customers who are seeking an RRFP Disabilities card will be able to provide all the required information remotely. Metro staff members will then create the cards and mail it to the customers’ homes. This will allow customers with disabilities to avoid taking an extra trip to a Metro facility or event.

Metro staff believes that this portal could potentially be popular with youth seeking ORCA Youth cards. Given the timeline of the project and the technology parameters, the portal will not be able to support financial transactions. If Metro allows youth to obtain cards via the portal, it will not be able to collect the youth card fees.

This portal is scheduled to be available in Q4 2020.

### The Metro Neighborhood Pop-Up Program

In March 2019, the Westlake Customer Service Center in the downtown bus tunnel closed when Sound Transit assumed operations of the bus tunnel. This made the King Street Center Pass Sales Office the only permanent, in-person site in all of King County for the sale and service of ORCA cards during regular business hours.

Westlake’s closure resulted in three customer service terminals available for other uses. These were redeployed in April 2019 as part of an expanded ORCA To-Go program – now called the Metro Neighborhood Pop-Up program – which serves around 30 individual sites every month throughout King County. Typically, two Pass Sales Office representatives use a mobile customer service terminal to support customers’ needs for about a two-hour window. Customers who attend these mobile outreach events can conduct most of the same transactions that are available at the Pass Sales Office in downtown Seattle.

### The Next Generation of ORCA

Metro is working with the other ORCA agencies to design a replacement and successor to the original 2009 ORCA system. “Next generation ORCA” is expected to launch in 3rd quarter 2021. The new system will be an account-based system, which will allow funds to be loaded into accounts nearly instantly instead of the current 24-48 hour delay. This change will allow expanded mobile options for fare payment and easier replacement of lost cards or other fare media.

Next gen ORCA will improve the customer experience in other ways as well. Technical capabilities of next gen ORCA and regional policy will enable individuals seeking Senior or Youth cards to order their cards online at the next gen ORCA website, without sending proof of age in by mail or bringing documentation to a Metro location. Instead, customers will be able to upload documentation electronically, which would then be reviewed and approved remotely by Metro staff in the Mail Center, and the appropriate Regional Reduced Fare Permit (RRFP), Senior card or Youth card would then be mailed to the customer.

People with disabilities that need a RRFP Disabled card could apply for a card online through the planned online reduced fare portal, which could be set up to provide information to next gen ORCA either through an export process, or potentially in next gen ORCA phase II through an integrated solution.

Metro predicts that implementation of online ordering of Senior and Youth cards in next gen ORCA and/or the reduced fare online portal would reduce the need for physical locations where people can apply for reduced fare ORCA cards. However, Metro also believes the need for in-person customer service generally will remain because people – particularly in disadvantaged populations, or those who lack easy access to technology – benefit from the ability to get assistance in person.

# Research and Strategy Development Methodology

Given the current and historic conditions related to this issue, Metro staff analyzed the requests of the proviso to determine which creative solutions to this challenge could provide clear strategic value to customers in a cost-effective manner. Metro first identified that it and the Council have a common goal of expanding access to reduced fare ORCA products for all qualifying King County residents.

## Constraints and Opportunities

Before creating a list of potential policy responses to the proviso, Metro staff identified several constraints and opportunities related to the current conditions and the requests in the proviso:

- Technological Restrictions to Expansion Opportunities: The production of reduced fare ORCA cards requires the presence of a customer service terminal. Mobile or remote operation of this would require two Metro staff members. This means that new cards can be offered at new sites only if new customer service centers are opened there; this is very expensive, and not enough new cards will be generated to justify the expense. Additionally, the need for in-person transactions may decline after the launch of ORCA Next Generation in 2022 because customers will no longer need coded cards to use their ORCA account (i.e., information on the card type will live in the online account, not on the card).

- Need for Equity Considerations to Lead Decision-Making: Locations can be created anywhere in King County. To reach the most people and align with the Equity and Social Justice Strategic Plan, Metro staff recommend that services be provided near the largest populations that are in need of them.

- Multiple Barriers to Obtaining  Reduced-Fare ORCA Products: Lack of physical access to application locations may not be the only -- or even the greatest -- barrier to the procurement and use of these cards. For example, the application itself and documentation requirements can also be confusing.

On the other hand, Metro agrees that the current procurement locations are challenging for many customers to reach. The proviso’s invitation to innovate is an opportunity to generate new ideas. The staff notes the following areas of opportunity in this research:

- Many Supporters and Partners: Many other organizations serve people who are eligible for these cards. These partners agree that there is a benefit to expanding access to the cards, and they may be able to assist in the implementation of additional locations.

- Chance to Address Multiple Barriers: Other barriers may be addressed if locations are added. Improvements can be made regarding communication about the ORCA card types, the application process, and the cards’ use.

- Improving Technology: The technology related to ORCA cards and mobility as a service is improving. The staff can leverage these improvements to improve efficiency and enhance the customer experience if locations are added.

## Potential Opportunities

Realizing these constraints and opportunities, Metro identified the following eight potential strategies to create new locations for procuring RRFP and Youth ORCA cards:

- Create a new, standalone Metro customer service center that would offer ORCA sales.

- Co-locate a customer service center for ORCA sales with a Seattle & King County Public Health Center.

- Delegate ORCA sales to an outside organization and transfer equipment to its custody.

- Offer a program in collaboration with community organizations to provide application assistance to customers.

- Create a network of agencies that provide verification for RRFP and Youth cards. This model is similar to the one in which passport agencies accept documents and process materials on behalf of the US Department of State.

- Expand Metro’s Neighborhood Pop-Up program.

- Expand institutional distribution through schools.

- Expand institutional distribution in other ways.

Given technical and staffing challenges, Metro began this analysis by assessing the value of strategies that would expand types of locations, after which data analysis provided further insights and suggestions for appropriate, specific geographic locations around the County for these types of new locations. Preferred locations are those which are accessible to those who need services and reach many likely customers.  The analysis is explained below.

## Evaluation Criteria

Each strategy was evaluated against several criteria, namely whether they were feasible, easy for customers to understand and access, equitable according to the ESJ strategic plan and Metro’s data analysis, and aligned with input from stakeholder outreach while also being likely to result in significant card distribution.

### Feasibility

The first criterion relates to whether the concept is feasible. Any new location would require an investment of resources, including staff members to create and support it. Additionally, many innovations require partnerships and cost-sharing to implement. The following questions relate to feasibility:

- Resource Use: Would this be an effective use of resources? What is the estimated cost of each additional location?

- Partnerships: Can the proposed partner organization work effectively with Metro? Will the training investment pay off? Is there high turnover? Is the staff familiar with document verification for this or other programs? Does the organization and its staff have the capacity to take on new responsibilities regarding card distribution and management?  Are there labor considerations to this proposal?

- Risk Management: Does this strategy effectively protect sensitive financial, personal and medical data? Can Metro’s financial system verify and protect transactions involving all payment types?

### High Impact/Ability to Distribute Many Cards

The second criterion is whether the location could generate significant card sales. Metro shares the goal of connecting as many people as possible in King County with the appropriate ORCA card. To assess this, Metro estimated how many cards would be generated at each location, based on past data from similar locations, foot traffic, and ease of travel to the location by car and transit.

### Easier Customer Experience

Metro considered the third criterion of whether each potential new location would offer an easier customer experience. Is the location easy to access? Will customers understand where it is, or how to use it? Many locations could be created, but certain types are easier access than others. As well, some are easier to communicate to customers than others.

The following questions relate to the customer experience:

- How comfortable would customers be in accessing this location?

- Does the organization protect their privacy while handling sensitive medical, personal and financial information?

- How easy is the communication process for customers?

- Can customers acquire all reduced-fare card types at this location, and are all payment types accepted there?

### Alignment with Equity and Social Justice Strategic Plan

The fourth criterion was whether the specific investment would be equitable. In developing this response, Metro was guided by King County’s Equity and Social Justice Strategic Plan, focusing on “investing upstream where the needs are greatest.” All staff members who led engagement and outreach had received training in the Equity and Social Justice Strategic Plan and in the correct implementation approaches, and they advised the team accordingly.

The following questions relate to equity:

- Does this investment occur where needs are greatest?

- Does it take resources from other Metro investments that would more effectively help populations that need assistance?

Spatial Analysis

To determine alignment with the Equity and Social Justice Strategic Plan, Metro did a spatial analysis of both where potential Youth, Senior RRFP and Disabled RRFP cardholders reside, and where existing registered Youth, Senior RRFP, and Disabled RRFP cardholders lived. Metro used American Community Survey (ACS) Data 2017 5-Year estimates to estimate how many individuals, by census tract, were eligible to receive Youth, Senior RRFP, and Disabled RRFP cards. Using this data, Metro used ArcGIS to map out the density of eligible populations (by passenger type) across King County. Metro also used ORCA data to identify where existing registered Youth, Senior RRFP and Disabled RRFP cardholders live.

Using both datasets, analysis was conducted to compare registered card use against eligible population per census tract. Census tracts fell into one of five quintiles for both estimated eligible population density and for density of registered cards.  A comparison of the two indicated whether registered cards for that census were representative or over/under-represented, and to what degree. See Appendix B “Equity Analysis: Utilization Gaps in King County” for map of card over/underrepresentation. Locations that showed more underrepresentation in reduced fare card distribution and locations with a higher 2017 equity score were used to create an initial list of locations to consider for new in-person service centers or for other strategies to increase Youth and RRFP card enrollment.

Once initial locations were selected, additional criteria were examined to identify locations that would have a higher equity outcome. These criteria included: density of households with school-age children, percentage of individuals living at or below 200% of the Federal Poverty Level, percentage of individuals born outside of the United States, number of people with Limited English Proficiency, and if that census tract was identified by the Mobility Framework as an area of greatest need.

Metro also examined census tracts for features that would make it successful location, including access to transit (such as if there is a transit hub and number of bus routes) and foot traffic (determined by number of shops in the area that could attract a lot of customers to the Customer Sales Office).

## Alignment with Results of Stakeholder Outreach

Finally, strategies were evaluated against whether they aligned with the result of the outreach and engagement conducted for this proviso response. The implementation plan was informed by engagement from October 2019-January 2020 with populations that would be eligible for a reduced fare ORCA card, including youth ages six to eighteen, seniors ages sixty-five and over, and individuals with disabilities; and parents of youth, schools, other stakeholders, and members of the public. The engagement process solicited input on what are the barriers to immediately accessing the existing reduced fare ORCA cards and suggestions for more accessible and convenient procurement locations and enrollment processes for these ORCA cards. This engagement was carried out in conjunction with other Metro fares outreach and engagement efforts.

### Description of Outreach/Engagement

As Metro began development of this implementation plan, it sought guidance and input from people who are most directly engaged with the reduced fare products – youth, parents, seniors, people with disabilities, and representatives of organizations that support these individuals.

In-person surveys of groups of youth, seniors, and/or those with disabilities and stakeholder conversations were guided by the following questions.

- Do you or the people you serve know about and use Metro’s reduced fares for youth, seniors, or those with disability?

- Was getting your card easy or hard? Why?

- What actions should Metro take to make it easier to obtain a reduced fare card?

- Are there barriers other than access to physical locations that Metro hasn’t considered? What else makes it difficult to use a RRFP ORCA or Youth ORCA?

Qualitative research was conducted with 18 participants, all of whom were current Metro Transit RRFP users and/or caregivers of ORCA Youth card users. These focus groups and in-depth telephone interviews were conducted with the aim of understanding the target groups’ access to applying for and obtaining Regional Reduced Fare Permits or ORCA Youth cards. Additionally, participants were asked questions about different barriers that might prevent target groups from easily applying for and obtaining a reduced fare ORCA card. Participants also provided recommendations for application or customer service locations.

## Recommended Strategies

The eight potential strategies in Section IV, part B were analyzed against feasibility, impact, customer experience, equity, and alignment with stakeholder feedback. The results of this assessment are shown below, with the darker the shade equal to a stronger correlation:

Table 2: Analysis of Available Strategies to Expand Reduced Fare ORCA Card Procurement Locations

| Strategy | Feasible | High Impact | Easier Customer Experience | Equitable | Aligns with Outreach |
| --- | --- | --- | --- | --- | --- |
| Create new, standalone customer service center | ¡ | ¡ | l | l | l |
| Co-locate a customer service center with a Seattle & King County Public Health Center | l | ¡ | l | l | l |
| Delegate ORCA sales to an outside organization and transfer equipment to its custody | ¡ | ¡ | l | l | l |
| Collaborate with community organizations to provide application assistance to customers | l | ¡ | l | l | l |
| Create a network of agencies that provide verification for RRFP and Youth cards | l | l | l | l | l |
| Expand Metro’s Neighborhood Pop-Up program | l | l | l | l | l |
| Expand distribution through schools | l | l | l | l | l |
| Expand distribution through other ways | l | l | l | l | l |

Feasibility

The most feasible of the options evaluated were expanding Metro’s NPU program, creating a network of verifying agencies, and co-locating a new customer service center in a King County facility because these options represent just an expansion of current operations. The least feasible option is delegating ORCA sales to an outside organization because of the need to receive approval from the seven ORCA agencies to do so as well as the security risks associated with the legacy ORCA machines. Creating a new standalone customer service center also did not score high because of the cost.

High Impact

Strategies that can meet customers where they are greatly reduces the amount of barriers that they might otherwise face in obtaining a reduced fare ORCA card. Expanding distribution through schools is the option with the highest impact, because in addition to bringing cards to where the Youth are, its proposed comprehensive transit education program also provides Youth with the knowledge of how to use their Youth ORCA cards and how to ride transit, helping to develop the next generation of transit riders. The option with the lowest impact is creating a new, a standalone customer service center because it requires customers to go in-person to a physical location during work hours and an additional location does not address issues that many customers might currently face in getting to the existing Customer Service Office at King Street Center.

Customer Experience

Strategy options were evaluated on how simple and streamlined it would be for customers to obtain a reduced fare card. Collaborating with community organizations to provide application assistance to customers and creating a network of agencies that provide verification for RRFP and Youth cards both ranked highly because they provide options to apply for reduced fare cards at locations that customers are already visting and comfortable with, and potentially also closer to them. Expanding distribution through schools and expanding distribution through other ways also ranked highly in terms of customer experience because they significantly reduce the steps required for eligible cardholder to get a card, making it easier for customers to obtain the reduced fare card that is right for them.

Equitable

King County’s Equity and Social Justice Strategic plan calls for investments where needs are the greatest.  As detailed later in this report in Section V.A, Metro’s equity analysis indicates that ORCA reduce fare card use is underrepresented primarily in areas of south King County.  Analysis of utilization along with other factors such as equity score, access to transit, and foot traffic highlighted the following areas as the top as the top locations to consider:

- Federal Way

- Kent

- Auburn

- Burien

- Bellevue Crossroads

Therefore, the most equitable approaches are those that can be designed to ensure a focus on the populations in the above areas relative to promoting access to reduced fare cards, namely collaborating with community organizations to provide application assistance to customers, creating a network of agencies that provide verification for RRFP and Youth cards, expanding distribution through schools, and expanding distribution through other ways.

Aligns with Outreach

As detailed later in this report in Section V.D, Metro’s outreach and engagement indicated the following major themes:

- Access to physical ORCA enrollment locations is not the only or the greatest barrier. More time is needed to gain a deeper understanding of other barriers these populations may face to ensure an increase in physical locations is successful and helpful.

- The current application processes for reduced fare cards is confusing and should be improved. Application assistance could benefit all audiences, including trained service providers, school staff, etc.

- Metro should go where the community already is, and leverage relationships that already exist between community and organizations to improve this work.

- Improved marketing and education can help reach these specific populations.

- For better access to ORCA Youth cards, the business hours and locations of an enrollment location need to work for working parents and students.

- An online option is needed for added flexibility for families that cannot go to physical locations due to the limited hours and days of operation.

Based on the above feedback, the highest scoring options were those that work with community based organizations and schools to help individuals apply for and access reduced fare cards or that take advantage of areas in the community that populations used anyway to promote access to and improve knowledge of reduced fare cards.  Those high scoring options include  collaborating with community organizations to provide application assistance to customers, creating a network of agencies that provide verification for RRFP and Youth cards, expanding Metro’s Neighborhood Pop-Up program, expanding distribution through schools, and expanding distribution through other ways.

Conclusion

As a result of the assessment against criteria, data analysis, and stakeholder engagement process, the Metro staff recommends the following four strategies for potential implementation:

- Create a network of agencies to verify RRFP and Youth card eligibility. This model resembles passport agencies, which accept documents and process materials for the US Department of State. Through a two-phase process, Metro combined this idea with a second strategy (“Offer a program, in collaboration with community organizations, to provide application assistance to customers”) to better reach the populations with the greatest need where they live. Metro may look to do this regionally with Snohomish and Pierce to mirror other fare programs and to best serve customers who travel throughout the region.

- Expand school partnerships to include distribution of youth ORCA cards and educating students on how to access and use public transportation. This would be a one-time expenditure in 2021 to evaluate the opportunities of stronger partnerships with schools.

- Expand Metro’s Neighborhood Pop-Up Program.

- Improve communications to customers about fare products and their use.

These are identified as potential new strategies alongside the ongoing innovations of the Executive Branch to expand access to these cards, as outlined in Section III, Part E, “Ongoing Executive Branch Programs.”

The Metro staff do not recommend the following options as they are the least cost effective in reaching many people:

- Create a new, standalone customer service center that would offer ORCA sales.

- Co-locate a customer service center for ORCA sales with a King County Public Health Clinic.

- Delegate ORCA sales to an outside organization and transfer equipment to its custody.

- Expand institutional distribution in other ways.

# Report Requirements

## Locations Considered

This implementation plan considered public health clinics, retail locations, buildings where government services are provided such as city halls, libraries, schools, mobile outreach in vans, community organizations, social services agencies, the King County Executive Services Records and Licensing Division office in Kent, community colleges, and King County Department of Local Services office in Snoqualmie. All options assumed the mobile outreach Neighborhood Pop-Up program, formerly known as ORCA To-Go, would continue offering service throughout the county.

Metro worked to ensure that all proposed additional locations would use County resources in an equitable way to reach priority populations and locations where needs are greatest. Metro determined these locations according to where populations live in King County, as well as by identifying areas where card-utilization rates are below expectations, areas where there are high numbers of people with low incomes and/or limited English proficiency, as well as areas with high racial and ethnic diversity. Metro additionally evaluated locations against King County’s Equity Score, access to transit, and foot traffic.

After reviewing all the options, Metro is recommending no new physical locations, but instead is recommending efforts be focused on areas highlighted by the spatial analysis as having both low reduced fare card distribution compared to the eligible population and higher proportions of priority populations. As such, Metro is recommending that efforts should be focused primarily in South King County, particularly Federal Way, Kent, Auburn Burien, as well as Bellevue Crossroads.

## Estimated Costs, FTE and Contracting Needs, and Proposed Funding Sources

The summary of all estimated costs and revenues for the identified strategies are shown below. Specific information about each recommendation is listed later in the document.

Projected Net Program Costs

| Net Impact | Y 2019-20 | Y 2021-22 | Y 2023-24 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Total Expenses | $1,080K | $1,609K | $1,712K | $1,789K | $5,110K |
| Revenue | $11K | $1,041K | $2,074K | $2,773K | $5,888K |
| Net Costs | $1,069K | $568K | -$362K | -$984K | $-778K |

Capital Expenses (One-Time)

| Estimated Expenses | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Verifying Agencies | $897K | - | - | - | - |
| NPU Expansion | - | $60K | - | - | $60K |
| Total Capitol Expenses | $897K | $60K | - | - | $60K |

Operating Expenses (Ongoing)

| Estimated Expenses | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Verifying Agencies | - | $653K | $776K | $812K | $2,241K |
| Schools Program | - | $394K | $406K | $419K | $1,219K |
| NPU Expansion | $183K | $402K | $426K | $450K | $1,278K |
| Improved Communications | - | $100K | $104K | $108K | $312K |
| Total Operating Expenses | $183K | $1,549K | $1,712K | $1,789K | $5,050K |

Revenue Details

| Revenue Impact | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Projected Revenue | $11K | $1,041K | $2,074K | $2,773K | $5,888K |

## Potential Policy Changes

Several policy changes could enable broader distribution of these cards or easier communication to customers of how to procure and use them.

- Subsidize fees for ORCA Youth cards or work regionally through ORCA to eliminate fees. Alternatively, align fees with those of RRFPs to allow first cards to be issued without charge and replacement cards to cost $3.00. The need to charge a fee for the card restricts how the cards can be distributed and complicates the transaction significantly. For example, the online application portal, scheduled to launch in 2020, will not be able to accept payment for the Youth cards. When the costs have been subsidized, Metro has been able to distribute Youth cards quickly. Youth often don’t have much money in their control, so requirements to charge card fees for Youth cards make Youth cards are more challenging to distribute and less appealing for Youth to seek and use.

- Work regionally to revisit or remove requirement for picture on Disability RRFP card.

Due to technical limitations of current ORCA equipment, only a new full Customer Service Center staffed by Metro staff or the deployment of ORCA Next Generation will expand the number of physical locations at which ORCA cards can be immediately issued.

## Engagement Activities

Metro conducted engagement for this proviso from October 2019-January 2020 with populations that would be eligible for a reduced fare ORCA card, including youths ages six to eighteen, seniors ages sixty-five and over, and individuals with disabilities; and parents of youth, schools, other stakeholders, and members of the public. The engagement process solicited input on what are the barriers to immediately accessing the existing reduced fare ORCA cards and suggestions for more accessible and convenient procurement locations and enrollment processes for these ORCA cards. This engagement was carried out in conjunction with other Metro fares outreach and engagement efforts. Activities included community meetings, an online survey distributed through social media, individual interviews and a focus group.

### Major Themes/Takeaways

- Access to physical ORCA enrollment locations is not the only or the greatest barrier. More time is needed to gain a deeper understanding of other barriers these populations may face to ensure an increase in physical locations is successful and helpful.

- The current application processes for reduced fare cards is confusing and should be improved. Application assistance could benefit all audiences, including trained service providers, school staff, etc.

- Metro should go where the community already is, and leverage relationships that already exist between community and organizations to improve this work.

- Improved marketing and education can help reach these specific populations.

- For better access to ORCA Youth cards, the business hours and locations of an enrollment location need to work for working parents and students.

- An online option is needed for added flexibility for families that cannot go to physical locations due to the limited hours and days of operation.

### Outreach/Engagement by Group

Participants expressed frustration with obtaining the ORCA Youth card and Disability RRFP for reasons regarding both location/logistics and application process/communication. Cultivating a more robust outreach and ORCA RRFP communications campaign, expanding physical locations, improving the application process and form, pursuing schools distribution for ORCA Youth cards, and having an online application portal were all popular solutions to identified barriers. Several participants expressed the need for a diversity of solutions because the ability to access different locations physical or online will be different from population to population and person to person.

## The section below summarizes findings for each audience identified in the proviso.

Youth (30 youth; 3 staff who serve about 50-75 youth)

Metro participated in a conversation with staff members at the Burien Community Center to discuss access to ORCA and transit for youth and seniors. Metro also conducted a brief survey with youth at the Vietnamese Friendship Association homework help program at the Seattle World School. .)

Results/Key Themes:

- Some youth have no funds to load onto a Youth card.

- Business hours and days of operation of Neighborhood Pop Up program should be extended because students can’t leave school.

- Onsite distribution at schools would be effective because this is where the youth are.

- There is a need for improved bus service for students who don’t qualify for the school bus.

- The process for getting ORCA and using it is a barrier for families who speak limited English.

- Overall, lack of awareness of ORCA and transit services is a barrier.

Seniors (3 agency staff, who served as proxies because their organizations serve seniors; 11 focus group participants)

Metro met with staff at Hopelink, a social service and transportation provider, the senior programs coordinator at the Burien Community Center, and the program coordinator at the University District Food Bank.  Feedback for this audience was prioritized less than that from youth and people with disabilities because seniors generally have more options to procure a card. They also tend to have more flexible schedules, which makes options like Neighborhood Pop-Up easier for them to use.

Results/Key Themes:

- Libraries and community centers are convenient enrollment/distribution locations for seniors, who already use other services at those locations and are often familiar with the staff.

- Neighborhood Pop Up staff could provide more value by sharing information about other Metro services and reduced fare programs.

- Neighborhood Pop Ups at community centers are helpful for seniors since they are already there.

- The RRFP application is confusing and cumbersome, and seniors require assistance from social service provider staff members. The RRFP application should be separated into two applications – one for seniors, and one for people with disabilities.

People w/ disabilities (56 consulted and 3 focus group participants)

Metro conducted a brief survey and discussion with members of the King County Mobility Coalition, an advisory board of King County Metro, which facilitates the coordination of King County special needs transportation options. This includes special needs transportation providers, clients and funders of services, and interested governments, non-profit partners, and for-profit partners from rural and urban areas of King County. Metro also had an extended stakeholder conversation with Hopelink’s Mobility Coalition coordinators. Finally, a focus group and individual interviews were held in January which included three people with disabilities.

Results/Key Themes:

- Community centers, senior centers and libraries are the best enrollment/distribution locations for people with disabilities

- The RRFP application is confusing. The RRFP application should be separated into two applications – one for seniors, and one for people with disabilities. The application is cumbersome and seniors require assistance from social service provider staff members.

Parents/Caregivers (116 consulted)

Metro conducted a brief parent survey promoted through Metro’s social media channels including Nextdoor, Facebook and Twitter and through paid advertising on Facebook. The ads ran from Jan. 4 to Jan. 13 in both English and Spanish. Overall, 83 participants took the online survey.

Metro also spoke with parents at the Vietnamese Friendship Association, at a Spanish-speaking family English class, and a job readiness class with Vietnamese-speaking parents.

Results/Key Themes:

- Greater education/awareness of how to use transit services and ORCA is needed, especially for families with limited-English proficiency and recently resettled refugees. In-person training is preferred.  Parents, especially those with limited-English proficiency and recently resettled refugees, need more education/information about transit services.

- The business hours of the downtown Seattle location, and the fact it is only open on weekdays, do not work for working families. Any physical location would need greater flexibility with extended hours and weekends to accommodate working parents.

- Parents - mainly surveyed parents - want an option to apply for youth cards online. They also wanted to be able to scan documents, to use student IDs as proof of age and  greater clarity about what constitutes “proof of age.” Mail-in application option works, but only if you have stamps and a printer.

- There were concerns about affordability of transit fares. Some believe that customers, especially youth, should not pay for public transit. Some thought that some families may not have enough income to load money onto an ORCA card.

- Some parents expressed safety concerns associated with their children riding the bus.

School district/provider staff (6 staff members consulted):

Metro met with school district staff who coordinate the following services in their districts: family engagement, McKinney Vento (homelessness) services, and student support services. School district staff were from from North Shore School District, Bellevue School District, Kent School District Support Services, Lake Washington School District and Tukwila School District, as well as one staff member from Treehouse for Kids, a foster care youth service provider.

Results/Key Themes:

- There is a value for youth to have ORCA cards.

  - Students, especially those experiencing homelessness or who have low-incomes, often forgo opportunities for after school clubs, jobs, sports or other programs because they don’t have reliable transportation to and from those activities.

  - Summer use of ORCA cards can be very beneficial for students, supporting access to explore opportunities for growth during the summer like clubs, sports, and other activities.

  - There were concerns the age limit of ORCA Youth cards was too low. Age limit to 18 leaves out a lot of students who are still in the public school system until they are 21.

- Schools are the most convenient access point.

  - Distributing cards at school would be challenging for schools to manage given current workload. There should be a dedicated staff person at schools or the district to manage card registration; some school staff may not have capacity to do this type of work even with training.

  - Foster youth could benefit from a dedicated person that manages their card if it’s received through school; they often switch schools.

- Students often have little money, but students need funds to load and use an ORCA card.

  - Youth often only have cash, so they must be educated on how and where to reload their cards with cash. There is a need for more physical locations where students can add cash, and these locations need to be well-publicized.

  - There was a suggestion to have an app for reloading money onto cards and online training in multiple languages.

- There is a need for more, multi-lingual education and awareness of transit options among parents and youth.

  - Language barriers still prevent families from learning how to use transportation and how to obtain/reload ORCA cards using the internet or other methods.

  - Students need to know about transit options and how to use them. Some may need incentives.

- The application is confusing. It should be for youth cards only.

EMC Research - Focus Group

Metro contracted with EMC Research to conduct additional research using focus groups to understand needs, barriers, preferred service locations and service providers for those eligible for RRFP and Youth ORCA cards. Please see Appendix C – “EMC Research Report on Focus Groups” for the full report.

## Expansion Marketing

Each strategy would be marketed in a different way, which is specified in its implementation plan. Methods include marketing new locations through partners, social media, and information on the Metro website.

| Strategy | Additional Funding Requested | Materials/Strategy Collaborators | Targeted Audience |
| --- | --- | --- | --- |
| Network of Verifying Agencies | $156K (2021-2026) | Customers Enrollment agencies | Youth Seniors People with disabilities People with low incomes |
| School Distribution | None at this time | Students Caregivers School staff Other stakeholders | Schools with highest percentages of Free and Reduced School Lunch Program |
| Expand Metro's Neighborhood Pop-Up | None at this time | Community partners | NPU host site community members General marketing |
| Improved Communications | None at this time | None at this time | General marketing |

Please see Section VI “Implementation Plan for Recommended Strategies” for more information.

## Potential Partners/Partnerships

Each strategy includes a method for seeking partners. As all programs are new, Metro would need to seek partners for each for the programs to be successful. As funding is limited, Metro transit department would partner and seek partners to serve as locations by finding those to whom this program is of mutual benefit.

| Strategy | Additional Funding Requested | Potential Partners/Partnerships |
| --- | --- | --- |
| Network of Verifying Agencies | $855K (2021-2026) | Phase 1: Harborview DSHS Seattle & King County Public Health Phase 2: Senior centers Youth centers Community centers Libraries |
| School Distribution | None at this time | School districts |
| Expand Metro's Neighborhood Pop-Up | None | Hopelink Neighborhood Pop-Up host partners |
| Improved Communications | None | ORCA agency partners |

Please see Section VI “Implementation Plan for Recommended Strategies” for more information.

## Populations Anticipated To Be Served at Each Location

| Strategy | Primary Populations to be Served |
| --- | --- |
| Network of Verifying Agencies | Youth Seniors People with disabilities People with low incomes |
| School Distribution | Youth |
| Expand Metro's Neighborhood Pop-Up | Youth Seniors People with disabilities People with low incomes |
| Improved Communications | General population |

Please see Section VI “Implementation Plan for Recommended Strategies” for more information.

## Map of the Potential Locations

A map is included in each strategy’s implementation plan.

## Potential Schedule for Opening the New Reduced Fare ORCA Card Procurement locations

| Strategy | Potential Schedule for Opening New Locations |
| --- | --- |
| Network of Verifying Agencies | Portal ready in 2020 Bring in partners 2021 |
| School Distribution | Start of 2021-2022 school year |
| Expand Metro's Neighborhood Pop-Up | 2021-2022 |
| Improved Communications | 2021-2022 |

Please see Section VI “Implementation Plan for Recommended Strategies” for more information.

# Implementation Plan for Recommended Potential Strategies

Below are the implementation plans for the identified potential strategies to expand procurement locations.

## Create a Network of ORCA Verifying Agencies

The first potential strategy is to open a network of “verifying agencies” to help individuals apply for reduced-fare ORCA products throughout the County. This model was inspired by the successful model of passport offices for the U.S. Department of State. In communities, the U.S. Department of State – Consular Affairs Bureau delegates authority to public institutions like post offices and City Halls to review documents and accept materials on the Departments’ behalf for greater customer convenience.

Staff at the verifying agencies would be able to accept an individual’s reduced fare ORCA card applications and help verify their eligibility. This strategy leverages incoming technology improvements and successful partnerships from the LIFT distribution model to create new locations. This responds to the feedback from the engagement process that people wanted to apply for these cards in locations throughout the County which are open during regular business hours, and that application assistance for these fare products would be beneficial.

### Description

The current limited number of ways and places that individuals can obtain a reduced fare ORCA card places an unfair burden on some of the most vulnerable populations in King County, especially those with disabilities who can only apply at the Pass Sales Office at King Street Center or at a Neighborhood Pop-Up event.

In this strategy, Metro would leverage the new online portal to substantially increase accessibility and registration of Metro’s reduced fare programs and advance King County's Equity and Social Justice (ESJ) goals. A network of verifying agencies, rolled out in a phased approach, would help individuals use the online portal and help confirm eligibility. Metro would then fulfil the orders and mail the appropriate card within the week.

In Phase 1, the network would include 28 locations with Harborview Medical Center, Department of Social and Health Services (DSHS), and Seattle & King County Public Health. These agencies are experienced in verifying eligibility for several programs, including the LIFT program, and serve customers eligible for reduced fares.

In Phase 2, Metro would expand the number of participating agencies and locations. Metro would make efforts to partner specifically with senior centers, community centers, youth centers and libraries, as well as open opportunities for other interested agencies.

### Estimated Program Costs and Revenues

The estimate for creating and maintaining the online portal and the associated verifying agencies network using through the end of 2026 is estimated at $2,241,000. This includes already budgeted capital funds for the online portal.

The program would require hiring a Project/Program Manager. Increased demand either in the mail room or to manage agencies could result in a request for additional staffing. If this happens, Metro will request funding from Council at that time.

Revenue assumptions are based on purchasing trends observed in Neighborhood Pop-Up sales. Specifically, roughly half of cards issued are to new customers, roughly half of those new customers might add $20 one time to their E-Purse, and only a small percentage of new customers would purchase a monthly pass periodically (roughly every other month). Revenue estimates also include attrition each year and include costs to subsidize card fees returning to Metro in the form of revenue. See “Potential Policy Changes” below for more information.

Program Net Costs

| Estimated Expenses | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Expenses | $897K | $653K | $776K | $812K | $2,241K |
| Revenue | - | $270K | $620K | $900K | $1,790K |
| Net costs | $897K | $383K | $156K | $88K | $451K |

Capital Expense (One-Time)

| Estimated Expenses | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Portal creation | $897K | - | - | - | $897K |

Operating Expenses (Ongoing)

| Estimated Expenses | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Wages & benefits (1.0 FTE) | - | $275K | $292K | $309K | $876K |
| Portal maintenance and Licenses | - | $34K | $35K | $36K | $105K |
| Marketing | - | $50K | $52K | $54K | $156K |
| Card stock | - | $40K | $54K | $56K | $150K |
| Card fees | - | $22K | $30K | $31K | $83K |
| Materials & travel | - | $5K | $5K | $6K | $16K |
| Agency reimbursements | - | $227K | $308K | $320K | $855K |
| Total operating expenses | - | $653K | $776K | $812K | $2,241K |

Revenue Details

| Revenue Impact | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Projected Revenue | - | $270K | $620K | $900K | $1,790K |

### Potential Policy Changes

Metro would propose to subsidize the card fee in this strategy. Due to constraints in the online portal system, collecting fees for new and renewal cards would require Metro to create a separate process for collecting and processing payment, which would create additional barriers and burdens for customers and negatively impact their customer experience. Additionally, the staffing costs required to set up a process to collect card fee payment would be greater than the card fees that would be collected.

By subsidizing the card fee, Metro could ease the enrollment process for clients, show the true cost of the program, and proceed without needing to obtain approval from the rest of the ORCA transit agencies. A portion of card fees would return to Metro in the form of revenue as card fees are split up between the ORCA transit agencies.

Another option is to waive the card fee, where neither customers nor any transit agencies are responsible for collecting nor paying card fees. Waiving the card fee would require regional approval from the other ORCA transit agencies and could potentially delay program rollout.

### Engagement

Metro received input for this strategy through consultation with youth, seniors, people with disabilities, caretakers, parents, and schools. Through the engagement process, Metro heard feedback that people wanted to apply for these cards in locations throughout the County which are open during regular business hours, and that application assistance for these fare products would be beneficial.  Please see the engagement process summary in Section V, Part D “Engagement Activities” for more information.

### Marketing

Metro would engage customers and enrollment partners to create materials that are available in multiple languages, easy to read, and culturally appropriate. Metro would work with partners to trans-create marketing materials into King County’s tier 1 and tier 2 languages. Marketing efforts would be targeted mostly in spaces where large concentrations of populations eligible for reduced fares frequent or reside in but would also be marketed broadly. Metro anticipates using several different types of communications tools and strategies; the materials would use simple language and images to describe the program and locations where customers can apply for reduced fare cards.

### Partnerships

For Phase 1, Metro would launch this network with Harborview Medical Center, eight Public Health locations and all 17 DSHS offices that currently enroll customers in ORCA LIFT. A map of these locations is shown below, and the addresses of these locations are shown in Appendix D.  These locations were determined in consultation with partners and were chosen because staff at each of the three agency types have experience with verifying information and distributing LIFT cards. Harborview currently verifies customers for Disabled RRFP eligibility and can also verify the age requirements for Senior and Youth reduced fare programs. DSHS and Public Health are currently verifying identity for their health and human service programs, as well as for LIFT eligibility, and would be able to extend verification services for other reduced fare programs.

For Phase 2 partnerships, Metro proposes to reach out to senior centers, municipalities, community centers, libraries and youth centers as well as solicit an open call for partners. There are two ways that agencies can be partners in Phase 2:

- Becoming a verifying agency. In this model, new agencies would take on a role like partners in Phase 1. Enrollment agencies would be held responsible for accurately verifying a customer’s eligibility for a Youth, Senior or Disabled RRFP card. Verifying agencies would sign off that a customer is eligible for the reduced fare program; no additional proof of eligibility would be required for upload to the portal.

- Conduct application assistance electronically. Agencies could fill out the application via the online portal on behalf of customers that might be having difficulties completing the paper application. In this model, agencies would not be verifying eligibility, and would have to upload verifying documents to prove a customer’s eligibility in the reduced fare program. Employees at Metro would verify the documents for eligibility before proceeding with issuing the reduced fare card.

To manage risk of fraud and maintain the integrity of the reduced fare programs, Metro would work with each agency to determine which partnership option is a better fit based on factors such as experience verifying eligibility, turnover, internal capacity, and type of agency operations. For organizations that are unable to or do not to be a verifying agency, application assistance would provide an easier and more accessible way for agencies to support their clients.

Regardless of which type of partnership agreement an agency decides to enter with Metro, agencies and Metro would work in partnership to establish participation guidelines.

### Individuals Served by the Program

This project would reduce barriers for youth, seniors, people with disabilities, and people with low incomes to getting reduced fare ORCA products. This approach would also better serve customers who might otherwise face technological or other difficulties in submitting an online application for themselves.

Each type of verifying agency would likely primarily serve specific populations. For example, Harborview Medical Center currently serves people with disabilities as the sole evaluator for eligibility in Access Transportation, Metro’s ADA Paratransit program. As such, Harborview would likely primarily reach people with disabilities and seniors. LIFT agencies would continue to primarily serve people with low incomes but may also serve youth and seniors. DSHS locations would serve a variety of customers, including seniors, people with disabilities, and people with low incomes.

### Map of New Locations

A map of locations for this  program can be found below. Appendix D includes the addresses and facility types of all locations.

### Schedule

Metro is currently implementing a capital project to produce the online portal. This is scheduled to be ready for customer use in late 2020. Metro would test this concept in 2020 and fully implement in 2021 if funding is provided in the 2021-2022 budget.

Phase 1 – 2020

Metro anticipates that agencies would start serving customers using the online portal by late 2020. During this phase, startup agencies would help Metro refine the enrollment process, work out bugs in the portal, and conduct outreach for agencies that would participate in Phase 2.

Phase 2 – 2021

In Phase 2, Metro would be able to roll out additional agency verification locations as well as new electronic assistance partners. Metro plans to have additional agency verification locations by end of Quarter 2 of 2021. Metro would continue to add agencies as verifying agencies or electronic assistance partners on a quarterly basis through 2022. Once enrollment of additional agencies slows down, Metro would add agencies on a rolling basis.

Next Generation ORCA - 2022

The online portal will continue to operate alongside Next Generation ORCA that will be launched in 2022. Next Generation ORCA will have technological updates that might enhance back-end processes of the online portal but will not replace the online portal.

## Develop a Program to Expand Distribution through Schools

Feedback from teenagers and parents revealed that it would be most convenient if more ORCA cards were available in schools. This approach could also include transit education within the school environment to help the region grow the next generation of transit riders.

### Description

In this strategy, Metro would work with school districts in King County to build a comprehensive approach to distribute more ORCA cards through schools. The goal would be to 1) provide youth cards to every student who wanted one and 2) launch a comprehensive transit education program. Metro would build on lessons learned from past and current programs, and potentially incentivize card uptake by including a small number of trips or card value on each card.

As a first step, Metro would work to identify the resources needed to ensure effective program delivery, potential fare subsidy or foregone revenue needed to support this program, and a roll-out strategy prioritizing delivery over time to the highest-need schools and districts. This program development work would inform a future supplemental budget request.

This strategy would build on Metro’s current efforts:

Passport Program. There are nearly 300,000 public school students in King County. Metro currently works with the school districts to offer either schoolyear or annual transit passes through its Passport program. About 18,000 of these students receive school-year transit passes, and 9,000 receive annual passes. School districts generally participate in this program if Metro service offers a robust and cost-effective transportation alternative to standard “yellow bus services” for those students who do not live close enough to school to walk. School districts are reimbursed by the State for the cost of either passes or yellow bus service. See the map further down in section “Map”for a map of King County school districts and Appendix E for a list of Metro’s school contracts for the 2019-2020 school year.

State-funded pilots. In the past two years, Metro also has partnered with school districts to explore and pilot regional distribution of preloaded Youth ORCA cards and a Summer ORCA Pass Pilot:

- Youth ORCA E-Purse $10 regional distribution: King County Metro contracted with Hopelink to execute a Washington state Youth ORCA Transit Coordination grant to distribute $10 pre-loaded Youth ORCA cards and transit education materials to teenagers in King County. About 6,000 Youth cards were distributed through school districts, high schools, youth-serving organizations, and individual requests generated through a targeted marketing campaign. Of the 6,000 cards distributed roughly 54% were used on transit on nearly 50,000 trips and 11% were reloaded with funds, for a nearly of $37,000 loaded for additional trips.

- Summer Youth ORCA Pass Pilot: A Washington state budget proviso funded a 3 -year Summer ORCA Program to distribute unlimited regional ORCA passes to income-qualified high school students in three school districts for three summers. The program distributed an average of 1,500 cards to  8th - 12th grade students qualified for free or reduced-price lunch across 32 schools. Participants record an average of 73,000 trips over the summer, for an average of 16 trips per month per student. The fare cost is about $56 per participant over the summer and the pilot is being evaluated for expansion in 2021.

- Both programs received a positive response from students, parents, and school districts.

### Estimated Program Costs and Revenues

One FTE for a Transportation Planner or Project/Program Manager would planner would lead efforts to work with school districts to develop a potential program, including developing and distributing marketing materials, conducting outreach to schools and districts, and tracking distribution and use of cards. Support Services & Materials includes funding for additional outreach and program development work, draft materials design, and costs of the cards themselves. Projected revenue is based on a conservative assumption that half of all cards issued reload $20 one time per year.

Projected Net Program Costs

| Net Impact | Y 2019-20 | Y 2021-22 | Y 2023-24 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Expenses | - | $ 394K | $ 406K | $ 419K | $ 1,219K |
| Revenue | - | $ 563K | $ 938K | $ 1,125K | $ 2,626K |
| Net Costs | - | $ (169K) | $ (532K) | $ (706K) | $ (1,407K) |

Operating Expenses

| Expanded School Distribution | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Wages & Benefits (1.0 FTE) | - | $ 244K | $ 251K | $ 259K | $ 754K |
| Support Services & Materials | - | $ 150K | $ 155K | $ 160K | $ 465K |
| Total Expenses | - | $ 394K | $ 406K | $ 419K | $ 1,219K |

Revenue Details

| Revenue Impact | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Projected Revenue | - | $ 563K | $ 938K | $ 1,125K | $ 2,626K |

Ongoing funding for a program would be requested in the 2021-2022 budget or a supplemental budget request. Metro would estimate projected revenues as part of the program development.

### Potential Policy Changes

No policy changes would be required for program development. However, Metro might learn more about policy changes which could increase card uptake and usage through the program development process, including maintaining or eliminating the current $5 card fee.

### Engagement

Metro received input for this strategy through the proviso engagement process, including consultation with youth, parents, and contacts at school districts. Please see the engagement process summary in section IV, part D for more information.

### Marketing

No marketing would be conducted in the program development phase; however, additional outreach and engagement with students, parents and caregivers, school staff, and other stakeholders would inform the development of a marketing strategy that would be conducted as part of program implementation. All marketing for school distribution programs would focus on districts and schools that have the highest percentages of students in free and reduced lunch programs.

### Partnerships

School districts would be essential partners to both program design and program implementation. Large scale card distribution, as experienced in Seattle’s ORCA Opportunity program, places significant burden on school-based administrators. Seattle’s program seeks to address that burden through hiring a contractor to work within the school district. With resources for program development, Metro would engage the school districts and site administrators and develop a program together that can work for all.

### Individuals Served

There are nearly 300,000 public school youth in King County. The program development phase would identify which districts and school ages should be prioritized for implementation, assess likely uptake rates, and compile additional information that would inform Metro’s understanding of the population who could be served by full program implementation. Appendix F shows current demographic information by district.

### Map

A map of school districts in King County is included below.

### Schedule

Metro is anticipating program development to take six months after receipt of funding. Ideally, program implementation could be planned to begin with the 2021-2022 school year.

## Expand Metro’s Neighborhood Pop-Up Program

The third potential strategy is to expand Metro’s Neighborhood Pop-Up Program, so people can obtain any type of ORCA product right in their community. An expansion of one team would provide additional capacity to flexibly deploy resources throughout King County, allowing additional outreach, expanded educational opportunities, and broader access to Metro customer service and support. This strategy is in direct response to the feedback from the engagement process: People want to apply for ORCA cards in locations they already visit such as libraries, community centers, and senior centers. It also responds to feedback that customers would like to purchase a variety of Metro cards and products in their own communities.

This expansion also could improve the customer experience during the transition to ORCA Next Generation. Having a network of established locations where customers can reliably find Metro help and ORCA sales would ease this significant service transition.

### Description

New locations for Metro Neighborhood Pop-Ups would be chosen using a variety of factors. Locations must be publicly accessible, safe and protected from the elements. Metro looks for places where the public would be going to for other services and asked for input from other groups who work with the public, including public health. In expanding the program and setting up regular events in 2019, Metro worked to evenly distribute recurring events throughout King County with prioritization of areas with high Equity Scores and locations that support other King County efforts such as the Burien Community Court. Finally, Metro prioritized locations near transit.

The more than 30 regular current locations receive monthly or bi-monthly visits. The locations include courts, city halls, senior centers, hospitals, community colleges, libraries, public health clinics, and non-profit organizations. The map of current locations is shown below, and the full list of all locations with addresses and facility types is shown in Appendix G.

Future locations would be chosen using the same factors and a continued focus on bringing these services to priority populations and in locations where the needs are greatest. A conceptual map of new locations can be found in the section “Map of New Locations” below.

The strategy to expand the Neighborhood Pop-Up program is reinforced by the positive feedback Metro currently receives. Examples of this feedback can be found in Appendix H.

### Estimated Program Costs and Revenues

Additional FTEs would be required to staff additional Neighborhood Pop-Up teams to establish new locations at regularly scheduled intervals. Revenue projections are based on the trends seen thus far in the set schedule program. Specifically, roughly half of cards issued are to new customers, roughly half of those new customers might add $20 one time to their E-Purse, and only a small percentage of new customers would purchase a monthly pass periodically (roughly every other month). Revenue estimates also include attrition each year.

Projected Net Program Costs

| Net Impact | Y 2019-20 | Y 2021-22 | Y 2023-24 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Expenses | $183K | $462K | $426K | $450K | $1,338K |
| Revenue | $11K | $208K | $516K | $748K | $1,483K |
| Net Costs | $172K | $254K | -$90K | -$298K | -$145K |

Capital Expenses (One-Time)

| Estimated Expenses | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Van Purchase and Configuration | - | $60K | - | - | $60K |

Operating Expenses (Ongoing)

| Estimated Expenses | Y 2019-20 | Y 2021-22 | Y 2023-24 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Wages & Benefits (2.0 FTEs) | $183K | $394K | $418K | $442K | $1,254K |
| Van Operating Costs | - | $3K | $3K | $3K | $9K |
| Materials & Software License | - | $5K | $5K | $5K | $15K |
| Total Operating Expenses | $183K | $402K | $426K | $450K | $1,278K |

Revenue Details

| Revenue Impact | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Projected Revenue | $11K | $208K | $516K | $748K | $1,483K |

### Potential Policy Changes

Metro does not anticipate policy changes needed to expand the Neighborhood Pop-Up program.

### Marketing

The expansion of Neighborhood Pop-Up would be marketed in a variety of ways:

- Supporting partner locations by providing marketing information for them to use through their own networks and communications tools.

- Conducting Metro-sponsored outreach to communities, including social media, email outreach and signage.

- Providing information to community partners, such as Hopelink, who would then distribute to their networks.

### Partnerships

The Neighborhood Pop-Up programs relies on having a network of partners who serve as “hosts.”

### Individuals Served

This program is designed to reach a variety of populations by working in different communities and with diverse locations. Locations are chosen based on a variety of factors, including the Equity Score heat map and the need to reach specific populations. For example, Metro currently schedules events at Senior Centers to reach older adults and at Harborview and the VA to reach those who qualify for a disability RRFP. The Neighborhood Pop-Up event at Kirkland City Hall was specifically scheduled for a day when schools have early release.

### Map of New Locations

A map of proposed new locations is shown below.

## Improve communications to customers about fare products and their use.

Metro  recommends focusing resources to improve communication about ORCA fare products, including the reduced-fare cards, and their use through the use of ongoing engagement and continuous improvement in markering materials. This would respond directly to the feedback that Metro heard in the engagement process: Confusion about the products and the process is a top barrier to greater utilization of these products. Metro can promote products independently but would need to work with the other ORCA partners to improve shared communications such as the card descriptions and applications.

| Estimated Expenses | Y 2019-2020 | Y 2021-2022 | Y 2023-2024 | Y 2025-2026 | Total 2021-26 |
| --- | --- | --- | --- | --- | --- |
| Program Costs - Improved Marketing & Communications | - | - | - | - | - |
| Focus Groups (coordination, consultants, surveys and evaluation) | - | $50K | $52K | $54K | $156K |
| Support Services & Materials | - | $50K | $52K | $54K | $156K |
| Total Expenses | - | $100K | $104K | $108K | $312K |

# Conclusion/Next Steps

The proviso requested an implementation plan to expand the number of locations at which customers can apply for and receive reduced fare ORCA products (RRFP and Youth cards).

Metro evaluated eight potential strategies which could respond to this:

- Create a new, standalone Metro customer service center that would offer ORCA sales.

- Co-locate a customer service center for ORCA sales with a Seattle & King County Public Health Center.

- Delegate ORCA sales to an outside organization and transfer equipment to its custody.

- Offer a program in collaboration with community organizations to provide application assistance to customers.

- Create a network of agencies that provide verification for RRFP and Youth cards.

- Expand Metro’s Neighborhood Pop-Up program.

- Expand institutional distribution through schools.

- Expand institutional distribution in other ways.

The strategies were evaluated against the following criteria:

- Feasibility

- High Impact/Ability to Distribute Many Cards

- Customer Experience

- Alignment with ESJ Strategic Plan

- Alignment with Results of Stakeholder Outreach

This resulted in recommendations of these potential strategies:

- Create a network of agencies that provide verification for RRFP and Youth cards.

- Expand Metro’s Neighborhood Pop-Up program.

- Expand institutional distribution through schools.

- Improve communications to customers about fare products and their use.

# Appendices

## ORCA and RRFP Agencies

| Transit Agency | One Regional Card for All | Reduced Regional Fare Permit |
| --- | --- | --- |
| King County - Transit & Water Taxis | X | X |
| Sound Transit | X | X |
| Washington State Ferries | X | X |
| Pierce County – Transit & Ferries | X | X |
| Community Transit (Snohomish) | X | X |
| Kitsap Transit | X | X |
| Everett Transit | X | X |
| Intercity Transit (Thurston) |  | X |
| Skagit Transit |  | X |
| Mason Transit |  | X |
| Jefferson Transit |  | X |
| Clallam Transit |  | X |
| Grays Harbor Transit |  | X |
| Whatcom Transportation Authority |  | X |

## Equity Analysis: Utilization Gaps in King County

## EMC Research Report on Focus Groups

## Verifying Agencies: Phase 1 Locations - Addresses

Harborview:

- Harborview 	325 9th Ave, Seattle, WA 98104

Public Health:

- Federal Way Store Front	1640 318th Pl, Federal Way, WA 98003

- Catholic Community Services Kent	1229 W Smith St, Kent, WA 98032

- Renton Public Health	3201 NE 7th St, Renton, WA 98056

- ORCA LIFT Office	201 S Jackson St, Seattle, WA 98104

- Downtown Public Health	2124 4th Ave, Seattle, WA 98121

- Columbia Public Health Center	10521 Meridian Ave N, Seattle, WA 98121

- Global to Local	4040 S 188th St, SeaTac, WA 98188

DSHS:

- Auburn CSO	810 28th St NE, Auburn, WA 98002

- Federal Way CSO	616 S 348th St, Federal Way, WA 98003

- King East CSO	805 156th Ave NE, Bellevue, WA 98007

- King South CSO	1313 W Meeker, Kent, WA 98032

- Alderwood CSO	20311 52nd Ave W, Lynnwood, WA 98036

- Renton CSO	500 SW 7th St, Renton, WA 98057

- North Seattle CSO	9600 College Way N, Seattle, WA 98103

- White Center CSO	9650 15th Ave SW, Seattle, WA 98106

- Rainier CSO	3600 S Graham St, Seattle, WA 98118

- Belltown CSO	2106 2nd Ave, Seattle, WA 98121

- Capitol Hill CSO	1700 E Cherry, Seattle, WA 98122

- Everett CSO		840 North Broadway Ave, Everett, WA 98201

- Puyallup CSO	201 West Main St, Puyallup, WA 98371

- Pierce South CSO	1301 E 72nd St, Tacoma, WA 98404

- Pierce North CSO	1949 S State St, Tacoma, WA 98405

- Lakewood CSO	5712 Main St W, Lakewood, WA 98499

- Sky Valley CSO	19705 US-2, Monroe, WA 98272

## Schools Distribution: Contracts for ORCA Cards and Metro Services – 2019-2020 School Year

| District/School | Eligible Students | 2019-20 Total Contract |
| --- | --- | --- |
| Bellevue Public School | 4800 | $649,157 |
| Highline Public Schools | 550 | $167,379 |
| Lakeside/University Prep/Evergreen School (Private) | 1950 | $282,844 |
| Lake Washington Public Schools | 1250 | $203,512 |
| Mercer Island Public Schools | 950 | $74,232 |
| Seattle Public Schools* | 8500 | $1,703,249 |

*The City of Seattle, using FEPP levy funds, covers another 9,153 students in a similar but separate contract totaling $2.8M.  Total 2019 contract is $4,503,249.

## Schools Distribution:  School Districts in King County – Demographic Data

|  | Total Free/Reduced Lunch Students | Total Enrollment | Percentage Free/Reduced Lunch | Estimated middle/high school population | Estimated elementary school population | Current Passes | Current Transit Commute Mode Share in District |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Auburn School District | 8,436 | 16,134 | 52% | 8,443 | 7,691 |  | 6.2% |
| Bellevue School District | 3,605 | 20,431 | 18% | 11,184 | 9,247 | 4,800 | 11.7% |
| Enumclaw School District | 1,234 | 4,052 | 30% | 2,255 | 1,797 |  | 1.4% |
| Excel Public Charter School LEA | 74 | 187 | 40% | 4,173 | 4,173 |  | N/A |
| Federal Way School District | 13,807 | 23,024 | 60% | 11,940 | 11,084 |  | 8.3% |
| Highline School District | 12,400 | 19,730 | 63% | 8,675 | 11,055 | 550 | 11.3% |
| Issaquah School District | 1,554 | 20,312 | 8% | 10,778 | 9,534 |  | 6.8% |
| Kent School District | 13,373 | 27,841 | 48% | 12,624 | 15,217 |  | 6.8% |
| Lake Washington School District | 3,300 | 29,124 | 11% | 14,351 | 14,773 | 1,250 | 8.9% |
| Mercer Island School District | 129 | 4,465 | 3% | 3,536 | 3,536 |  | 8.5% |
| Muckleshoot Indian Tribe | 383 | 464 | 83% | 27,110 | 27,110 |  | N/A |
| Northshore School District | 3,058 | 21,902 | 14% | 9,551 | 12,351 |  | 7.8% |
| Rainier Prep Charter School District | 191 | 251 | 76% | 28 | 28 |  | N/A |
| Renton School District | 7,972 | 15,804 | 50% | 77,44 | 8,060 |  | 8.1% |
| Riverview School District | 461 | 3,355 | 14% | 1,772 | 1,583 |  | 3.5% |
| Seattle Public Schools | 18,443 | 54,221 | 34% | 23,529 | 30,692 | 17,600 | 20.8% |
| Shoreline School District | 2,442 | 9,621 | 25% | 4,560 | 5,061 |  | 14.5% |
| Skykomish School District | 40 | 57 | 70% | 1,495 | 1,495 |  | 1.4% |
| Snoqualmie Valley School District | 698 | 7,073 | 10% | 3,509 | 3,564 |  | 4.5% |
| Summit Public School: Sierra | 89 | 190 | 47% | 95 | 95 |  | N/A |
| Tahoma School District | 947 | 8,346 | 11% | 4,437 | 3,909 |  | 2.8% |
| Tukwila School District | 2,150 | 2,990 | 72% | 1,571 | 1,419 |  | 13.3% |
| Vashon Island School District | 346 | 1,620 | 21% | 4,810 | 4,810 |  | 22.6% |
| Grand Total | 95,132 | 291,556 | 33% | 37995 | 33,992 | 29,000 | 16.9% |

## Metro Neighborhood Pop-Up: Current Locations – Addresses and Facility Types

| Location | Address | Type of Location |
| --- | --- | --- |
| Burien Community Court | 14700 6th Ave SW, Burien, 98166 | Community Center |
| Renton City Hall | 1055 South Grady Way, Renton, 98057 | City Hall |
| Shoreline Hopelink | 17837 Aurora Ave N, Shoreline, WA 98133 | Hopelink/foodbank |
| Bailey Boushay | 2720 E Madison St, Seattle, WA 98112 | Medical |
| Kirkland City Hall | 123 Fifth Avenue Kirkland, Washington 98033 | City Hall |
| Harborview | 325 9th Ave, Seattle, WA 98104 | Medical |
| Auburn Customer Service Center | 1 E Main Street, Auburn, WA 98002 | City Hall |
| Federal Way Storefront | 1640 S. 318th Pl, Ste B, Federal Way, 98003 | Public Health |
| Bellevue Mini City Hall | 15600 NE 8th St #H9, Bellevue, WA 98008 | City Hall |
| Issaquah City Hall | 130 E Sunset Way, Issaquah, 98207 | City Hall |
| Kent City Hall | 220 4th Ave S, Kent, WA 98032 | City Hall |
| VA Hospital | 1660 S. Columbian Way | Medical |
| Redmond City Hall | 15670 NE 85th Street, Redmond, 98073 | City Hall |
| Bothell City Hall | 18415 101st Ave NE, Bothell, WA 98011 | City Hall |
| Green Lake Community Center | 7201 E Green Lake Dr N, Seattle, WA 98115 | Community Center |
| Enumclaw City Hall | 1339 Griffin Avenue, Enumclaw, WA 98022 | City Hall |
| Green River College | 12401 SE 320th St, Auburn, WA 98092 | College |
| Tukwila Library | 14380 Tukwila International Blvd, Tukwila, 98168 | Library |
| South Park Neighborhood Center | 8201 10th Ave S, Seattle, 98108 | Senior Center |
| Lake City Senior Center | 12531 28th Ave NE, Seattle, 98125 | Senior Center |
| Evergreen Hospital | 12040 NE 128th St, Kirkland, 98034 | Medical |
| Skyway CSO | 12629 Renton Ave S, Renton, WA 98178 | Public Location |
| Woodinville Library | 17105 Avondale Rd NE, Woodinville, WA 98072 | Library |
| Ballard Community Center | 6020 28th Ave NW, Seattle, WA 98107 | Community Center |
| Wallingford Senior Center | 4649 Sunnyside Ave N, Ste 140, Seattle, WA 98103 | Senior Center |
| Des Moines Senior Center | 2045 S 216th St, Des Moines, WA 98198 | Senior Center |
| SeaTac Airport | 17801 International Blvd, Seattle, WA 98158 | Airport |
| Bellevue Library | 1111 110th Ave NE, Bellevue, WA 98004 | Library |
| North Bellevue Community Center | 4063 148h Ave NE, Bellevue, WA 98007 | Community Center |
| Federal Way Community Center | 876 S 333rd St, Federal Way, WA 98003 | Community Center |
| Fairwood Library | 17009 140th Ave SE, Renton, WA 98058 | Library |
| Renton Housing Authority | 2900 NE 10th St, Renton, WA 98056 | Public Service |
| Fall City Library | 33415 SE 42nd Pl, Fall City, WA 98024 | Library |
| Shoreline Court | 17500 Midvale Ave N, Shoreline, WA 98133 | City Hall |

## Metro Neighborhood Pop-Up: A Sample of Customer Feedback

“Customer service expertise coupled with collaborative and innovative approach to inform the public about the regional transit system make their services consistent, efficient, and up to date. Since the service improvements started earlier this year, Neighborhood Pop-Up has provided a bi-monthly schedule at Kirkland City Hall that has been growing the number of customers as well as attracting residents from other neighbor cities to Kirkland City Hall for all type of ORCA card needs.”

- Armaghan Baghoori | Transportation Program Coordinator, City of Kirkland

“The partnership … has provided City of Seattle and Seattle Department of Transportation the opportunity to better serve aging adults, particularly seniors of color. Through our Senior Regional Reduced Fare Permit (RRFP) Pilot, Neighborhood Pop-Up in the local senior centers has allowed aging adults in the community to enroll in this essential, underutilized program. By bringing the resource to the community, the barriers seniors experience in signing up is eliminated and Metro’s knowledgeable staff answer any questions community members have. We are thankful for the collaboration and appreciate the collective partnership!”

- Annya Pintak | City of Seattle / South Park and Lake City Senior Centers Program Manager

“. . . We love having the team come here, they are always so professional and friendly.  . . .  Having (Neighborhood Pop-Up) come to Bailey saves us so much time and genuinely facilitates clients getting their bus cards who otherwise would not be able to independently get to Metro and do it themselves. We are satisfied customers and look forward to keeping this valuable relationship going in to the future.”

- Jeff Matheson, Bailey Boushay House

“Thank you so much for offering Neighborhood Pop-ups! This made it possible for me and my disabled teenaged son to get his reduced-fare Orca card when he needed it.  Otherwise, we would have had to wait until summer because of the logistical obstacles of school conflicts and the trip downtown. This is an important program and I hope you continue it.”

- A Redmond parent

“I am so pleased that you folks have been setting up in public spaces in the county for people to get ORCA assistance. All of our students use RRFP cards and it is now so convenient to be able to get them cards without having to travel to Seattle. I hope you are able to expand the program to meet the needs of the community in the future.”

- Jon Goodman, M.Ed., Lake Washington School District) Transition Academy

“ . . . so happy to have the convenience and ease of these mobile locations to conduct business. Michael and Sonya were working the event and they were both very helpful and pleasant. Great program and staff, keep up the good work.”

- Customer comment called in to Customer Information Office

Link to Ordinance 18930

The proviso does not address ORCA LIFT cards. For the remainder of this report, “reduced fare ORCA products” should be read as referring to only the three card types that the proviso addresses.

ORCA LIFT cards appear the same as Adult and Youth cards on the front but show card’s expiration date on the back.

ORCA LIFT cards can be replaced at Neighborhood Pop Up, but cannot be obtained for the first time or renewed there (unless Public Health is there too).

Youth cards cannot be obtained online for the first time but can be replaced online.

ORCA LIFT cards typically must be obtained in person. There is an online portal for King County college students.

Youth whose parents qualify for ORCA LIFT are eligible to receive Youth cardswith the card fee waived.

Access Transportation customers pay $1.75 per trip and can use ORCA pass products through a manual backend process. King County Water Taxi reduced fares are between $2.50 and $4.50, depending on route and fare type.

Only requires to be registered with a youth’s date of birth due to privacy reasons.

Measured by # of (youth, Seniors, or people with disabilities) per square mile of each census tract.

The 2017 Equity Score combines the following three demographics into one attribute by census tract: English proficiency, people of color, and household income. Lower scores mean a wealthier, less diverse community and higher scores mean more diverse, less wealthy community.

Current reduced fare card fees: $5 for new Youth cards and $0 for new LIFT or RRFP cards; $5 to replace Youth cards and $3 to replace LIFT or RRFP cards.

Public Health locations chosen by Public Health as locations most ready to become a verifying agency at launch of the online portal.

Source: 2016-2017 Demographic Information by School, Washington Office of Superintendent of Public Instruction

Source: 2015-2017 5-Year ACS Data, U.S. Census