2020 AMENDMENT TO

CONTRACT FOR FLOOD PREPAREDNESS BROCHURE

GRAPHIC DESIGN AND PROJECT MANAGEMENT

THIS AMENDMENT amends Sections 1, 2 and 3 of the Contract for Flood Preparedness Brochure Graphic Design and Project Management (“Contract”) between the King County Flood Control Zone District, King County, Washington, a municipal corporation of the State of Washington (“District”) and Cocker Fennessy, INC (“Consultant”), as follows:

A.	Amendment of Section 1.  Effective August 20, 2020, Section 1 of the Contract is further amended as follows:

1.	Scope of Services to be Performed by Consultant.  The Consultant shall perform the services described in Exhibit “A” to the 2020 Amendment.  In performing the services, the Consultant shall comply with all federal, state and local laws and regulations applicable to the services.  The Consultant shall perform the services diligently and completely and in accordance with professional standards of conduct and performance.

B.	Amendment of Section 2.  Effective August 20, 2020, Section 2 of the Contract is further amended as follows:

2.	Compensation and Method of Payment.  The Consultant shall request payment for work performed using the billing invoice form at Exhibit “B.”  The District shall pay the Consultant according to the rates set forth in Exhibit “A” to the 2020 Amendment.  The total compensation for services performed in the calendar year 2019 shall not exceed $32,350.

The Consultant shall complete and return to the District Exhibit “C,” Tax Identification Number,” prior to or along with the first billing invoice.

C.	Amendment of Section 3.  Section 3 of the Contract is further amended as follows:

# 3.	Duration of Agreement. This Agreement shall be in force and effect for a period commencing on August 20, 2020 and ending December 31, 2020, unless sooner terminated or extended under the provisions of this Agreement. Time is of the essence of this Agreement in each and all of its provisions in which performance is required.

IN WITNESS WHEREOF, the parties hereto have executed this 2020 Amendment on the dates written below:

COCKER FENNESSY, INC				KING COUNTY FLOOD CONTROL 								ZONE DISTRICT

By: 							By:

CEO/Partner						Dave Upthegrove, Chair

Date:  							Date:

EXHIBIT A

SCOPE OF SERVICES

2020 AMENDMENT

2020-2021 Be Flood Ready Brochure | Proposed Timeline & Budget

Introduction

The following provides a timeline and budget for a “refresh” of the 2020-2021 King County Flood Control District Be Flood Ready Brochure. The budget assumes:

- Developing this year’s brochure using last year’s template, only updating the Chair’s message, individual District articles and current flood season data.

- Preparing one general audience/countywide brochure and up to 5 district specific brochures.

- Does not include production/printing and mailing of the brochure (to be completed by Flood Control District or WLRD).

Timeline

The goal is to have brochures hit homes close to October 1.

| Date | Tasks | Lead |
| --- | --- | --- |
| Mon. Aug. 24 | Provide project examples info, updated Flood Flow information and any other updated brochure content | WLRD/FCD |
| Mon. Aug. 31 | Distribute 1st draft (content) for Flood District review | Consultant |
| Fri. Sept. 4 | Feedback on 1st draft (content) from Flood District (includes WLRD SME review) | FCD |
| Mon. Sept. 7 | Distribute final content draft for Flood District review | Consultant |
| Tues. Sept. 8 | Final approval on content from Flood District | FCD |
| Mon. Sept. 14 | Distribute draft (design) for Flood District review | Consultant |
| Wed. Sept. 16 | Feedback on draft (design) from Flood District | FCD |
| Fri. Sept. 18 | Distribute final draft (design) to Flood District for review | Consultant |
| Mon. Sept 21 | Final approval from Flood District on final brochure | FCD |
| Wed. Sept. 23 | Print ready files to FCD | Consultant |
| Thurs. Sept. 24 | Send brochure files to printer (printed, folded, mailed, etc.) | FCD |
| Week of Oct. 12-16 | Countywide brochures hit homes |  |
| Brochures are translated | End-Oct |  |

Notes

- Timeline reflects Countywide brochure (district specific versions will be drafted in parallel to the extent possible)

- Assumes developing design colors and updating flood chart, etc. while drafting

Budget Estimate

The below not to exceed total estimate (including translations) of $32,350 is developed based on experience from previous brochures. Hours will be billed against the budget and if less time is needed for any tasks, the budget will be preserved.

Content, Project Management, etc.

- $11,000

- Support development of projects to highlight

- Draft updated content – chair’s message, individual district articles and additional content revisions including flood flow information; manage approvals

- Coordinate design and translations of countywide brochure into 21 languages

- Project management including managing timelines, etc.

Design

- $6,000

- Minimal design and development of county wide brochure plus design tweaks and development of 5 district versions.

- Preparation and delivery of final print files for each.

Translations

- $15,350 (this is last year’s total cost; there will likely be some savings as Dynamic Language will analyze new content against last years and any matches would be provided at a reduced rate)

- Translation, independent review, and graphic design of the full brochure from English into Amharic, Arabic, Burmese, Khmer, Simplified Chinese, Traditional Chinese, Farsi, Hindi, Japanese, Korean, Nepali, Oromo, Punjabi, Russian, Samoan, Somali, Spanish (Latin America), Tagalog, Tigrinya, Ukrainian, and Vietnamese: (total of 21 languages)